## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-11
Name of the builder group |  |  |  | M/s.Shree Shivbali Builders Private Limited
Name of the builder company |  |  |  | M/s.Shree Shivbali Builders Private Limited
Name of the Project |  |  |  | Akshay Enclave
Contact Details ( Name & Contact No.) |  |  |  | Mr.Amit Singh 7709545078
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Om : 7709545078
Name / No of the Building |  |  |  | Building No.1 (A & B Wings) & Row House No. 1 & 2
Name / No of the Building as per RERA |  |  |  | Pooja Pride 1 (A & B Wings) & Pooja Pride 2
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P99000030582
Project location details |  | Akshay Enclave, Survey No.189/1/1/2, near Raj Emarald Building, Naigaon East Vasai Link Road, Rajivali, Vasai East, Vasai, Palghar - 401208.
Survey No |  | 189/1/1/2
Road |  | Naigaon East Vasai Link Road |  | Locality/Village |  | Rajivali
City |  | Vasai East |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401208
Nearby Landmark |  | Raj Emarald Building |  | Distance from city centre: |  | 4.00KM from Vasai Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Naigaon East Vasai Link Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Raj Emarald Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.383008,72.856282
Location Link |  | https://goo.gl/maps/H4Wg8aTrRPLbQ8AB6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2793.1
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.86148
Total FSI availaible for the project |  |  |  | 1.9615
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 5478.62
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-Virar City Municipal Corporation
Layout Approval No |  | VVCMC/TP/AMEND/VP/5501/ 465/2022-23 |  |  | Dated | 2022-12-30
Approved Floor plan No. |  | VVCMC/TP/AMEND/VP/5501/ 465/2022-23 |  |  | Dated | 2022-12-30
Commencement Certificate No. |  | VVCMC/TP/RDP/VP-5501/ 464/2022-23 |  |  | Dated | 2022-12-30
Valid Up to: Building No. 1 (Wing A & B)= G + 1st to 12th Floor Row House 1 & 2 = Gr + 1st Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 5478.62
Approved no of units |  |  | Flats - 126, Shop = 07, Row House = 02
Approved no of Floors |  |  | Building No. 1 (Wing A & B)= G + 1st to 12th Floor Row House 1 & 2 = Gr + 1st Floor
Proposed no of Floors |  |  | Building No. 1 (Wing A)= G + 1st to 14th Floor
Building No. 1 (Wing B)= G + 1st to 14th Floor
Row House 1 & 2 = Gr + 1st Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Granite Kitchen Platform, Decorative Entrance, Landscaping & Garden, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 1 (Wing A)= G + 1st to 14th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 5 Floor, External Plaster upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 5 Floor, External Plaster upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 47.73% |  | 72.36% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 11 | 73.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 8 | 57.14% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 5 | 35.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Building No. 1 (Wing B)= G + 1st to 14th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 2 Floor, External Plaster upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 8 Floor, Internal Plaster upto 2 Floor, External Plaster upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 46.12% |  | 71.29% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 11 | 73.33% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 8 | 57.14% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 2 | 14.29% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Row House 1 & 2 = Gr + 1st Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 0.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000 |  |  | rate 6000 by shailesh cost sheet n verbal on 12/03/2025
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000 |  |  | Shop Rate 10000 11/02/2025
Society Charges |  |  |  |  | 1,00,000/-
Recommended rate of Parking |  |  |  |  | 1,50,000/-
Distressed valuation of the Property |  |  |  |  | 4800
Commercia1 Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A Shops |  | 7 |  | 1537.4221 |  | 2306.1332
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (A Wing) |  | 67 |  | 24428.8711 |  | 35421.8631
Building No.1 (B Wing) |  | 59 |  | 21908.7227 |  | 31767.6479
Row House |  | 2 |  | 1991.7813 |  | 3005.1952
Total |  | 128 |  | 48329.3751 |  | 70194.7062 |  | 93
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No. 1 | [14 empty] | 10.764
Wing A
Ground Floor For Commercial, Entrance Lobby & Parking
1 |  | Shop | 84.2821 | 0 | 84.2821 | 0 | 126.4232 | 7.5625
2 |  | Shop | 126.5846 | 0 | 126.5846 | 0 | 189.877
3 |  | Shop | 252.8464 | 0 | 252.8464 | 0 | 379.2695 | 23.106
4 |  | Shop | 383.5213 | 0 | 383.5213 | 0 | 575.282
5 |  | Shop | 187.4012 | 0 | 187.4012 | 0 | 281.1019
6 |  | Shop | 288.4752 | 0 | 288.4752 | 0 | 432.7128
7 |  | Shop | 214.3112 | 0 | 214.3112 | 0 | 321.4669
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | Encl Balcony + Chajja Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Building No. 1
Wing A
1st to 6th Floor
1 |  | 1BHK | 282.3397 | 94.5886 | 376.9284 | 0 | 546.5461 | 25.5825 | 3.1625 | 25.5825 | 3.1625
2 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
3 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
4 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
5 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
6 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
7th Floor
1 |  | 1BHK | 282.3397 | 94.5886 | 376.9284 | 0 | 546.5461
2 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
3 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
4 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
5 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
6 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
8th to 12th Floor
1 |  | 1BHK | 282.3397 | 94.5886 | 376.9284 | 0 | 546.5461
2 |  | 1RK | 199.5646 | 69.4278 | 268.9924 | 0 | 390.0389
3 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
4 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
5 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
Wing B
1st to 6th Floor
1 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
2 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
3 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
4 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
5 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
7th Floor (Part Refuge Area)
1 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
2 |  | Refuge Area
3 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
4 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
5 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
8th to 12th Floor
1 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
2 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
3 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
4 |  | 1BHK | 282.3397 | 87.1884 | 369.5281 | 0 | 535.8158
5 |  | 1BHK | 282.3397 | 91.6285 | 373.9683 | 0 | 542.254
Row House |  | Description | Carpet area | Varandah + AF Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Row House 1
Gr + 1st Floor
1 |  | 2.5BHK | 886.9052 | 108.9855 | 995.8907 | 117.1123 | 1502.5976
Row House 2
Gr + 1st Floor
1 |  | 2.5BHK | 886.9052 | 108.9855 | 995.8907 | 117.1123 | 1502.5976
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.1 (A Wing)
Ground Floor
1 |  | 1BHK | 309.0883 | 0 | 650 | Ground Floor |  |  | 2.103
2 |  | 1RK | 216.464 | 0 | 410 | Ground Floor |  |  | 1.8941
3 |  | 1RK | 228.143 | 0 | 410 | Ground Floor |  |  | 1.7971
4 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor |  |  | 2.1037
5 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor |  |  | 2.1037
1st to 4th Floor
101 to 401 |  | 1BHK | 376.9284 | 0 | 650 | 1st to 4th Floor |  |  | 1.7245 |  |  | 101 to 401 | 101 | 401
102 to 402 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor |  |  | 1.7381 |  |  | 102 to 402 | 102 | 402
103 to 403 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor |  |  | 1.759 |  |  | 103 to 403 | 103 | 403
104 to 404 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor |  |  | 1.759 |  |  | 104 to 404 | 104 | 404
105 to 405 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor |  |  | 1.759 |  |  | 105 to 405 | 105 | 405
106 to 406 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor |  |  | 1.7381 |  |  | 106 to 406 | 106 | 406
Building No.1 (B Wing)
Ground Floor
1 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
2 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
3 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
4 |  | 1BHK | 309.0883 | 0 | 650 | Ground Floor
1st to 4th Floor
101 to 401 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor | [5 empty] | 101 to 401 | 101 | 401
102 to 402 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 102 to 402 | 102 | 402
103 to 403 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 103 to 403 | 103 | 403
104 to 404 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 104 to 404 | 104 | 404
105 to 405 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor | [5 empty] | 105 to 405 | 105 | 405
Building No.2
Ground Floor
1 |  | 1BHK | 309.0883 | 0 | 650 | Ground Floor
2 |  | 1BHK | 309.0883 | 0 | 650 | Ground Floor
3 |  | 1RK | 226.2055 | 0 | 410 | Ground Floor
4 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
5 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
6 |  | 1RK | 226.2055 | 0 | 410 | Ground Floor
7 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
8 |  | 1BHK | 308.9806 | 0 | 650 | Ground Floor
1st to 4th Floor
101 to 401 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 101 to 401 | 101 | 401
102 to 402 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 102 to 402 | 102 | 402
103 to 403 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 103 to 403 | 103 | 403
104 to 404 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor | [5 empty] | 104 to 404 | 104 | 404
105 to 405 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor | [5 empty] | 105 to 405 | 105 | 405
106 to 406 |  | 1BHK | 373.9683 | 0 | 650 | 1st to 4th Floor | [5 empty] | 106 to 406 | 106 | 406
107 to 407 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 107 to 407 | 107 | 407
108 to 408 |  | 1BHK | 369.5281 | 0 | 650 | 1st to 4th Floor | [5 empty] | 108 to 408 | 108 | 408
Remarks:
1 | Construction work is in process at the time of Visit. Internal visit not allowed.
2 | We considered Saleable area of Flat as per Builder area Sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We have considered proposed No. of Floor for Stage Calculation.
5 | We considered Gross carpet area For Flats= Net carpet + Enclose balcony + Chajja Area. We considered Gross carpet area For Row House = Net carpet + Varandah + AF Area.
6 | We have considered rate by verifying it from market inquire.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | Car parking is subjected to authentic documentation.
9 | We have updated revised approved CC & Plans (on 31/03/2024).
10 | Building No. 1 Wing A has 06 flats from the 1st to the 7th floor, but only 05 flats from the 8th to the 12th floor (01 flat has been reduced).
11 | Since Row House No. 1 & 2 have received CC on 30/12/2022, but as of construction work is not started.
12 | Recommended Rates / Other charges of the Property have been revised on 12/03/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Akshay Enclave
Layout :
Google Map :
Formulas:
Rajivali = [Rajivali, row above]
1B
1A
1B
Building No. 1
Wing A
Building No. 1
Wing B
Row House 1 & 2
Bldg1 (A)
Bldg1 (B)
Bldg1 (A)
Bldg1 (A)
Bldg1 (B)
Note on H140: SACHIN: Give loading of 50% for A Category
Note on H184: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 1bhk | 370 | 650 | 5076.9231 | 3300000
Magic Brick |  | 1bhk | 375 | 650 | 5384.6154 | 3500000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
housing |  | 1rk | 228 | 410 | 3365.8537 | 1380000
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted