## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-14
Name of the builder group |  |  |  |  | M/s.Samarth Sai Builders & Developers
Name of the builder company |  |  |  |  | M/s.Samarth Sai Builders & Developers
Name of the Project |  |  |  |  | Seasons Sahara
Name of the Building |  |  |  |  | Seasons Sahara Building No.2
Contact Details ( Name & Contact No.) |  |  |  |  | 9022744227
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Ms. Kartiki 9137223230
Name / No of the Building |  |  |  |  | Building No.2
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC.
RERA No. |  |  |  |  | P51700025218
Project location details |  | Seasons Sahara, Survey No.S.No.24, H.No.2 & 3 At village Adivli Dokli S.No.34, H.No.9, 10, 11, 12, 14, 15 At village Pisavli, Malangad Road, Pisavli & Adivli Dokli , Kalyan, Ambernath, Thane.
Survey No |  | S.No.24, H.No.2 & 3 At village Adivli Dokli S.No.34, H.No.9, 10, 11, 12, 14, 15 At village Pisavli
Road |  | Malangad Road |  |  | Locality/Village |  | Pisavli & Adivli Dokli
City |  | Kalyan |  |  | District |  | Thane
Taluka |  | Ambernath |  |  | Pin Code |  | 421306
Near by Landmark |  | Aryan apartment |  |  | Distance from city centre: |  | About 5.2Km from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Building |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.2131 |  | Longitude |  | 73.1281
Location Link |  | https://goo.gl/maps/7K8MEAs196mSqUTV7
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 8572.81
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.56146
Total FSI availaible for the project |  |  |  |  | 1.5615
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 13386.1
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | KDMP/NRV/BP/27GAVE/2018-19/22/171 |  |  |  | Dated | 2020-03-03
Approved Floor plan No. |  | KDMP/NRV/BP/27GAVE/2018-19/22/171 |  |  |  | Dated | 2020-03-03
Commencement Certificate No. |  | KDMP/NRV/BP/27GAVE/2018-19/22/171 Valid Up to: Blg No.2 = Stilt + 1st To 15th Floors |  |  |  | Dated | 2020-03-03
O. Certificate No.: Approved upto : |  | KDMC/TPD/CC/27Village/431 Gr + 1st to 15th Floor Tenaments = 120 |  |  | Date of approval: | Dated | 2023-03-01 | NA
Commencement date of construction |  |  | 43893 |  | Expected Completion |  | Completed
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 13386.1 |  | Approved no of units |  | Flats = 110
Approved no of Floors |  | Stilt + 1st to 15th Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 58 Years
Material laying at Site: Nothing
Construction details:
Construction details: |  | Building No.2 = Stilt + 1st to 15th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 15
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% |  | 100% |  | 100% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% | [5 empty] | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% | [5 empty] | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% | [5 empty] | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 15 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 15 | 100% | [5 empty] | Plinth in process | 11.25
Possession |  | 15 | 100% | [5 empty] | Plinth completed | 15
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) Development charges, Club house charges, Other charges & Floor rise are all included. | [5 empty] | 6600
Recommended rate of Parking | [5 empty] | 200000/-
Distressed valuation of the Property | [5 empty] | 5280
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No.2 |  | 110 | 53452.3556 |  |  | 85189.3595
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. (As per Approved plan) |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.2
Ground Floor is For Parking
1 |  | 3BHK (Duplex Flat) | 836.8472 |  | 0 | 1305.4816 | N | Ground Floor
2 |  | 3BHK (Duplex Flat) | 860.1781 |  | 0 | 1341.8779 | N
1st Floor
1 |  | 1BHK | 391.2714 |  | 0 | 645 | N | 1st Floor
2 |  | 1BHK | 391.2714 |  | 0 | 645 | N
3 |  | 2BHK | 566.4017 |  | 0 | 888 | N
4 |  | 1BHK | 391.2714 |  | 0 | 645 | N
5 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  | Index II
6 |  | 2BHK | 604.0488 |  | 0 | 930 | N |  |  | 4836.5591
2nd to 5th Floor
1 |  | 1BHK | 391.2714 |  | 0 | 645 | N | 2nd to 5th Floor |  |  | 4257000 | 4319500
2 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  |  | 4257000 | 4319500
3 |  | 2BHK | 566.4017 |  | 0 | 888 | N |  |  |  | 5860800 | 5923300
4 |  | 2BHK | 566.4017 |  | 0 | 888 | N |  |  |  | 5860800 | 5923300
5 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  |  | 4257000 | 4319500
6 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  |  | 4257000 | 4319500
7 |  | 2BHK | 604.0488 |  | 0 | 930 | N |  |  |  | 6138000 | 6200500
8 |  | 2BHK | 604.0488 |  | 0 | 930 | N |  |  |  | 6138000 | 6200500
6th to 15th Floor
1 |  | 1BHK | 391.2714 |  | 0 | 645 | N | 6th to 15th Floor |  | Index II
2 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  | 6046.5116
3 |  | Open Terrace on 6th Floor | [7 empty] | 5292.9412
4 |  | 2BHK | 566.4017 |  | 0 | 888 | N |  |  | 5066.4414
5 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  | 6067.3829
6 |  | 1BHK | 391.2714 |  | 0 | 645 | N |  |  | 5871.9054
7 |  | 2BHK | 604.0488 |  | 0 | 930 | N |  |  |  | 6236.5591
8 |  | 2BHK | 604.0488 |  | 0 | 930 | N |  |  | 4836.5591
Remarks:
1. All work completed. OC received. 2. We considered Saleable area as per Builder saleable area. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area. 5. We considered given rate verify by market inquire. 6. Car parking is subjected to authentic documentation. 7. As per approved plans, Flat No.3 from 6th Floor is Terrace area and void space on 7th to 15th Floor But As per site visit, we notice that Flat No.3 from 6th Floor upto 15th Floor is constructed. So, please provide revised approved Plans. 8. We have updated approved OC from RERA site on 19/01/2024. 7. On site, we meet Arun - 9699151500.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
Inspected By : |  | Krishna Kambali |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Seasons Sahara
Google Map :
Formulas:
Pisavli & Adivli Dokli = [Pisavli & Adivli Dokli, row above]
Building No.2

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 15
Particulars | total floor | 15
plinth | 10 | 10 | 100%
slab | 16 | 16 | 100% |  | Parking |  | Rate
Bricks | 15 | 11 | 73.33% |  | Palghar |  | 100000/-
plaster | 15 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 15 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 15 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 15 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 11 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 11 | 0 | 0 | 0 | 0
Bricks | 11 | 11
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 61% | 71% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
05/10/2020. | Pratiksha | We considered Flat rate as per Builder cost sheet (Including all Other charges).

## Valuation
05/10/2020. | Pratiksha | Market Research Data
|  | Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
|  | Magic Brick | Season Sahara | 1BHK | 429 | 650 | 5538.4615 | 3600000
|  | Magic Brick | Season Sahara | 2BHK | 583 | 890 | 5595.5056 | 4980000
|  | Housing | Season Sahara | 1BHK | 314 | 650 | 5769.2308 | 3750000
|  | Housing | Season Sahara | 1BHK | 313 | 650 | 5692.3077 | 3700000
|  | Housing | Season Sahara | 2BHK | 583 | 890 | 5808.9888 | 5170000
|  | Housing | Season Sahara | 2BHK | 606 | 915 | 5810.929 | 5317000
|  | ProoTiger | Season Sahara | 1BHK | 313 | 650 | 5692.3077 | 3700000
|  | ProoTiger | Season Sahara | 2BHK | 470 | 890 | 5974.1573 | 5317000
|  | Average |  |  |  |  | 5735.236
|  | Valuation Adopted |  |  |  |  | 5700

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.05 | 3.5 | 14.175 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.1 | 2.35 | 4.935 | CB | 2.4 | 0.25 | 0.6 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.75 | 7.5625 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.75 | 3.1 | 8.525 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.3 | 1.8 | 2.34 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.3 | 1.8 | 2.34 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 3.05 | 3.05 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 462.0716 | 42.9275 |  |  | 6.4584 | 0.6 |  | 0 | 0
|  |  | 468.53 | 43.5275
26.77
42.3525