## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-09
Name of the builder group |  |  |  | Godrej Projects Development Ltd
Name of the builder company |  |  |  | Godrej Projects Development Ltd
Name of the Project |  |  |  | Godrej Horizon Phase I
Contact Details ( Name & Contact No.) |  |  |  | 9812511860
Name / No of the Building |  |  |  | Phase I = Tower 1 (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Phase I = P51900034851
Project location details |  | Proposed Redevelopment Of Propoerty Known As Azad Nagar, Bearing C.T.S. No.437(pt),335(pt) ,338(pt),339(pt), 340(pt),341(pt), 342(pt), 346(pt), 347(pt), 348(pt), 350(pt),351(pt), 352(pt), 353(pt), 354(pt), 355(pt), 356 (Pt), Wadala (W), Mumbai - 31.
CTS No |  | 437(pt),335(pt) ,338(pt),339(pt), 340(pt),341(pt), 342(pt), 346(pt), 347(pt), 348(pt), 350(pt),351(pt), 352(pt), 353(pt), 354(pt), 355(pt), 356 (Pt)
Locality |  | Azad Nagar
Road |  | Rafi Ahmed Kidwai |  | Village |  | Wadala
City |  | Wadala West |  | District |  | Mumbai
Taluka |  | Mumbai |  | Pin Code |  | 400031
Nearby Landmark |  | Vijay Niwas |  | Distance from city centre: |  | 500 M from Wadala Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Pardhandas House
West | NA | NA |  |  | Amardeep Building
North | NA | NA |  |  | Railway Track
South | NA | NA |  |  | Rafi Ahmed Kidwai Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.013633,72.856078 | [6 empty] | x
Location Link |  | https://goo.gl/maps/yeQFyZFCTEFPzjfw9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 30443
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 0.53807
Total FSI availaible for the project |  |  |  | 3.5381
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 107709.61
Total number of Buildings |  |  |  | 2 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation Of Greater Mumbai
Layout Approval No |  | P-9221/2021/(354 And Other)/F/North/DADAR-NAIGAON |  |  | Dated | 2023-03-03
Approved Floor plan No. |  | P-9221/2021/(354 And Other)/F/North/DADAR-NAIGAON |  |  | Dated | 2023-03-03
Commencement-CC No Valid Up to: |  | P-9221/2021/(354 And Other)/F/North/DADARNAIGAON/FCC/1/Amend |  |  | Dated | 2024-10-17
|  | This Further C. C. Is Extended Upto Top Of 40th Floor For Sale Tower-1 Wing ‘A & B’ And Further C.C. Is Issued Upto Top Of 44th Floor For Sale Tower-2 Wing ‘A & B’ As Per Last Approved Plan Dated. 18.07.2023 Subject To Taking All Preecautions During Construction In Regards Of Air Polution Guidlines Issued U/No. Mgc/F/1102 Dtd. 25.10.2023 And D.O.No. Cap-2023/Cr-170/Tc-2 Dtd. 27.10.2023. |  |  | Valid Upto Date | 2025-10-16
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 107709.61 |  |  |  |  | 35839.8
Approved no of units |  |  | Flats - 400
Approved no of Floors |  |  | Tower 1 (Wing A & B) = B + G + 1st to 44th Floor
Proposed no of Floors |  |  | Tower 1 (Wing A & B) = B + G + 1st to 44th Floor
Expected Completion |  |  | As per RERA - Phase I = 31/05/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Walkway, Terraced Pool, Gym, Kids Playing Area, Chess Court, Jogging Track, Green Surrounding, Badminton Court
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 1 (Wing A & B) = B + G + 1st to 44th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 30 Floor, External Plaster upto 28 Floor Completed | , RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 30 Floor, External Plaster upto 28 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 44 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 41 Slab, Brickwork upto 40 Floor, Internal Plaster upto 30 Floor, External Plaster upto 28 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 11
Excavation |  | 44 | 100% | 64.74% |  | 83.47% |  | Excavation in process | 22
Plinth |  | 44 | 100% |  |  |  |  | Excavation Completed | 44 |  | 11
RCC (Including podiums) |  | 41 | 91.11% |  |  |  |  | Footing in Process | 11 | 32.12
Brickwork | Brickwork & Internal Plaster | 40 | 90.91% |  |  |  |  | Footing Completed | 22
Internal Plaster | Brickwork & Internal Plaster | 30 | 68.18% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28 | 63.64% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 33
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 44
Construction details: |  | Tower 1 (Wing B) = B + G + 1st to 44th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 19.5 Floor, External Plaster upto 19.5 Floor Completed | , RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 19.5 Floor, External Plaster upto 19.5 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 44 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 19.5 Floor, External Plaster upto 19.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 11
Excavation |  | 44 | 100% | 46.19% |  | 70.39% |  | Excavation in process | 22
Plinth |  | 44 | 100% |  |  |  |  | Excavation Completed | 44 |  | 11
RCC (Including podiums) |  | 27 | 60% |  |  |  |  | Footing in Process | 11
Brickwork | Brickwork & Internal Plaster | 26 | 59.09% |  |  |  |  | Footing Completed | 22
Internal Plaster | Brickwork & Internal Plaster | 19.5 | 44.32% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 19.5 | 44.32% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 33
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 44
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 26500 |  |  | 25000 to 25700 & OC |  | Sanket | Cost sheet | 2023-06-14
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from 4th Floor |  |  |  |  | 75 |  |  | 25,700 & 26500 | 2024-03-14 | Trupti
Development Charges
Legal Charges |  |  |  |  | 25000
LUC Charges |  |  |  |  | 450000
Corpus Fund |  |  |  |  | 75000
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 70000
Society Formation Charges |  |  |  |  | 20000
Advance Maintenance Charges |  |  |  |  | 225000
Recommended rate of Parking |  |  |  |  | 1000000
Distressed valuation of the Property |  |  |  |  | 21200
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Phase I Tower 1 | Wing A | 200 |  | 165538.372 |  | 264861.3951
| Wing B | 200 |  | 165371.4223 |  | 264594.2757
Total |  | 400 |  | 330909.7943 |  | 529455.6708
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Phase I
Tower 1
Wing A
Basement For Tanks
Ground Floor For parking, Society Office & Common Electric Room & Letter Box
1st Floor Part Residential | [8 empty] | 10.764
1 |  | 2 | 651.5449 | 0 | 1042.4719 | 1st Floor Part Residential
2 |  | 2 | 657.6804 | 0 | 1052.2886 | 1st Floor Part Residential
3 |  | Double Height Entrance |  |  |  | 1st Floor Part Residential
4 | [5 empty] | 1st Floor Part Residential
5 | [5 empty] | 1st Floor Part Residential
2nd Floor
1 |  | 2 | 651.5449 | 0 | 1042.4719 | 2nd Floor
2 |  | 2 | 657.6804 | 0 | 1052.2886 | 2nd Floor
3 |  | Void |  |  |  | 2nd Floor
4 | [5 empty] | 2nd Floor
5 | [5 empty] | 2nd Floor
3rd to 6th Floor
1 |  | 2 | 651.5449 | 0 | 1042.4719 | 3rd to 6th Floor
2 |  | 2 | 657.6804 | 0 | 1052.2886
3 |  | Void
4
5 |  | 1 | 494.7134 | 0 | 791.5415
7th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 7th Floor (Part Refuge Area)
2 |  | 2 | 659.0797 | 0 | 1054.5276
3 |  | 2 | 695.5697 | 0 | 1112.9115
4 |  | 3 | 1007.8333 | 0 | 1612.5333
5 |  | Refuge Area
8th to 13th & 15th to 20th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 8th to 13th & 15th to 20th Floor
2 |  | 2 | 659.0797 | 0 | 1054.5276
3 |  | 2 | 695.5697 | 0 | 1112.9115
4 |  | 3 | 1007.8333 | 0 | 1612.5333
5 |  | 3 | 1172.6302 | 0 | 1876.2083
14th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 14th Floor (Part Refuge Area)
2 |  | 2 | 659.0797 | 0 | 1054.5276
3 |  | 2 | 695.5697 | 0 | 1112.9115
4 |  | 3 | 1007.8333 | 0 | 1612.5333
5 |  | Refuge Area
21st Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 21st Floor (Part Refuge Area)
2 |  | 2 | 660.6943 | 0 | 1057.1109
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | Refuge Area
22nd to 24th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 22nd to 24th Floor
2 |  | 2 | 660.6943 | 0 | 1057.1109
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | 3 | 1173.8142 | 0 | 1878.1027
25th to 27th, 29th & 30th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 25th to 27th, 29th & 30th Floor
2 |  | 2 | 696.8614 | 0 | 1114.9782
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | 3 | 1173.8142 | 0 | 1878.1027
28th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 28th Floor (Part Refuge Area)
2 |  | 2 | 696.8614 | 0 | 1114.9782
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | Refuge Area
31st to 34th, 36th to 41st, 43rd & 44th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 31st to 34th, 36th to 41st, 43rd & 44th Floor |  | 239668.4611
2 |  | 2 | 698.9065 | 0 | 1118.2504 |  |  | 24155.4611
3 |  | 2 | 699.2294 | 0 | 1118.7671
4 |  | 3 | 1032.3752 | 0 | 1651.8004
5 |  | 3 | 1174.9982 | 0 | 1879.9972
35th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 35th Floor (Part Refuge Area)
2 |  | 2 | 698.9065 | 0 | 1118.2504 | 35th Floor (Part Refuge Area)
3 |  | 2 | 699.2294 | 0 | 1118.7671 | 35th Floor (Part Refuge Area)
4 |  | 3 | 1032.3752 | 0 | 1651.8004 | 35th Floor (Part Refuge Area)
5 |  | Refuge Area
42nd Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 42nd Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 42nd Floor (Part Refuge Area)
3 |  | 2 | 699.2294 | 0 | 1118.7671 | 42nd Floor (Part Refuge Area)
4 |  | 3 | 1032.3752 | 0 | 1651.8004 | 42nd Floor (Part Refuge Area)
5 |  | 3 | 1174.9982 | 0 | 1879.9972 | 42nd Floor (Part Refuge Area)
Wing B
Basement For Tanks
Ground Floor For Double Height Entrance, Meter Room, Multipurpose Hall, Common Electric Room
1st Floor Part Residential
1 |  | 2 | 651.5449 | 0 | 1042.4719 | 1st Floor Part Residential
2 |  | 2 | 657.6804 | 0 | 1052.2886 | 1st Floor Part Residential
3 |  | Double Height Entrance |  |  |  | 1st Floor Part Residential
4 | [5 empty] | 1st Floor Part Residential
5 | [5 empty] | 1st Floor Part Residential
2nd Floor
1 |  | 2 | 651.5449 | 0 | 1042.4719 | 2nd Floor
2 |  | 2 | 657.6804 | 0 | 1052.2886 | 2nd Floor
3 |  | Void |  |  |  | 2nd Floor
4 | [5 empty] | 2nd Floor
5 | [5 empty] | 2nd Floor
3rd to 6th Floor
1 |  | 2 | 651.5449 | 0 | 1042.4719 | 3rd to 6th Floor
2 |  | 2 | 657.6804 | 0 | 1052.2886
3 |  | Void
4
5 |  | 1 | 494.7134 | 0 | 791.5415
7th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 7th Floor (Part Refuge Area)
2 |  | 2 | 659.0797 | 0 | 1054.5276
3 |  | 2 | 695.5697 | 0 | 1112.9115
4 |  | 3 | 1007.8333 | 0 | 1612.5333
5 |  | Refuge Area
8th to 13th & 15th to 20th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 8th to 13th & 15th to 20th Floor
2 |  | 2 | 659.0797 | 0 | 1054.5276
3 |  | 2 | 695.5697 | 0 | 1112.9115
4 |  | 3 | 1007.8333 | 0 | 1612.5333
5 |  | 3 | 1167.5711 | 0 | 1868.1137
14th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 14th Floor (Part Refuge Area)
2 |  | 2 | 659.0797 | 0 | 1054.5276
3 |  | 2 | 695.5697 | 0 | 1112.9115
4 |  | 3 | 1007.8333 | 0 | 1612.5333
5 |  | Refuge Area
21st Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 21st Floor (Part Refuge Area)
2 |  | 2 | 660.6943 | 0 | 1057.1109
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | Refuge Area
22nd to 24th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 22nd to 24th Floor
2 |  | 2 | 660.6943 | 0 | 1057.1109
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | 3 | 1168.7551 | 0 | 1870.0082
25th to 27th, 29th & 30th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 25th to 27th, 29th & 30th Floor
2 |  | 2 | 696.8614 | 0 | 1114.9782
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | 3 | 1168.7551 | 0 | 1870.0082
28th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 28th Floor (Part Refuge Area)
2 |  | 2 | 696.8614 | 0 | 1114.9782
3 |  | 2 | 697.1843 | 0 | 1115.4948
4 |  | 3 | 1011.1702 | 0 | 1617.8723
5 |  | Refuge Area
31st to 34th, 36th to 41st, 43rd & 44th Floor
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 31st to 34th, 36th to 41st, 43rd & 44th Floor |  | 239668.4611
2 |  | 2 | 698.9065 | 0 | 1118.2504 |  |  | 24155.4611
3 |  | 2 | 699.2294 | 0 | 1118.7671
4 |  | 3 | 1032.3752 | 0 | 1651.8004
5 |  | 3 | 1169.9392 | 0 | 1871.9027
35th Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 35th Floor (Part Refuge Area)
2 |  | 2 | 698.9065 | 0 | 1118.2504 | 35th Floor (Part Refuge Area)
3 |  | 2 | 699.2294 | 0 | 1118.7671 | 35th Floor (Part Refuge Area)
4 |  | 3 | 1032.3752 | 0 | 1651.8004 | 35th Floor (Part Refuge Area)
5 |  | Refuge Area
42nd Floor (Part Refuge Area)
1 |  | 2 | 701.4899 | 0 | 1122.3838 | 42nd Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 42nd Floor (Part Refuge Area)
3 |  | 2 | 699.2294 | 0 | 1118.7671 | 42nd Floor (Part Refuge Area)
4 |  | 3 | 1032.3752 | 0 | 1651.8004 | 42nd Floor (Part Refuge Area)
5 |  | 3 | 1169.9392 | 0 | 1871.9027 | 42nd Floor (Part Refuge Area)
Remarks:
* | Construction work is in process at the time of visit. (Internal photo was not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area + Utility Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated Approved Floor Plan & CC of Phase I (on 19/04/2023).
* | Recommended Rates of the Property have been revised on 14/03/2024.
* | We have updated latest CC from MCGM site (On 16/08/2024).
* | We have updated revised approved CC from MCGM site (On 22/11/2024).
* | Provide revised approved plans.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Karan Misal |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
Wing B
PHOTOGRAPHS OF PROPERTY : |  |  | Godrej Horizon Phase I
Layout Plan
Google Map :
Formulas:
Wadala = [Wadala, row above]
Phase I
Phase II
Phase III
A
B
B
A
Shree Azadnagar
Tower 1
Shree Azadnagar
Tower 2
OM Azadnagar

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted