## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-09
Name of the builder group |  |  |  |  | M/s.SRA Project Developers Private Limited
Name of the builder company |  |  |  |  | M/s.SRA Project Developers Private Limited
Name of the Project |  |  |  |  | Vrindavan City (Wing F)
Contect Details ( Name & Contect No.) |  |  |  |  | 9321444470
Name / No of the Building |  |  |  |  | F Wing = Building No. 6 (Type C)
Docouments Provided |  |  |  |  | Approved Plans, CC, Builder Salable Area, Sale Plan, Cost Sheet
RERA No. |  |  |  |  | P99000027989
Project location details |  | Vrindavan City (Wing F), Survey No.28/3, 30/4, 28/3/1 & 30/3, Boisar- Tarapur Road, Kurgoan, Boisar, Palghar.
Survey No |  | 28/3, 30/4, 28/3/1 & 30/3
Road |  | Boisar- Tarapur Road |  |  | Locality/Village |  | Kurgoan
City |  | Boisar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401501
Near by Landmark |  | Shalimar Swayam |  |  | Distance from city centre: |  | About 8.6 Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Internal Road |  | Vrindavan A, B, C |  | Building No.6
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.839596,72.725083
Location Link |  | https://goo.gl/maps/YPMFv2iypEdeRHUMA
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 20375
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 18337.5
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | MHSL/KS.1/T.1/BSP/SR/CR/69/2018. |  |  |  | Dated | 2018-12-01
Approved Floor plan No. |  | MHSL/KS.1/T.1/BSP/SR/CR/69/2018. |  |  |  | Dated | 2018-12-01
Commencement Certificate No. |  | MHSL/KS.1/T.1/BSP/SR/CR/69/2018. Valid Up to: F Wing = Building No. 6 (Type C) = G + 4th Floor |  |  |  | Dated | 2018-12-01 | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2018-12-01 |  | Expected Completion |  | As per RERA-30/04/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2557.63 |  | Approved no of units |  | Flats = 90
Approved no of Floors |  | F Wing = Building No. 6 (Type C) = G + 1st to 4th Floor |  |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | F Wing = Building No. 6 (Type C) = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 76.25% |  | 90% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 25% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3700
Society formation charges | [5 empty] | 60000/-
Recommended rate of Parking | [5 empty] | 100000/-
Development charges | [5 empty] | 90000/-
Distressed valuation of the Property | [5 empty] | 2960
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Wing F |  | 90 | 24408.4464 |  |  | 39150
Total |  | 90 | 24408.4464 |  |  | 39150
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor |  | Index II of 2020
F Wing = Building No. 6 (Type C)
Ground Floor for Residential | [9 empty] | 20.6892
1 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N | Ground Floor for Residential |  | 4.22 |  | 1609500 | 1609500
2 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  |  | 1609500
3 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
4 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 1609500
5 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
6 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
7 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
8 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
9 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
10 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
11 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
12 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  |  |  | 1.6049
13 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
14 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 1653000
15 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 1803000
16 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
17 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
18 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
1st to 4th Floor
101 to 401 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N | 1st to 4th Floor
102 to 402 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
103 to 403 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 2528.7356
104 to 404 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 2471.2644
105 to 405 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 2275.8621
106 to 406 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
107 to 407 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
108 to 408 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
109 to 409 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
110 to 410 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
111 to 411 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N |  |  | 2528.7356
112 to 412 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
113 to 413 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
114 to 414 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
115 to 415 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
116 to 416 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
117 to 417 |  | 1 Room(1RK) | 271.0375 |  | 0 | 435 | N
118 to 418 |  | 1 Room(1RK) | 274.8049 |  | 0 | 435 | N
Remarks:
1. Construction work is in process at the time of Visit. (Slow Speed) 2. We considered Saleable area as per Builder Salable Area Sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. Recommended Rates of the Property have been revised as per market inquire on 14/02/2024. 9. The project has received first CC on 01/12/2018, But construction work is not yet completed. 10. As per RERA, completion period of project Vrindavan City (Wing F) is expired on 30/04/2025 but still project is under construction. 8. On site, we meet Mr.Shakti Singh - 9321444470.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vrindavan City (Wing F)
Google Map :
Formulas:
Kurgoan = [Kurgoan, row above]

## Note
05/06/2020. | Pratiksha | 9. On Site, we meet Mr.Chetan Gawade (9320334470). As per his information, rate is 2689/-
22/09/2020. | Pratiksha
13/10/2020. | DHANASHREE | OLD APF

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Shalimar Swayam | 1BHK | 0 | 520 | 2500 | 1300000
housing | Shalimar Swayam | 1BHK | 0 | 610 | 2500 | 1525000
housing | Shalimar Swayam | 1BHK | 0 | 630 | 2500 | 1575000
housing | Shalimar Swayam | 1BHK | 0 | 640 | 2500 | 1600000
housing | Sai park | 1RK | 232 | 336.4 | 2514.8633 | 846000
housing | Sai park | 1RK | 237 | 343.65 | 2522.9158 | 867000
housing | Sai park | 1RK | 247 | 358.15 | 2524.0821 | 904000
housing | Sai park | 1BHK | 327 | 474.15 | 2520.2995 | 1195000
housing | Sai park | 1BHK | 328 | 475.6 | 2518.9235 | 1198000
housing | Sai park | 1BHK | 342 | 495.9 | 2514.6199 | 1247000
housing | Sai park | 1BHK | 347 | 503.15 | 2514.1608 | 1265000
housing | Sai park | 1BHK | 353 | 511.85 | 2514.4085 | 1287000
housing | Sai park | 1BHK | 366 | 530.7 | 2517.4298 | 1336000
roofandfloor | Sai park | 1BHK | 328 | 475.6 | 3784.693 | 1800000
roofandfloor | Sai park | 1BHK | 353 | 511.85 | 3784.3118 | 1937000
roofandfloor | Sai park | 1BHK | 367 | 532.15 | 3784.6472 | 2014000
Average |  |  | 0 | 0 | 2750.9597
Valuation Adopted |  |  |  |  | 2700

## 6%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 1 | 20% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 8 | 0 | 0 | 0 | 0 | 0
RCC | 8 | 6 |  | Recommended |  | 30 | 6 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 18% | 36% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0