## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 13/08/2025.
Name of the builder group |  |  |  | Ashapura Estates
Name of the builder company |  |  |  | Ashapura Estates
Name of the Project |  |  |  | Ashapura Galaxy
Contact Details ( Name & Contact No.) |  |  |  | 9820620325 / 9323592671
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Prafull : 9619940666
Name / No of the Building |  |  |  | Wing A1, A2, B1, C1
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700045776
Project location details |  | Ashapura Galaxy, Survey No.21 & S.N. 22 Hissa No.4/1, near Krishna Enclave, Ambivli Gaon Road, Vadavali, Vadavali, Ambivli West, Kalyan, Thane - 421102.
Survey No |  | 21 & S.N. 22 Hissa No.4/1
Locality |  | Vadavali
Road |  | Ambivli Gaon Road |  | Village |  | Vadavali
City |  | Ambivli West |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421102
Nearby Landmark |  | Krishna Enclave |  | Distance from city centre: |  | 0.95KM from Ambivli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Krishna Enclave
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2657 |  | Longitude |  | 73.1648
Location Link |  | https://goo.gl/maps/ARN2VFscqmStcBTHA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10622
Permissible FSI |  |  |  | 1.13
Permissible TDR/Paid FSI |  |  |  | 0.32471
Total FSI availaible for the project |  |  |  | 1.4547
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 15451.98
Total number of Buildings |  |  |  | 4 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kalyan-Dombivli Municipal Corporation
Layout Approval No |  | KDMC/TPD/BP/KD/2021-2022/85 |  |  | Dated | 16/03/2022.
Approved Floor plan No. |  | KDMC/TPD/BP/KD/2021-2022/85 |  |  | Dated | 16/03/2022.
Commencement-CC No Valid Up to: |  | KDMC/TPD/BP/KD/2021-2022/85 |  |  | Dated | 16/03/2022.
Wing A1, A2 & B1 = G/St + 1st to 12th Floor Wing C1 = G/St + 1st to 2nd Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 15451.98
Approved no of units |  |  | Flats - 189, Shops -7, Offices -13
Approved no of Floors |  |  | Wing A1, A2 & B1 = G/St + 1st to 12th Floor Wing C1 = G/St + 1st to 2nd Floor
Proposed no of Floors |  |  | Wing A1 = G/St + 1st to 12th Floor
Wing A2 & B1 = G/St + 1st to 12th Floor
Wing C1 = G/St + 1st to 2nd Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A1 = G/St + 1st to 12th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 100% |  | 100% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 12 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 12 | 100% |  |  |  |  | Plinth in process | 9
Possession |  | 12 | 100% |  |  |  |  | Plinth completed | 12
Progress % |  | 100% |  | Disbursement % |  | 100% |  | Plinth completed | 12
Construction details: |  | Wing A2 = G/St + 1st to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 10 Floor, Flooring upto 7 Floor Completed | , External Plaster upto 10 Floor, Flooring upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 10 Floor, Flooring upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 79.17% |  | 92.08% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 13 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 83.33% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 58.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Wing B1 = G/St + 1st to 12th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 1 Slab Completed | , RCC upto 1 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 12 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 1 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 13.08% |  | 47.31% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 1 | 7.692% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Wing C1 = G/St + 1st to 2nd Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 2 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 1
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4800 |  |  |  | 4500 to 4800 | 2023-02-22 | Rushikesh
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 6500
Development Charges |  |  |  |  | 300000 |  |  | DC | 2023-02-09 | cost sheet | Rushikesh
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3840
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing C1 | Shop | 7 |  | 1789.4666 |  | 2773.6732
| Office | 13 |  | 2439.4776 |  | 3781.1903 |  |  |  | rate sheet
Total |  | 20 |  | 4228.9442 |  | 6554.8635 |  |  | 95392.0265 | visitor | market
Residential Area Details : | [9 empty] | 4100 | 4800
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A1 |  | 71 |  | 34906.6402 |  | 52579.223
Wing A2 |  | 71 |  | 34906.6402 |  | 52579.223
Wing B1 |  | 47 |  | 21349.802 |  | 32024.703
Total |  | 189 |  | 91163.0823 |  | 137183.1489
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Wing C1
Ground Floor For Commercial & Parking
1 |  | Shop | 256.1886 | 0 | 397.0923 | Ground Floor For Commercial & Parking
2 |  | Shop | 284.654 | 0 | 441.2137
3 |  | Shop | 281.2633 | 0 | 435.9581
4 |  | Shop | 293.8572 | 0 | 455.4787
5 |  | Shop | 306.4511 | 0 | 474.9992
6 |  | Shop | 183.5262 | 0 | 284.4656
7 |  | Shop | 183.5262 | 0 | 284.4656
1st & 2nd Floor for Commercial
1 |  | Office | 164.2855 | 0 | 254.6426 | 1st & 2nd Floor for Commercial
2 |  | Office | 179.2206 | 0 | 277.7919
3 |  | Office | 164.2855 | 0 | 254.6426
4 |  | Office | 149.189 | 0 | 231.243
5 |  | Office | 162.7517 | 0 | 252.2651
6 |  | Office | 87.1884 | 0 | 135.142
7 |  | Office | 133.6889 | 0 | 207.2178
8 |  | Office | 121.095 | 0 | 187.6972
9 |  | Office | 116.2512 | 0 | 180.1894
10 |  | Office | 623.8599 | 0 | 966.9829
11 |  | Office | 179.2206 | 0 | 277.7919
12 |  | Office | 179.2206 | 0 | 277.7919
13 |  | Office | 179.2206 | 0 | 277.7919
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A1
Ground Floor For Parking
1st, 3rd, 5th, 7th, 9th & 11th Floor For Residential
1 |  | 2 | 647.0779 | 0 | 970.6168 | 1st, 3rd, 5th, 7th, 9th & 11th Floor For Residential |  |  | 46.6625 | 4367775.555
2 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
3 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
4 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
5 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
6 |  | 2 | 647.0779 | 0 | 970.6168 |  |  |  |  | 4367775.555
2nd, 4th, 6th, 10th & 12th Floor | [9 empty] | 0
1 |  | 2 | 648.2673 | 0 | 972.4009 | 2nd, 4th, 6th, 10th & 12th Floor |  |  | 4375804.1535 | 4375804.1535
2 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  | 2714465.52 | 2714465.52
3 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  | 2714465.52 | 2714465.52
4 |  | 1 | 402.143 | 36.5438 | 639.7583 |  |  |  |  | 2878912.53
5 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
6 |  | 2 | 648.2673 | 0 | 972.4009 |  |  |  |  | 4375804.1535
8th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 2 | 648.2673 | 0 | 972.4009 | 8th Floor (Part Refuge Area) |  |  |  | 4375804.1535
2 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
3 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
4 |  | 1 | 402.143 | 36.5438 | 639.7583 |  |  |  |  | 2878912.53
5 |  | Refuge Area | [7 empty] | 0
6 |  | 2 | 648.2673 | 0 | 972.4009 |  |  |  |  | 4375804.1535
Wing A2 | [9 empty] | 0
Ground Floor For Parking | [9 empty] | 0
1st, 3rd, 5th, 7th, 9th to 11th Floor For Residential | [9 empty] | 0
1 |  | 2 | 647.0779 | 0 | 970.6168 | 1st, 3rd, 5th, 7th, 9th to 11th Floor For Residential |  |  | 46.6625 | 4367775.555
2 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
3 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
4 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
5 |  | 1 | 421.3837 | 0 | 632.0755 |  |  |  |  | 2844339.9075
6 |  | 2 | 647.0779 | 0 | 970.6168 |  |  |  |  | 4367775.555
2nd, 4th, 6th, 10th & 12th Floor | [9 empty] | 0
1 |  | 2 | 648.2673 | 0 | 972.4009 | 2nd, 4th, 6th, 10th & 12th Floor |  |  |  | 4375804.1535
2 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
3 |  | 1 | 402.143 | 36.5438 | 639.7583 |  |  |  |  | 2878912.53
4 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
5 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
6 |  | 2 | 648.2673 | 0 | 972.4009 |  |  |  |  | 4375804.1535
8th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 2 | 648.2673 | 0 | 972.4009 | 8th Floor (Part Refuge Area) |  |  |  | 4375804.1535
2 |  | Refuge Area | [7 empty] | 0
3 |  | 1 | 402.143 | 36.5438 | 639.7583 |  |  |  | 2880000 | 2878912.53
4 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
5 |  | 1 | 402.143 | 0 | 603.2146 |  |  |  |  | 2714465.52
6 |  | 2 | 648.2673 | 0 | 972.4009 |  |  |  |  | 4375804.1535
Wing B1 | [9 empty] | 0
Ground Floor For Parking | [9 empty] | 0
1st, 3rd, 5th, 7th, 9th to 11th Floor For Residential | [9 empty] | 0
1 |  | 1 | 467.1038 | 0 | 700.6557 | 1st, 3rd, 5th, 7th, 9th to 11th Floor For Residential |  |  | 30.105 | 3152950.515
2 |  | 1 | 467.1038 | 0 | 700.6557 |  |  |  | 30 | 3152950.515
3 |  | 1 | 467.1038 | 0 | 700.6557 |  |  |  |  | 3152950.515
4 |  | 1 | 467.1038 | 0 | 700.6557 |  |  |  |  | 3152950.515
2nd, 4th, 6th, 10th & 12th Floor | [9 empty] | 0
1 |  | 1 | 440.8396 | 0 | 661.2594 | 2nd, 4th, 6th, 10th & 12th Floor |  |  |  | 2975667.435
2 |  | 1 | 440.8396 | 0 | 661.2594 |  |  |  |  | 2975667.435
3 |  | 1 | 440.8396 | 0 | 661.2594 |  |  |  |  | 2975667.435
4 |  | 1 | 440.8396 | 0 | 661.2594 |  |  |  |  | 2975667.435
8th Floor (Part Refuge Area) | [9 empty] | 0
1 |  | 1 | 440.8396 | 0 | 661.2594 | 8th Floor (Part Refuge Area) |  |  |  | 2975667.435
2 |  | 1 | 440.8396 | 0 | 661.2594 |  |  |  |  | 2975667.435
3 |  | 1 | 440.8396 | 0 | 661.2594 |  |  |  |  | 2975667.435
4 |  | Refuge Area | [7 empty] | 0
Remarks: | [9 empty] | 0
* | Wing A1 = All work completed. Please provide OC. Wing A2 & B1 = Construction is in process at the time of Visit. Wing C1 = Work not yet started. | [8 empty] | 0
* | We have considered Saleable area of Flats as per our Calculation. | [8 empty] | 0
* | We have considered Saleable area of Commercial as per our Calculation. | [8 empty] | 0
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Praful - 9619940666.
* | Since wing C1 have received CC on 16/03/2022, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Krishna Kambali |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ashapura Galaxy
Google Map :

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted