## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-14
Name of the builder group |  |  |  | Luceat Realtors Private Limited
Name of the builder company |  |  |  | Luceat Realtors Private Limited
Name of the Project |  |  |  | Bella
Provided Contact Details (Name & Contact No.) |  |  |  | 9167708076
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Bhagvan wankhede 7021552596
Name / No of the Building |  |  |  | Wing A to D
Docouments Provided |  |  |  | Approved plans & CC
RERA No. |  |  |  | Wing A & B = P51800031973 Wing C & D = P51800029526
Project location details |  | Bella, CTS No.279, 280, 280/1, 282/A, 282/C & 281/A/1/1, near Kalpataru Crest, LBS Marg, , Bhandup, Bhandup (West), Kurla, Mumbai - 400078.
CTS No |  | 279, 280, 280/1, 282/A, 282/C & 281/A/1/1
Locality |  | NA
Road |  | LBS Marg |  | Locality/Village |  | Bhandup
City |  | Bhandup (West) |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400078
Nearby Landmark |  | Kalpataru Crest |  | Distance from city centre: |  | 1.9 KM from Bhandup Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Slum Area
West | NA | Other Plot |  |  | Gopala's Next - Restaurant
North | NA | Existing 12.20 M. W Internal Access Road |  |  | Internal Road
South | NA | Other Plot |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.155940,72.938960
Location Link |  | https://goo.gl/maps/ivcADK5Rsufi3ahXA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7200.56
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.0963
Total FSI availaible for the project |  |  |  | 2.0963
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 15094.6
Total number of Buildings |  |  |  | 04 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | CHE/ES/1674/S/337(NEW) |  |  | Dated | 2024-09-24
Approved Floor plan No. (Basement & 1st to 22nd Floor) |  | CHE/ES/1674/S/337(NEW) |  |  | Dated | 2024-09-24
Approved Floor plan No (Ground Floor) |  | P-23655/2024/S/Ward/BHANDUP-W/342/1 |  |  | Dated | 2024-12-26
Commencement-CC No Valid Up to: |  | CHE/ES/1674/S/337(NEW)/FCC/1/Amend |  |  | Dated | 2023-03-23
[5 empty] | Valid Upto Date | 2023-05-23
Further CC of wing A and wing B is granted up to 18th upper floors as per last approved amended plans dated 21.12.2022 subject to timely renewal of B.G. , SWM NOC, Workmen’s compensation policy and taking precautions during construction work.
Commencement-CC No Valid Up to: |  | CHE/ES/1674/S/337(NEW)/FCC/3/Amend |  |  | Dated | 2024-05-13
[5 empty] | Valid Upto Date | 2024-05-23
Full C.C. is re endorsed for wing ‘C’ & ‘D’ and further C.C. upto 18th floor is granted for wing ‘A’ & ‘B’ as per amended approved plan dated 09.05.2024 by restricting C.C. of 19th to 22nd floor for wing ‘A’ & ‘B’ subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution.
Commencement-CC No Valid Up to: |  | CHE/ES/1674/S/337(NEW)/FCC/4/Amend |  |  | Dated | 2024-10-24
[5 empty] | Valid Upto Date | 2026-05-23
Further C.C. is granted for staircase, lift core, lobby area from 19th floor to terrace floor with OHT on terrace floor of wing ‘A’ & ‘B’ only as per last approved amended plans dated 09.05.2024 subject to timely renewal of B.G. ,SWM NOC, Workmen’s compensation policy and taking precaution during construction work.
Part O. Certificate No.: Approved upto : |  | CHE/ES/1674/S/337(NEW)/OCC/1/New |  |  | Dated | 2024-09-24
Part OC for Wing ‘A’ - Part Basement + Part Ground for shops + part stilt + 1st to 3rd Part Commercial floors Wing ‘C’ - Stilt & part Ground floor + 1st to 22nd upper residential floors Wing ‘D’ -having Ground for shops + part stilt + 1st to 3rd Part Commercial floors + 4th to 22nd upper floor upper residential floors
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 15094.6
Approved no of units |  |  | Sale Flats - 361, I to R Flat - 36 Shops - 12, Offices - 36
Approved no of Floors |  |  | Wing A to D = B + Gr/Stilt + 1st to 22nd Floor
Proposed no of Floors |  |  | Wing A & B = B + Gr/Stilt + 1st to 22nd Floor
Wing C & D = B + Gr/Stilt + 1st to 22nd Floor
Wing D = B + Gr/Stilt + 1st to 22nd Floor
Expected Completion |  |  | As per RERA - Wing A & B = 01/01/2026 Wing C & D = Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Banquet Hall, Fitnesscenter, Roof Top Seating Area, Childern Play Area, Party Lawn, Jogging Track, etc. |  |  |  |  | https://housing.com/in/buy/projects/page/255843-rustomjee-bella-wing-c-and-d-by-rustomjee-builders-in-bhandup-west
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A & B = B + Gr/Stilt + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 13 Floor Completed | , External Plaster upto 20 Floor, Flooring upto 13 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 13 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 80% |  | 92.5% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 90.91% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 59.09% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing C & D = B + Gr/Stilt + 1st to 22nd Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 100% |  | 100% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 22 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 22 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 22 | 100% |  |  |  |  | Plinth in process | 16.5
Possession |  | 22 | 100% |  |  |  |  | Plinth completed | 22
Progress % |  | 100% |  | Disbursement % |  | 100% |  | Plinth completed | 22
Construction details: |  | Wing D = B + Gr/Stilt + 1st to 22nd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 20 Slab, Brickwork upto 10 Floor Completed | , RCC upto 20 Slab, Brickwork upto 10 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 48.19% |  | 73.36% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 20 | 86.96% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 10 | 45.45% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | MIS | Online
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 17500 |  |  | 16471.2814 | 16000 | 16942.5628
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 30000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 22000 | [5 empty] | Rate 17500 Bhargav Case A1503 Verbal on 24/02/2025
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 14000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shop | 6 |  | 1140.5534 |  | 1824.8855
| Office | 18 |  | 4406.5663 |  | 7050.5061 |  | 36
Wing D | Shop | 6 |  | 1140.5534 |  | 1824.8855
| Office | 18 |  | 5135.7197 |  | 8217.1515
Total |  | 48 |  | 11823.3929 |  | 18917.4286
Residential Area Details :(Sale Flat)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 98 |  | 45920.6233 |  | 71176.9661
Wing B |  | 83 |  | 38633.6106 |  | 59882.0964 |  | 101
Wing C |  | 83 |  | 38633.6106 |  | 59882.0964
Wing D |  | 97 |  | 45926.3282 |  | 71185.8088 |  | 397
Total |  | 361 |  | 169114.1728 |  | 262126.9678
Residential Area Details :(I to R Flat)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | 397
Wing B |  | 18 |  | 7697.767 |  | 11931.5388
Wing C |  | 18 |  | 7697.767 |  | 11931.5388
Total |  | 36 |  | 15395.5339 |  | 23863.0776 |  | 18
Grand Total |  | 445 |  | 196333.0996 |  | 304907.474 |  |  | 10.764
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor |  | 1
[5 empty] | 60% |  |  | 24.3086
Building No.1
Wing A
Basement Floor for Parking
Ground Floor for Commercial & Parking
1 |  | Shop | 267.7007 | 0 | 428.3211 | Ground Floor for Commercial & Parking |  | 17.7783
2A |  | Shop | 181.0505 | 0 | 289.6808 |  |  | 1
2B |  | Shop | 149.189 | 0 | 238.7025 |  |  | 33.8782
3 |  | Shop | 153.7099 | 0 | 245.9359
4A |  | Shop | 190.9534 | 0 | 305.5254
4B |  | Shop | 197.95 | 0 | 316.7199
1st Floor
1 |  | Office | 369.0976 | 0 | 590.5561 | 1st Floor
2 |  | Office | 203.009 | 0 | 324.8145 |  |  | 1
3 |  | Office | 169.533 | 0 | 271.2528
4 |  | Office | 214.6342 | 0 | 343.4147
5 |  | Office | 246.8185 | 0 | 394.9096
6 |  | Office | 265.7632 | 0 | 425.2211
2nd Floor
1 |  | Office | 369.0976 | 0 | 590.5561 | 2nd Floor
2 |  | Office | 203.009 | 0 | 324.8145
3 |  | Office | 169.533 | 0 | 271.2528
4 |  | Office | 214.6342 | 0 | 343.4147
5 |  | Office | 246.8185 | 0 | 394.9096
6 |  | Office | 265.7632 | 0 | 425.2211
3rd Floor
1 |  | Office | 369.0976 | 0 | 590.5561 | 3rd Floor
2 |  | Office | 203.009 | 0 | 324.8145
3 |  | Office | 169.533 | 0 | 271.2528
4 |  | Office | 214.6342 | 0 | 343.4147
5 |  | Office | 246.8185 | 0 | 394.9096
6 |  | Office | 265.7632 | 0 | 425.2211
Wing D
Basement Floor for Parking
Ground Floor for Commercial & Parking
1 |  | Shop | 267.7007 | 0 | 428.3211 | Ground Floor for Commercial & Parking
2A |  | Shop | 181.0505 | 0 | 289.6808
2B |  | Shop | 149.189 | 0 | 238.7025
3 |  | Shop | 153.7099 | 0 | 245.9359
4A |  | Shop | 190.9534 | 0 | 305.5254
4B |  | Shop | 197.95 | 0 | 316.7199
1st Floor
1 |  | Office | 417.9661 | 0 | 668.7458 | 1st Floor
2 |  | Office | 340.4653 | 0 | 544.7445
3 |  | Office | 226.2593 | 0 | 362.0148
4 |  | Office | 214.6342 | 0 | 343.4147
5 |  | Office | 246.8185 | 0 | 394.9096
6 |  | Office | 265.7632 | 0 | 425.2211
2nd Floor
1 |  | Office | 417.9661 | 0 | 668.7458 | 2nd Floor
2 |  | Office | 340.4653 | 0 | 544.7445
3 |  | Office | 226.2593 | 0 | 362.0148
4 |  | Office | 214.6342 | 0 | 343.4147
5 |  | Office | 246.8185 | 0 | 394.9096
6 |  | Office | 265.7632 | 0 | 425.2211
3rd Floor
1 |  | Office | 417.9661 | 0 | 668.7458 | 3rd Floor
2 |  | Office | 340.4653 | 0 | 544.7445
3 |  | Office | 226.2593 | 0 | 362.0148
4 |  | Office | 214.6342 | 0 | 343.4147
5 |  | Office | 246.8185 | 0 | 394.9096
6 |  | Office | 265.7632 | 0 | 425.2211
1
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Building No.1 | [7 empty] | 29.0335
Wing A
1st Floor for Residential & Commercial | [7 empty] | 1
1 |  | Commercial Area |  |  |  | 1st Floor for Residential & Commercial
2
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
2nd Floor | [7 empty] | 1
1 |  | Commercial Area |  |  |  | 2nd Floor |  |  | 27.3815
2 | [7 empty] | `
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441 |  |  |  | 19543.4425
3rd Floor | [7 empty] | 1
1 |  | Commercial Area |  |  |  | 3rd Floor |  |  | 16092.1169
2 | [8 empty] | 15192.1289
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
4th Floor for Residential & Fitness Center
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 4th Floor for Residential & Fitness Center |  | 11
2 |  | 1BHK | 403.4347 | 0 | 625.3238 |  |  |  |  | 14
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | Fitness Center
5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor |  | 1
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
11th Floor
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 11th Floor |  | 1
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
20th Floor
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 20th Floor |  | 1
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
8th Floor (Part Refuge Area)
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 8th Floor (Part Refuge Area) |  | 1
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | Refuge Area
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
15th Floor (Part Refuge Area)
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 15th Floor (Part Refuge Area)
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | 1BHK | 417.8585 | 0 | 647.6806
4 |  | Refuge Area
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
Wing B
Basement Floor for Parking
Ground Floor for Parking
1st Floor for Residential
2 |  | 2BHK | 613.4404 | 0 | 950.8326 | 1st Floor for Residential
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | Meter Room
2nd Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 2nd Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
3rd Floor (Part Fitness Center)
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 3rd Floor (Part Fitness Center)
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | Fitness Center
4th Floor
1 |  | Fitness Center |  |  |  | 4th Floor
2 |  | 2BHK | 609.5653 | 0 | 944.8262
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1BHK | 427.6537 | 0 | 662.8633
11th Floor
1 |  | 1BHK | 530.127 | 0 | 821.6968 | 11th Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1BHK | 427.6537 | 0 | 662.8633
20th Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 20th Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1BHK | 427.6537 | 0 | 662.8633
8th Floor (Part Refuge Area)
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | Refuge Area
5 |  | 1BHK | 427.6537 | 0 | 662.8633
15th Floor (Part Refuge Area)
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 15th Floor (Part Refuge Area)
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | Refuge Area
4
5 |  | 1BHK | 427.6537 | 0 | 662.8633
Wing C
Basement Floor for Parking
Ground Floor for Parking
1st Floor for Residential
2 |  | 2BHK | 613.4404 | 0 | 950.8326 | 1st Floor for Residential
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | Meter Room
2nd Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 2nd Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
3rd Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 3rd Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
4th Floor
1 |  | Fitness Center |  |  |  | 4th Floor
2 |  | 2BHK | 609.5653 | 0 | 944.8262
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1BHK | 427.6537 | 0 | 662.8633
11th Floor
1 |  | 1BHK | 530.127 | 0 | 821.6968 | 11th Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1BHK | 427.6537 | 0 | 662.8633
20th Floor
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 20th Floor
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1BHK | 427.6537 | 0 | 662.8633
8th Floor (Part Refuge Area)
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | Refuge Area
5 |  | 1BHK | 427.6537 | 0 | 662.8633
15th Floor (Part Refuge Area)
1 |  | 1.5BHK | 530.127 | 0 | 821.6968 | 15th Floor (Part Refuge Area)
2 |  | 1BHK | 419.9036 | 0 | 650.8506
3 |  | Refuge Area
4
5 |  | 1BHK | 427.6537 | 0 | 662.8633
Wing D
1st Floor for Residential & Commercial
1 |  | Commercial Area |  |  |  | 1st Floor for Residential & Commercial
2
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | Meter Room
2nd Floor
1 |  | Commercial Area |  |  |  | 2nd Floor
2
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
3rd Floor
1 |  | Commercial Area |  |  |  | 3rd Floor
2
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
4th Floor for Residential & Fitness Center
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 4th Floor for Residential & Fitness Center
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
- |  | Fitness Center
5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 5th to 7th, 9th to 10th & 12th to 14th, 16th to 19th, 21st to 22nd Floor
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
11th Floor
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 11th Floor
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | 2BHK | 577.7039 | 0 | 895.441
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
20th Floor
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 20th Floor
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 & 4 |  | 3BHK | 909.8809 | 0 | 1410.3154
5 |  | 1BHK | 529.1582 | 0 | 820.1953
8th Floor (Part Refuge Area)
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | MP Room | 326.4721 | 0 | 506.0318
4 |  | Refuge Area
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
15th Floor (Part Refuge Area)
1 |  | 1.5BHK | 521.1929 | 0 | 807.849 | 15th Floor (Part Refuge Area)
2 |  | 1BHK | 403.4347 | 0 | 625.3238
3 |  | 1BHK | 417.8585 | 0 | 647.6806
4 |  | Refuge Area
5 |  | 1.5BHK | 529.1582 | 0 | 820.1953
Remarks:
* | Wing A = Part OC Received upto 3rd Floor But Construction work is in process at the time of Visit. (Internal photographs not allowed.) Wing B = Construction work is in process at the time of Visit. Wing C & D = All work completed. Part OC received
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We refer latest approved floor plan & CC from MCGM site.
* | Validity of CC is expired on 23/05/2022. So please provide latest CC.
* | We have updated latest CC from MCGM site (On 15/06/2024).
* | We have updated latest CC from MCGM site on 17/12/2024.
* | As per the approved floor plan, out of 397 flats, there are 36 flats that are "I to R" flats. Please check from your end.
* | We have updated latest approved plans & Part OC from MCGM site on 18/02/2025.
* | Recommended Rates of the Property have been revised on 24/02/2025
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nainesh Tambe |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Bella
Layout :
Google Map :
Formulas:
Bhandup = [Bhandup, row above]
Wing A & B
Wing C & D
B
D Wing
A
B
C
D

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted