## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-09
Name of the builder group |  |  |  |  | M/s. Shree Malhar Enterprises
Name of the builder |  |  |  |  | Mr. Kishor Devidas Walhe
Name of the Project |  |  |  |  | Darshan Complex (Type A, B & C)
Contact Details ( Name & Contact No.) |  |  |  |  | 9769696056
RERA No. |  |  |  |  | P99000016305
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | Darshan Complex (Type A, B & C), S. No. 160/95, Navapur Road, Next to MIDC, Pam Tembhi Village, Boisar (W), Palghar 401 501.
S No | 160/95 |  |  | Plot No. | NA | Locality | Pam Tembhi
Road | Navapur Road |  |  |  | District | Palghar
City | Boisar |  |  |  | Pin Code | 401 501
Near by Landmark |  | Pam Naka |  |  | Distance from city centre: |  | About 6.2Km Distance From Boisar Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.791851, 72.713471
Location Link |  | https://goo.gl/maps/XUSX4FLXzXECMtmq6
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 5000
Permissible FSI |  |  |  |  | 0.58
Permissible TDR/Paid FSI |  |  |  |  | N.A
Total FSI availaible for the project |  |  |  |  | N.A
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 2866.03
Total number of Buildings |  |  |  |  | 03 wings
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  |  | Dated | NA
Building plan approval No |  | PJP/GP/Pradhikaran/33 |  |  |  | Dated | 26/06/2017.
C.certificate No |  | PJP/GP/Pradhikaran/33 Valid Up to: (Building No. 2- Type A & B) &(Building No. 2- Type A (Wing C) = Ground + 1st to 2nd Floor |  |  |  | Dated | 26/06/2017.
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 26/06/2017. |  | Expected Completion |  | 2025-12-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2866.03 |  | Approved no of units residential |  |  | NA
Approved no of Floors |  | Building No. 2- Type A & B) = Ground + 1st to 2nd Floor Building No. 2- Type A (Wing C) = Ground + 1st to 2nd Floor |  |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | (Building No. 2- Type A ) = Ground + 1st to 2nd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 2
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% |  | 36.67% |  | 65% |  | Excavation in process | 1
Plinth |  | 2 | 100% | [5 empty] | Excavation Completed | 2
RCC (Including podiums) |  | 2 | 66.67% | [5 empty] | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 1.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 2
Construction details: |  | (Building No. 2- Type B) = Ground + 1st to 2nd Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 2
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% |  | 10% |  | 45% |  | Excavation in process | 1
Plinth |  | 2 | 100% | [5 empty] | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 1.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 2
Construction details: |  | Type A (Wing C) = Ground + 1st to 2nd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 2
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 2 | 100% |  | 87.5% |  | 95% |  | Excavation in process | 1
Plinth |  | 2 | 100% | [5 empty] | Excavation Completed | 2
RCC (Including podiums) |  | 3 | 100% | [5 empty] | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 1.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 2
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 4000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Club Hous Charges | [5 empty] | NA
Development Charges | [5 empty] | 1,00,000/-
Electric/Water Charges | [5 empty] | NA
Mahanagar Gas connection Charges | [5 empty] | NA
Society Formation Charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 1,00,000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 3200
Remarks: 1. Type A (Wing C) = Construction work has incresed as compare to last visited date 11/05/2025. but at the time of visit no labour or no active work found on site. Building No. 2 (Type A) = Construction work was stopped at the time of visit. Work same since visit (24/03/2021). Building No. 2 (Type B) = Construction work is the same since visit (05/05/2024). 2. We considered given rate verify by market inquire. 3. Car parking is subjected to authentic documentation. 4. Since the project has received first CC on 26/06/2017., But construction work of Type A, B & C is under construction. 4. On site, we meet Mr.Vinay Salvi - 8879902646.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Darshan Complex (Type A, B & C)
Google Map :
Bldg No. 02 (Type A)
Type A (Wing C)
Bldg No. 02 (Type A)

## A
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 2
Particulars | total floor | 2
plinth | 10 | 10 | 100%
slab | 3 | 1 | 33.33% |  | Parking |  | Rate
Bricks | 2 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 2 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 2 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 2 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 2 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 13.3333 | 0 | 0 | 0 | 0 | 0
RCC | 13.3333 | 10 |  | Recommended |  | 30 | 10 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 23.33% | 40% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 2
Particulars | total floor | 2
plinth | 10 | 10 | 100%
slab | 3 | 0 | 0% |  | Parking |  | Rate
Bricks | 2 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 2 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 2 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 2 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 2 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 2
Particulars | total floor | 2
plinth | 10 | 10 | 100%
slab | 3 | 3 | 100% |  | Parking |  | Rate
Bricks | 2 | 2 | 100% |  | Palghar |  | 100000/-
plaster | 2 | 1 | 50% |  | Ulwe, karanjade |  | 200000/-
Flooring | 2 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 2 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 2 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 5 | 5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 70% | 80% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-10-16 | Pratiksha
2021-01-05 | Pratiksha
2021-02-28 | Pratiksha

## Valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Darshan Complex |  |  |  |  | 55800000
Magic Brick | [5 empty] | 120000000
Magic Brick | [5 empty] | 76300000
Magic Brick | [5 empty] | 118500000
Magic Brick | [5 empty] | 139000000
99 Acres | [5 empty] | 77400000
99 Acres | [5 empty] | 86300000
Average |  |  |  |  | #DIV/0!
Valuation Adopted |  |  |  |  | 32000

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0