## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 11/08/2025.
Name of the builder group |  |  |  | Mr. Ninath Bhausaheb Shingade
Name of the builder company |  |  |  | Mr. Ninath Bhausaheb Shingade
Name of the Project |  |  |  | Konnark Oasis
Contact Details ( Name & Contact No.) |  |  |  | 7977074609
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Sanjay 7977074609
Name / No of the Building |  |  |  | Building No.1 Building No.2 (Wing A, B, C, D) Building No.3 (Wing A, B ) Building No.4 (Wing A, B ) Building No.5 Building No.6 (Wing A & B) Building No.7 (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000031755
Project location details |  | Konnark Oasis, Gut No.4/6 & 5/1, near Konnark Heavens, Internal Road, Chindharan, Taloja, Panvel, Raigad - 410206.
Gut No |  | 4/6 & 5/1
Road |  | Internal Road |  | Locality/Village |  | Chindharan
City |  | Taloja |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Konnark Heavens |  | Distance from city centre: |  | 11.5 KM from Taloja Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude : |  | 19.074654,73.159809
Location Link : |  | https://maps.app.goo.gl/5PfDUSLjtaxKouvE7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 11693.672
Permissible FSI |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  | 0.3
Total FSI availaible for the project |  |  |  | 1.2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 14032.406
Total number of Buildings |  |  |  | 14 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | NAINA CIDCO
Layout Approval No. |  | CIDCO/NAINA/Panvel/Chindhran/ BP-00525/CC/2021/0105 |  |  | Dated | 26/08/2021.
Approved Floor plan No. |  | CIDCO/NAINA/Panvel/Chindhran/ BP-00525/CC/2021/0105 |  |  | Dated | 26/08/2021.
Commencement-CC No Valid Up to: |  | CIDCO/NAINA/Panvel/Chindhran/ BP-00525/CC/2021/0105 |  |  | Dated | 26/08/2021.
Building No. 1 to 7 = Gr/st + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 14032.406
Approved No.of units |  |  | Sale Flats - 268, EWS/LIG Flats - 48, Shops - 24
Approved No.of Floors |  |  | Building No.1 = Gr/St + 1st to 4th Floor Building No.2 (Wing A, B, C, D) = Gr/St + 1st to 4th Floor Building No.3 (Wing A, B ) = Gr/St + 1st to 4th Floor Building No.4 (Wing A, B ) = Gr/St + 1st to 4th Floor Building No.5 = Gr/St + 1st to 4th Floor Building No.6 (Wing A & B) = Gr/St + 1st to 4th Floor Building No.7 (Wing A & B) = Gr/St + 1st to 4th Floor
Proposed No.of Floors |  |  | Building No.1 = Gr/St + 1st to 4th Floor
Building No.2 (Wing A, B, C, D) = Gr/St + 1st to 4th Floor
Building No.3 (Wing A, B ) = Gr/St + 1st to 4th Floor
Building No.4 (Wing A, B ) = Gr/St + 1st to 4th Floor
Building No.5 = Gr/St + 1st to 4th Floor
Building No.6 (Wing A & B) = Gr/St + 1st to 4th Floor
Building No.7 (Wing A & B) = Gr/St + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 26/08/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative entrance
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 3 Floor Completed, External Plaster upto 1 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster upto 3 Floor Completed, External Plaster upto 1 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 65.62% |  | 85% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 25% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.2 (Wing A & B) = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 34% |  | 63% |  | Excavation in process | 2 | *
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 3 | 60% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.2 (Wing C & D) = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 34% |  | 63% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 3 | 60% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0 | *+
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.3 (Wing A, B ) = Gr/St + 1st to 4th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.4 (Wing A) = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 3 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 3 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 72.5% |  | 88.75% |  | Excavation in process | 2 | *
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.4 (Wing B) = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 1 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 1 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 67.5% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 25% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.5 = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 2 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed, Brickwork Completed, Internal Plaster Completed, External Plaster upto 2 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 70% |  | 87.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.6 (Wing A & B) = Gr/St + 1st to 4th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No.7 (Wing A & B) = Gr/St + 1st to 4th Floor | [5 empty] | Excavation work in process
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work in process | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 2 | 50% | 0% |  | 10% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4300
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3440
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | Cost Sheet | Sheet | 99 acres | MIS
Building No.3 (Wing B) |  | 10 |  | 755.5682 |  | 1171.1307 |  |  | 5000 | 4155 per Sqft for Flats | 6858.3121 | 4000-6000
Building No.5 |  | 7 |  | 650.9744 |  | 1009.0104 |  |  | 5000 | 7000 for Shop | 7061.6523
Building No.6 (Wing A) |  | 3 |  | 254.8915 |  | 395.0819 |  | On Saleable Area | 5000 |  | 6959.9822
Building No.7 (Wing A) |  | 4 |  | 347.2897 |  | 538.299 |  |  |  |  | 4349.9889
Total |  | 24 |  | 2008.7239 |  | 3113.522
Residential Area Details for Sale Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 20 |  | 10140.6998 |  | 17870
Building No.2 (Wing A, B, C & D) |  | 100 |  | 33684.022 |  | 63180
Building No.3 (Wing A & B) |  | 48 |  | 17399.4032 |  | 32320
Building No.4 (Wing A & B) |  | 60 |  | 19195.0106 |  | 35880
Building No.5 |  | 24 |  | 10310.6634 |  | 18210
Building No.6 (Wing A)(Sale) |  | 20 |  | 7809.3251 |  | 13530
Total |  | 272 |  | 98539.1241 |  | 180990
Residential Area Details for EWS/LIG Flats
Building No.6 (Wing B)(EWS/LIG) |  | 14 |  | 6434.3748 |  | 10620
Building No.7 (Wing A)(EWS/LIG) |  | 16 |  | 7075.2203 |  | 11720
Building No.7 (Wing B)(EWS/LIG) |  | 14 |  | 5645.9118 |  | 9410
Total |  | 44 |  | 19155.5068 |  | 31750
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building No.3
Wing B
Ground Floor for Commercial & Parking
1 |  | Shop | 75.4772 | 0 | 116.9896 | Ground Floor for Commercial & Parking
2 |  | Shop | 74.9174 | 0 | 116.122 | Ground Floor for Commercial & Parking
3 |  | Shop | 64.1534 | 0 | 99.4378 | Ground Floor for Commercial & Parking
4 |  | Shop | 81.3758 | 0 | 126.1326 | Ground Floor for Commercial & Parking
5 |  | Shop | 76.4782 | 0 | 118.5412 | Ground Floor for Commercial & Parking
6 |  | Shop | 76.4782 | 0 | 118.5412 | Ground Floor for Commercial & Parking
7 |  | Shop | 81.3758 | 0 | 126.1326 | Ground Floor for Commercial & Parking
8 |  | Shop | 74.9174 | 0 | 116.122 | Ground Floor for Commercial & Parking
9 |  | Shop | 74.9174 | 0 | 116.122 | Ground Floor for Commercial & Parking
10 |  | Shop | 75.4772 | 0 | 116.9896 | Ground Floor for Commercial & Parking
Building No.5
Ground Floor for Commercial & Parking
1 |  | Shop | 106.5636 | 0 | 165.1736 | Ground Floor for Commercial & Parking
2 |  | Shop | 101.2354 | 0 | 156.9149 | Ground Floor for Commercial & Parking
3 |  | Shop | 101.2354 | 0 | 156.9149 | Ground Floor for Commercial & Parking
4 |  | Shop | 90.4929 | 0 | 140.2641 | Ground Floor for Commercial & Parking
5 |  | Shop | 85.7353 | 0 | 132.8897 | Ground Floor for Commercial & Parking
6 |  | Shop | 91.5478 | 0 | 141.8991 | Ground Floor for Commercial & Parking
7 |  | Shop | 74.164 | 0 | 114.9541 | Ground Floor for Commercial & Parking
Building No.6
Wing A
Ground Floor for Commercial & Parking
1 |  | Shop | 73.841 | 0 | 114.4536 | Ground Floor for Commercial & Parking
2 |  | Shop | 107.2094 | 0 | 166.1746 | Ground Floor for Commercial & Parking
3 |  | Shop | 73.841 | 0 | 114.4536 | Ground Floor for Commercial & Parking
Building No.7
Wing A
Ground Floor for Commercial & Parking
1 |  | Shop | 81.3758 | 0 | 126.1326 | Ground Floor for Commercial & Parking
2 |  | Shop | 92.269 | 0 | 143.017 | Ground Floor for Commercial & Parking
3 |  | Shop | 92.269 | 0 | 143.017 | Ground Floor for Commercial & Parking
4 |  | Shop | 81.3758 | 0 | 126.1326 | Ground Floor for Commercial & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No.1
Ground Floor for Parking
1st & 3rd Floor for Residential
101 & 301 |  | 2BHK | 546.6713 | 70.0413 | 970 | 1st & 3rd Floor for Residential |  |  | 1.6463
102 & 302 |  | 2BHK | 546.6713 | 66.3278 | 970 | 1st & 3rd Floor for Residential |  |  | 1.653
103 & 303 |  | 1BHK | 349.8515 | 40.1712 | 635 | 1st & 3rd Floor for Residential |  |  | 1.7002
104 & 304 |  | 2BHK | 546.6713 | 68.0285 | 970 | 1st & 3rd Floor for Residential |  |  | 1.6499
105 & 305 |  | 2BHK | 546.6713 | 67.6948 | 970 | 1st & 3rd Floor for Residential |  |  | 1.6505
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 2BHK | 546.1115 | 58.9544 | 950 | 2nd & 4th Floor |  |  | 1.6316
202 & 402 |  | 2BHK | 546.1115 | 58.9544 | 950 | 2nd & 4th Floor |  |  | 1.6316
203 & 403 |  | 1BHK | 349.3671 | 31.4524 | 620 | 2nd & 4th Floor |  |  | 1.6846
204 & 404 |  | 2BHK | 546.1115 | 58.9544 | 950 | 2nd & 4th Floor |  |  | 1.6316
205 & 405 |  | 2BHK | 546.1115 | 58.9544 | 950 | 2nd & 4th Floor |  |  | 1.6316
Building No.2 | [8 empty] | #DIV/0!
Ground Floor for Parking | [8 empty] | #DIV/0!
Wing A | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 377.2782 | 61.7315 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6918
102 & 302 |  | 2BHK | 504.1535 | 52.7759 | 870 | 1st & 3rd Floor for Residential |  |  | 1.621
103 & 303 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
104 & 304 |  | 1BHK | 350.6911 | 61.5378 | 670 | 1st & 3rd Floor for Residential |  |  | 1.735
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 376.7938 | 79.2876 | 725 | 2nd & 4th Floor |  |  | 1.7137
202 & 402 |  | 2BHK | 501.0642 | 79.2876 | 905 | 2nd & 4th Floor |  |  | 1.6479
203 & 403 |  | 1BHK | 350.6911 | 62.5496 | 670 | 2nd & 4th Floor |  |  | 1.7322
204 & 404 |  | 1BHK | 350.6911 | 62.5496 | 670 | 2nd & 4th Floor |  |  | 1.7322
Wing B | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
102 & 302 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
103 & 303 |  | 1BHK | 377.2782 | 64.7993 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6836
104 & 304 |  | 1BHK | 377.2782 | 62.5496 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6896
105 & 305 |  | 1BHK | 350.6911 | 62.8725 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7312
106 & 306 |  | 1RK | 245.6883 | 62.8725 | 510 | 1st & 3rd Floor for Residential |  |  | 1.8199
107 & 307 |  | 1RK | 240.7369 | 31.4524 | 455 | 1st & 3rd Floor for Residential |  |  | 1.7594
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 350.6911 | 62.5496 | 670 | 2nd & 4th Floor |  |  | 1.7322
202 & 402 |  | 1BHK | 350.6911 | 62.5496 | 670 | 2nd & 4th Floor |  |  | 1.7322
203 & 403 |  | 1BHK | 369.5281 | 0 | 600 | 2nd & 4th Floor |  |  | 1.6237
204 & 404 |  | 1BHK | 373.4785 | 35.8656 | 655 | 2nd & 4th Floor |  |  | 1.6578
205 & 405 |  | 1BHK | 350.6911 | 64.2826 | 670 | 2nd & 4th Floor |  |  | 1.7272
206 & 406 |  | 1RK | 237.9382 | 0 | 410 | 2nd & 4th Floor |  |  | 1.7231
207 & 407 |  | 1RK | 237.0448 | 80.138 | 520 | 2nd & 4th Floor |  |  | 1.8556
Wing C | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1RK | 240.7369 | 31.4524 | 455 | 1st & 3rd Floor for Residential |  |  | 1.7594
102 & 302 |  | 1RK | 245.6883 | 64.6055 | 510 | 1st & 3rd Floor for Residential |  |  | 1.8128
103 & 303 |  | 1BHK | 350.6911 | 62.8725 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7312
104 & 304 |  | 1BHK | 377.2782 | 62.5496 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6896
105 & 305 |  | 1BHK | 377.2782 | 64.7993 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6836
106 & 306 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
107 & 307 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1RK | 237.0448 | 80.138 | 520 | 2nd & 4th Floor |  |  | 1.8556
202 & 402 |  | 1RK | 237.9382 | 0 | 410 | 2nd & 4th Floor |  |  | 1.7231
203 & 403 |  | 1BHK | 350.6911 | 64.2826 | 670 | 2nd & 4th Floor |  |  | 1.7272
204 & 404 |  | 1BHK | 373.4785 | 35.8656 | 655 | 2nd & 4th Floor |  |  | 1.6578
205 & 405 |  | 1BHK | 369.5281 | 0 | 600 | 2nd & 4th Floor |  |  | 1.6237
206 & 406 |  | 1BHK | 350.6911 | 61.1395 | 670 | 2nd & 4th Floor |  |  | 1.7362
207 & 407 |  | 1BHK | 350.6911 | 61.1395 | 670 | 2nd & 4th Floor |  |  | 1.7362
Wing D | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
102 & 302 |  | 1BHK | 350.6911 | 61.1395 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7362
103 & 303 |  | 1BHK | 377.2782 | 64.7993 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6836
104 & 304 |  | 1BHK | 377.2782 | 62.5496 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6896
105 & 305 |  | 1BHK | 350.6911 | 62.8725 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7312
106 & 306 |  | 1RK | 237.5615 | 64.6055 | 510 | 1st & 3rd Floor for Residential |  |  | 1.8749
107 & 307 |  | 1RK | 237.8521 | 80.138 | 455 | 1st & 3rd Floor for Residential |  |  | 1.576
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 350.6911 | 62.5496 | 670 | 2nd & 4th Floor |  |  | 1.7322
202 & 402 |  | 1BHK | 350.6911 | 62.5496 | 670 | 2nd & 4th Floor |  |  | 1.7322
203 & 403 |  | 1BHK | 369.5281 | 0 | 600 | 2nd & 4th Floor |  |  | 1.6237
204 & 404 |  | 1BHK | 373.4785 | 35.8656 | 655 | 2nd & 4th Floor |  |  | 1.6578
205 & 405 |  | 1BHK | 350.6911 | 64.2826 | 670 | 2nd & 4th Floor |  |  | 1.7272
206 & 406 |  | 1RK | 238.7455 | 0 | 410 | 2nd & 4th Floor |  |  | 1.7173
207 & 407 |  | 1RK | 237.8521 | 80.138 | 520 | 2nd & 4th Floor |  |  | 1.8493
Building No.3 | [8 empty] | #DIV/0!
Wing A | [8 empty] | #DIV/0!
Ground Floor for Parking | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 343.2317 | 47.8783 | 635 | 1st & 3rd Floor for Residential |  |  | 1.7106
102 & 302 |  | 1BHK | 395.1895 | 47.8783 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6501
103 & 303 |  | 1BHK | 350.6911 | 63.0663 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7307
104 & 304 |  | 1BHK | 350.6911 | 63.0663 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7307
105 & 305 |  | 1BHK | 395.1895 | 47.8783 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6501
106 & 306 |  | 1BHK | 343.2317 | 47.8783 | 635 | 1st & 3rd Floor for Residential |  |  | 1.7106
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 340.3254 | 71.6237 | 665 | 2nd & 4th Floor |  |  | 1.7436
202 & 402 |  | 1BHK | 395.3617 | 47.0387 | 700 | 2nd & 4th Floor |  |  | 1.6516
203 & 403 |  | 1BHK | 350.6911 | 60.8166 | 670 | 2nd & 4th Floor |  |  | 1.7371
204 & 404 |  | 1BHK | 350.6911 | 60.8166 | 670 | 2nd & 4th Floor |  |  | 1.7371
205 & 405 |  | 1BHK | 395.3617 | 47.0387 | 700 | 2nd & 4th Floor |  |  | 1.6516
206 & 406 |  | 1BHK | 340.3254 | 59.1267 | 665 | 2nd & 4th Floor |  |  | 1.7803
Wing B | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 343.2317 | 47.8783 | 635 | 1st & 3rd Floor for Residential |  |  | 1.7106
102 & 302 |  | 1BHK | 395.1895 | 47.8783 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6501
103 & 303 |  | 1BHK | 350.6911 | 63.0663 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7307
104 & 304 |  | 1BHK | 350.6911 | 63.0663 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7307
105 & 305 |  | 1BHK | 395.2971 | 47.8783 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6497
106 & 306 |  | 1BHK | 340.3254 | 47.8783 | 635 | 1st & 3rd Floor for Residential |  |  | 1.7252
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 340.3254 | 71.6237 | 665 | 2nd & 4th Floor |  |  | 1.7436
202 & 402 |  | 1BHK | 395.3617 | 47.0387 | 700 | 2nd & 4th Floor |  |  | 1.6516
203 & 403 |  | 1BHK | 350.6911 | 60.8166 | 670 | 2nd & 4th Floor |  |  | 1.7371
204 & 404 |  | 1BHK | 350.6911 | 60.8166 | 670 | 2nd & 4th Floor |  |  | 1.7371
205 & 405 |  | 1BHK | 395.8999 | 47.0387 | 700 | 2nd & 4th Floor |  |  | 1.6493
206 & 406 |  | 1BHK | 340.3254 | 69.8907 | 665 | 2nd & 4th Floor |  |  | 1.7486
Building No.4 | [8 empty] | #DIV/0!
Wing A | [8 empty] | #DIV/0!
Ground Floor for Parking | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1RK | 240.7369 | 31.4524 | 455 | 1st & 3rd Floor for Residential |  |  | 1.7594
102 & 302 |  | 1RK | 245.6775 | 60.6228 | 510 | 1st & 3rd Floor for Residential |  |  | 1.8291
103 & 303 |  | 1RK | 241.3181 | 64.6055 | 500 | 1st & 3rd Floor for Residential |  |  | 1.8042
104 & 304 |  | 1RK | 241.3181 | 62.8725 | 500 | 1st & 3rd Floor for Residential |  |  | 1.8114
105 & 305 |  | 1BHK | 377.3535 | 62.5496 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6893
106 & 306 |  | 1BHK | 377.2782 | 64.6055 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6842
107 & 307 |  | 1BHK | 377.2782 | 61.3333 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6928
108 & 308 |  | 1BHK | 377.2782 | 61.3333 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6928
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1RK | 244.8487 | 79.589 | 520 | 2nd & 4th Floor |  |  | 1.7987
202 & 402 |  | 1RK | 237.9275 | 0 | 410 | 2nd & 4th Floor |  |  | 1.7232
203 & 403 |  | 1RK | 233.568 | 0 | 400 | 2nd & 4th Floor |  |  | 1.7126
204 & 404 |  | 1RK | 233.568 | 0 | 400 | 2nd & 4th Floor |  |  | 1.7126
205 & 405 |  | 1BHK | 373.4785 | 35.6827 | 655 | 2nd & 4th Floor |  |  | 1.6582
206 & 406 |  | 1BHK | 370.0663 | 0 | 600 | 2nd & 4th Floor |  |  | 1.6213
207 & 407 |  | 1BHK | 376.7938 | 79.5783 | 725 | 2nd & 4th Floor |  |  | 1.7129
208 & 408 |  | 1BHK | 376.7938 | 79.5783 | 725 | 2nd & 4th Floor |  |  | 1.7129
Wing B | [8 empty] | #DIV/0!
Ground Floor for Parking | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 377.2782 | 61.3333 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6928
102 & 302 |  | 1BHK | 377.2782 | 61.3333 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6928
103 & 303 |  | 1BHK | 377.2782 | 64.6055 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6842
104 & 304 |  | 1BHK | 377.3535 | 62.5496 | 700 | 1st & 3rd Floor for Residential |  |  | 1.6893
105 & 305 |  | 1BHK | 350.6911 | 62.8725 | 670 | 1st & 3rd Floor for Residential |  |  | 1.7312
106 & 306 |  | 1RK | 245.6775 | 64.5948 | 510 | 1st & 3rd Floor for Residential |  |  | 1.813
107 & 307 |  | 1RK | 240.7369 | 31.4524 | 455 | 1st & 3rd Floor for Residential |  |  | 1.7594
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 376.7938 | 79.5998 | 725 | 2nd & 4th Floor |  |  | 1.7129
202 & 402 |  | 1BHK | 376.7938 | 79.5998 | 725 | 2nd & 4th Floor |  |  | 1.7129
203 & 403 |  | 1BHK | 369.5281 | 0 | 600 | 2nd & 4th Floor |  |  | 1.6237
204 & 404 |  | 1BHK | 373.4785 | 35.6827 | 655 | 2nd & 4th Floor |  |  | 1.6582
205 & 405 |  | 1BHK | 350.6804 | 64.7993 | 670 | 2nd & 4th Floor |  |  | 1.7258
206 & 406 |  | 1RK | 237.9167 | 0 | 410 | 2nd & 4th Floor |  |  | 1.7233
207 & 407 |  | 1RK | 240.7369 | 80.138 | 520 | 2nd & 4th Floor |  |  | 1.8271
Building No.5 | [8 empty] | #DIV/0!
1st & 3rd Floor for Residential | [8 empty] | #DIV/0!
101 & 301 |  | 1BHK | 385.0498 | 68.9327 | 720 | 1st & 3rd Floor for Residential |  |  | 1.6909
102 & 302 |  | 1BHK | 375.1792 | 68.9327 | 710 | 1st & 3rd Floor for Residential |  |  | 1.7087
103 & 303 |  | 2BHK | 534.777 | 74.1101 | 965 | 1st & 3rd Floor for Residential |  |  | 1.6659
104 & 304 |  | 2BHK | 528.3186 | 74.1101 | 965 | 1st & 3rd Floor for Residential |  |  | 1.6863
105 & 305 |  | 1BHK | 381.5838 | 68.9327 | 720 | 1st & 3rd Floor for Residential |  |  | 1.7062
106 & 306 |  | 1BHK | 385.0498 | 68.9327 | 665 | 1st & 3rd Floor for Residential |  |  | 1.548
2nd & 4th Floor for Residential | [8 empty] | #DIV/0!
201 & 401 |  | 1BHK | 383.306 | 35.8226 | 665 | 2nd & 4th Floor for Residential |  |  | 1.6414
202 & 402 |  | 1BHK | 370.5722 | 0 | 605 | 2nd & 4th Floor for Residential |  |  | 1.6326
203 & 403 |  | 2BHK | 532.2798 | 37.7386 | 905 | 2nd & 4th Floor for Residential |  |  | 1.6293
204 & 404 |  | 2BHK | 525.8214 | 37.7386 | 905 | 2nd & 4th Floor for Residential |  |  | 1.6493
205 & 405 |  | 1BHK | 371.5948 | 0 | 615 | 2nd & 4th Floor for Residential |  |  | 1.655
206 & 406 |  | 1BHK | 381.7991 | 35.8226 | 665 | 2nd & 4th Floor for Residential |  |  | 1.6479
Building No.6 | [8 empty] | #DIV/0!
Wing A | [8 empty] | #DIV/0!
1st & 3rd Floor | [8 empty] | #DIV/0!
101 & 301 | Sale | 1BHK | 383.0046 | 40.8494 | 680 | 1st & 3rd Floor |  |  | 1.6688
102 & 302 | Sale | 2BHK | 466.5871 | 32.292 | 795 | 1st & 3rd Floor |  |  | 1.6347
103 & 303 | Sale | 1BHK | 371.7347 | 40.8494 | 670 | 1st & 3rd Floor |  |  | 1.6925
104 & 304 | Sale | 1BHK | 371.7347 | 40.8494 | 670 | 1st & 3rd Floor |  |  | 1.6925
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 | Sale | 1BHK | 381.1532 | 35.4566 | 670 | 2nd & 4th Floor |  |  | 1.6648
202 & 402 | Sale | 2BHK | 463.3579 | 35.4566 | 795 | 2nd & 4th Floor |  |  | 1.6392
203 & 403 | Sale | 1BHK | 365.1149 | 0 | 605 | 2nd & 4th Floor |  |  | 1.657
204 & 404 | Sale | 1BHK | 365.1149 | 0 | 605 | 2nd & 4th Floor |  |  | 1.657
Wing B | [8 empty] | #DIV/0!
Ground Floor for Residential | [8 empty] | #DIV/0!
1 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | Ground Floor for Residential |  |  | 1.6493
2 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | Ground Floor for Residential |  |  | 1.6493
1st & 3rd Floor | [8 empty] | #DIV/0!
101 & 301 | Sale | 1BHK | 371.7455 | 40.8494 | 670 | 1st & 3rd Floor |  |  | 1.6924
102 & 302 | EWS/LIG | 2BHK | 441.4532 | 0 | 730 | 1st & 3rd Floor |  |  | 1.6536
103 & 303 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 1st & 3rd Floor |  |  | 1.6493
104 & 304 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 1st & 3rd Floor |  |  | 1.6493
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 | Sale | 1BHK | 365.1149 | 0 | 605 | 2nd & 4th Floor |  |  | 1.657
202 & 402 | EWS/LIG | 2BHK | 441.4532 | 0 | 730 | 2nd & 4th Floor |  |  | 1.6536
203 & 403 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 2nd & 4th Floor |  |  | 1.6493
204 & 404 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 2nd & 4th Floor |  |  | 1.6493
Building No.7 | [8 empty] | #DIV/0!
Wing A | [8 empty] | #DIV/0!
1st & 3rd Floor | [8 empty] | #DIV/0!
101 & 301 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | 1st & 3rd Floor |  |  | 1.6766
102 & 302 | EWS/LIG | 2BHK | 456.3398 | 0 | 755 | 1st & 3rd Floor |  |  | 1.6545
103 & 303 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 1st & 3rd Floor |  |  | 1.6493
104 & 304 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 1st & 3rd Floor |  |  | 1.6493
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | 2nd & 4th Floor |  |  | 1.6766
202 & 402 | EWS/LIG | 2BHK | 456.3398 | 0 | 755 | 2nd & 4th Floor |  |  | 1.6545
203 & 403 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 2nd & 4th Floor |  |  | 1.6493
204 & 404 | EWS/LIG | 2BHK | 466.8562 | 0 | 770 | 2nd & 4th Floor |  |  | 1.6493
Wing B | [8 empty] | #DIV/0!
Ground Floor for Residential | [8 empty] | #DIV/0!
1 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | Ground Floor for Residential |  |  | 1.6766
2 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | Ground Floor for Residential |  |  | 1.6766
1st & 3rd Floor | [8 empty] | #DIV/0!
101 & 301 | EWS/LIG | 2BHK | 464.5958 | 0 | 765 | 1st & 3rd Floor |  |  | 1.6466
102 & 302 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | 1st & 3rd Floor |  |  | 1.6766
103 & 303 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | 1st & 3rd Floor |  |  | 1.6766
2nd & 4th Floor | [8 empty] | #DIV/0!
201 & 401 | EWS/LIG | 2BHK | 464.5958 | 0 | 765 | 2nd & 4th Floor |  |  | 1.6466
202 & 402 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | 2nd & 4th Floor |  |  | 1.6766
203 & 403 | EWS/LIG | 1BHK | 378.7529 | 0 | 635 | 2nd & 4th Floor |  | 5000 | 1.6766
Remarks:
* | Building No.1, 2 (C & D Wing) & 5 = Construction work is in process at the time of visit (Slow Speed). Building No. 2 (A & B Wing) & 4 = Construction work is the same as last visit (dtd.15/08/2025), but work is in process at the time of the visit. (Slow Speed). Building No. 7 = Construction work is same as last visit dtd. 26/06/2024. Building No. 3 & 6 = work not yet started.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Projected Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Since building no. 3 & 6 have received CC on 26/08/2021, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have No.direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Sunil Peravi |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Konnark Oasis
PHOTOGRAPHS OF PROPERTY : |  |  | Konnark Oasis
Google Map :
Bldg No 2B
Bldg No 2C
Bldg No 2D
Bldg No 3A
Bldg No 3B
Bldg No 4A
Bldg No 4B
Bldg No 5
Bldg No 7 A & B
Bldg No 3A
2D
2B
2C
2A
B1
B1

## Sheet1
Bldg 1 | Flat no 101 & 301 | Bldg 2 (A) | 102 & 103
| 42.465 |  | 33.137
Balcony | 3.325
cantiliver Bal | 2.4
Terrace | 6.473

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted