## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 11/08/2025.
Name of the builder group |  |  |  | M/s.Mahaavir Buildcon LLP
Name of the builder company |  |  |  | M/s.Mahaavir Buildcon LLP
Name of the Project |  |  |  | Mahaavir Pride |  |  |  | Construction % is given extra in previous report
Contact Details ( Name & Contact No.) |  |  |  | 9892509416
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Ashvin 9987299302 / Mr. Janardan 9702670084
Name / No of the Building |  |  |  | A & B Wings
Docouments Provided |  |  |  | Approved Plans & CC.
RERA No. |  |  |  | P51700027307
Project location details |  | Mahaavir Pride, S No.42/2, 237/5 & 256/1/A, near Sarvodaya Anand CHSL, Manpada Road, Bhopar, Dombivali East, Kalyan, Thane.
S No |  | 42/2, 237/5 & 256/1/A
Road |  | Manpada Road |  | Locality/Village |  | Bhopar
City |  | Dombivali East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Nearby Landmark |  | Sarvodaya Anand CHSL |  | Distance from city centre: |  | 3.60KM from Dombivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | 30.00 M. Wide Road |  |  | Manpada Road
West | NA | Other Plot |  |  | FDC Limited
North | NA | 18.00 M. Wide Road |  |  | Bhopar Road
South | NA | Other Plot |  |  | Horizon Banquet
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.192183,73.091722
Location Link |  | https://maps.app.goo.gl/GAwa17PRWM7vBvwK7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7303.95
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 3.7814
Total FSI availaible for the project |  |  |  | 4.8814
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 35653.31
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | KDMCC/RB/2023/APL/00023 |  |  | Dated | 2023-10-27
Approved Floor plan No. |  | KDMCC/RB/2023/APL/00023 |  |  | Dated | 2023-10-27
Commencement Certificate No. |  | KDMCC/RB/2023/APL/00023 |  |  | Dated | 2023-10-27
Valid Up to: |  | Wing A = Lower Ground + Ground + 1st (Commerical + Podium Parking ) + 2nd & 3rd Podium + 4th Podium + 5th Floor + 6th to 30th Floor (6th Floor Part for MHADA) B Wing = Lower Ground + Ground + 1st (Commerical + Podium Parking ) + 2nd & 3rd Podium + 4th Podium + 5th Floor + 6th to 30th Floor (6th & 7th Floor Part for MHADA) | [5 empty] | Wing A 6th Floor For Mhada as per plan
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 35653.31
Approved no of units |  |  | Sale Flats - 375, Mhada Flats - 25, Shops - 42, Offices - 39
Approved no of Floors |  |  | A Wing = Lower Ground + Ground + 1st (Commerical + Podium Parking) + 2nd & 3rd Podium + 4th Podium + 5th Floor + 6th to 30th Floor B Wing = Lower Ground + Ground + 1st (Commerical + Podium Parking) + 2nd & 3rd Podium + 4th Podium + 5th Floor + 6th to 30th Floor
Proposed no of Floors |  |  | A Wing = Lower Ground + Ground + 1st to 4th Podium + 5th Floor + 6th to 30th Floor
Proposed no of Floors |  |  | B Wing = Lower Ground + Ground + 1st to 4th Podium + 5th Floor + 6th to 30th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | A & B Wing = Lower Ground + Ground + 1st Commerical + 2nd to 5th Podium + 6th to 30th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 28 Slab completed, Brickwork upto 26 Floor completed, Internal Plaster upto 24 Floor completed, External Plaster upto 18 Floor completed, Flooring upto 4 Floor completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 30 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 28 Slab completed, Brickwork upto 26 Floor completed, Internal Plaster upto 24 Floor completed, External Plaster upto 18 Floor completed, Flooring upto 4 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 7.5
Excavation |  | 30 | 100% | 65.96% |  | 84.1% |  | Excavation in process |  | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed |  | 30
RCC (Including podiums) |  | 28 | 90.32% |  |  |  |  | Footing in Process |  | 6
Brickwork | Brickwork & Internal Plaster | 26 | 86.67% |  |  |  |  | Footing Completed |  | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 80% |  |  |  |  | Basement 1 |  | 18
Ext. Plaster & Plumbing | External Plaster & Plumbing | 18 | 60% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 13.33% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 24
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 30
Construction details: |  | B Wing = Lower Ground + Ground + 1st to 4th Podium + 5th Floor + 6th to 30th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 24 Slab completed, Brickwork upto 18 Floor completed, Internal Plaster upto 10 Floor completed, External Plaster upto 4 Floor completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 30 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 24 Slab completed, Brickwork upto 18 Floor completed, Internal Plaster upto 10 Floor completed, External Plaster upto 4 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 7.5
Excavation |  | 30 | 100% | 49.3% |  | 73.56% |  | Excavation in process |  | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed |  | 30
RCC (Including podiums) |  | 24 | 77.42% |  |  |  |  | Footing in Process |  | 6
Brickwork | Brickwork & Internal Plaster | 18 | 60% |  |  |  |  | Footing Completed |  | 12
Internal Plaster | Brickwork & Internal Plaster | 10 | 33.33% |  |  |  |  | Basement 1 |  | 18
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 13.33% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 24
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 30
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | Party Hall, Indoor games Area, Meditation & yoga area, Gymnasium, Swimming pool, Jacuzzi & kid’s pool, Landscape garden, Kids play area, Outdoor multipurpose court, etc. | [5 empty] | http://www.mahaavir-pride-dombivli.in/?gad_source=1&gclid=Cj0KCQjwy4KqBhD0ARIsAEbCt6jdhxKM3kmwXY9oNlfBuhIw5Y0tM28ApHE3Rcmx2F4psfr6GV2_AJ0aAvdIEALw_wcB#amenities
Recommended Rates of the Property : | [8 empty] | 7000 to 7300 | 2023-07-20 | smith pal | verbal
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7520 |  |  | 7300 to 7520 by sanket on 17/10/2023 on higher side
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000 |  |  | rate has changes as per disscussed with palas sir on 10/12/2021
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 12000
Society Charges |  |  |  |  | 1,00,000/-
Floor Rise Rate Per Sq.ft |  |  |  |  | 35/- from 6th Floor
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 5,00,000/-
Distressed valuation of the Property |  |  |  |  | 6016
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shops | 22 |  | 11053.0134 |  | 17684.8214
| Offices | 21 |  | 10379.2623 |  | 16606.8198
Wing B | Shops | 20 |  | 12219.2898 |  | 19550.8636
| Offices | 18 |  | 7477.6495 |  | 11964.2391
Total |  | 81 |  | 41129.215 |  | 65806.744
Residential Area Details (Mhada) :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | As per Approved Plans.
Wing A |  | 7 |  | 5397.3925 |  | 8365.9584 |  |  | Tower A | 175
Wing B |  | 18 |  | 9558.432 |  | 14815.5696 |  |  | Tower B | 225
Total |  | 25 |  | 14955.8245 |  | 23181.528 |  |  |  | 400
Residential Area Details (Sale) :
Wing A |  | 168 |  | 129523.9655 |  | 200762.1465
Wing B |  | 207 |  | 109921.968 |  | 170379.0504
Total |  | 375 |  | 239445.9335 |  | 371141.1969
Grand Total |  | 481 |  | 295530.973 |  | 460129.4689
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing B
Lower Ground Floor For Commercial & Parking
1 |  | Shop | 566.4634 | 0 | 906.3414 | Lower Ground Floor For Commercial & Parking
2 |  | Shop | 456.0018 | 0 | 729.6029
3 |  | Shop | 423.5096 | 0 | 677.6153
4 |  | Shop | 440.5328 | 0 | 704.8526
5 |  | Shop | 440.5328 | 0 | 704.8526
6 |  | Shop | 507.3073 | 0 | 811.6917
7 |  | Shop | 429.8065 | 0 | 687.6904 |  |  | 41.1555
8 |  | Shop | 400.2001 | 0 | 640.3202 |  |  | 37.1795
Wing B
Ground Floor for Entrance Lobby, Commercial & Parking
1+2+3+4+5+6+7+8 (Merged ) |  | Shop | 3459.4151 | 0 | 5535.0641 | Ground Floor for Entrance Lobby, Commercial & Parking
9 |  | Shop | 468.234 | 0 | 749.1744 |  |  | 43.37 | 43.5
10 |  | Shop | 429.7958 | 0 | 687.6732 |  |  | 31.8614
11 |  | Shop | 428.0412 | 0 | 684.866 |  |  | 39.2781
12 |  | Shop | 428.0412 | 0 | 684.866
13 |  | Shop | 427.9766 | 0 | 684.7626
14 |  | Shop | 466.4795 | 0 | 746.3671
15 |  | Shop | 602.558 | 0 | 964.0927 |  |  | 55.7039
16 |  | Shop | 491.7856 | 0 | 786.857
16A |  | Shop | 413.0619 | 0 | 660.899
17 |  | Shop | 459.1277 | 0 | 734.6042 |  |  | 45.0902
18 |  | Shop | 480.4188 | 0 | 768.6702 |  |  | 44.2408
1st Floor For Commercial & Parking | [7 empty] | 10.764
1 |  | Office | 379.6881 | 0 | 607.501 | 1st Floor For Commercial & Parking
2 |  | Office | 406.8216 | 0 | 650.9146
3 |  | Office | 364.778 | 0 | 583.6448
4 |  | Office | 348.2805 | 0 | 557.2488
5 |  | Office | 502.4494 | 0 | 803.919
6 |  | Office | 485.6824 | 0 | 777.0919 |  |  | 44.8325
7 |  | Office | 383.1769 | 0 | 613.083
8 |  | Office | 420.1189 | 0 | 672.1903 |  |  | 39.5915
9 |  | Office | 385.7925 | 0 | 617.268 |  |  | 35.3843
10 |  | Office | 384.2317 | 0 | 614.7708
11 |  | Office | 384.2317 | 0 | 614.7708
12 |  | Office | 384.2317 | 0 | 614.7708
13 |  | Office | 418.5581 | 0 | 669.693
14 |  | Office | 544.3678 | 0 | 870.9884 |  |  | 52.5829
15 |  | Office | 441.4962 | 0 | 706.394 |  |  | 43.646
15A |  | Office | 403.2152 | 0 | 645.1443
16 |  | Office | 409.5271 | 0 | 655.2434
17 |  | Office | 431.0013 | 0 | 689.6021 |  |  | 39.5721
Wing A
Lower Ground Floor For Parking
Ground Floor for Drivers Room, Entrance Lobby & Parking
19 |  | Shop | 479.1595 | 0 | 766.6551 | Ground Floor for Drivers Room, Entrance Lobby & Parking |  | 44.2349
20 |  | Shop | 483.8418 | 0 | 774.1469 |  |  | 44.6699
21 |  | Shop | 444.8223 | 0 | 711.7157 |  |  | 28.1447
22 |  | Shop | 446.0817 | 0 | 713.7307 |  |  | 41.1481
23 |  | Shop | 444.0903 | 0 | 710.5446
24 |  | Shop | 445.4574 | 0 | 712.7318
25 |  | Shop | 429.2145 | 0 | 686.7432
26 |  | Shop | 468.234 | 0 | 749.1744
27 |  | Shop | 428.0412 | 0 | 684.866
28 |  | Shop | 428.0412 | 0 | 684.866
29 |  | Shop | 466.9746 | 0 | 747.1594 |  |  | 43.1039
30 |  | Shop | 531.0527 | 0 | 849.6843 |  |  | 49.0489
31 |  | Shop | 399.2691 | 0 | 638.8305 |  |  | 36.8866
32 |  | Shop | 1164.9985 | 0 | 1863.9976 |  |  | 110.0087
33 |  | Shop | 418.655 | 0 | 669.848
34 |  | Shop | 471.3663 | 0 | 754.1861 |  |  | 43.5109
35 |  | Shop | 452.7123 | 0 | 724.3397 |  |  | 41.887
36 |  | Shop | 452.7123 | 0 | 724.3397
37 |  | Shop | 544.8306 | 0 | 871.729
38 |  | Shop | 563.6246 | 0 | 901.7993
39 |  | Shop | 544.9167 | 0 | 871.8668 |  |  | 50.446
40 |  | Shop | 544.9167 | 0 | 871.8668 |  |  | 50.446
1st Floor For Commercial & Parking
18 |  | Office | 429.8819 | 0 | 687.811 | 1st Floor For Commercial & Parking |  | 39.4765
19 |  | Office | 434.0583 | 0 | 694.4933 |  |  | 39.865
20 |  | Office | 398.9892 | 0 | 638.3827 |  |  | 36.6275
21 |  | Office | 400.3347 | 0 | 640.5355
22 |  | Office | 398.6555 | 0 | 637.8488
23 |  | Office | 399.775 | 0 | 639.6399
24 |  | Office | 385.2759 | 0 | 616.4414
25 |  | Office | 420.1189 | 0 | 672.1903 |  |  | 38.57
26 |  | Office | 384.2317 | 0 | 614.7708 |  |  | 35.2418
27 |  | Office | 384.2317 | 0 | 614.7708 |  |  | 35.2289
28 |  | Office | 418.9995 | 0 | 670.3991
29 |  | Office | 476.2209 | 0 | 761.9534 |  |  | 43.7775
30 |  | Office | 1468.2742 | 0 | 2349.2387 |  |  | 138.0005
31 |  | Office | 449.171 | 0 | 718.6735 |  |  | 55.6872
32 |  | Office | 445.0806 | 0 | 712.129 |  |  | 52.9512
33 |  | Office | 449.806 | 0 | 719.6897
34 |  | Office | 449.806 | 0 | 719.6897
35 |  | Office | 541.9243 | 0 | 867.079
36 |  | Office | 560.5568 | 0 | 896.8909 |  |  | 51.6167
37 |  | Office | 541.9459 | 0 | 867.1134
38 |  | Office | 541.9243 | 0 | 867.079 |  |  | 536.9729
Flat No. (Approved Plan) | Sale / Mhada | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
A Wing
2nd to 4th Floor for Podium Parking
5th Floor for Recreation Space | [7 empty] | 10.764
6th Floor For Residential
1 | Mhada | 2BHK | 725.8165 | 0 | 1125.0156 | 6th Floor For Residential |  | 56.5285 | 2.82 | 6288.8017 |  |  | 601,..,601 | 601 | 601
2 | Mhada | 2BHK | 725.8165 | 0 | 1125.0156 | [7 empty] | 602,..,602 | 602 | 602
3 | Mhada | 2BHK | 728.7766 | 0 | 1129.6038 |  |  | 58.141 | 3.456 | 6312.8331 |  |  | 603,..,603 | 603 | 603
4 | Mhada | 2BHK | 728.7766 | 0 | 1129.6038 | [7 empty] | 604,..,604 | 604 | 604
5 | Mhada | 3BHK | 881.9214 | 0 | 1366.9782 |  |  | 70.167 | 8.76 | 7171.292 |  |  | 605,..,605 | 605 | 605
6 | Mhada | 3BHK | 881.9214 | 0 | 1366.9782 |  |  |  |  | 7315.4055 |  |  | 606,..,606 | 606 | 606
7 | Mhada | 2BHK | 724.3634 | 0 | 1122.7632 |  |  |  |  | 6351.2945 |  |  | 607,..,607 | 607 | 607
8th, 10th, 12th, 14th, 16th, 18th & 20thFloor
1 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | 8th, 10th, 12th, 14th, 16th, 18th & 20thFloor |  |  |  | 6288.8017 |  |  | 601,..,2001 | 601 | 2001
2 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | [7 empty] | 602,..,2002 | 602 | 2002
3 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 |  |  |  |  | 6312.8331 |  |  | 603,..,2003 | 603 | 2003
4 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 | [7 empty] | 604,..,2004 | 604 | 2004
5 | Sale | 3BHK | 881.9214 | 0 | 1366.9782 |  |  |  |  | 7171.292 |  |  | 605,..,2005 | 605 | 2005
6 | Sale | 3BHK | 881.9214 | 0 | 1366.9782 |  |  |  |  | 7315.4055 |  |  | 606,..,2006 | 606 | 2006
7 | Sale | 2BHK | 724.3634 | 0 | 1122.7632 |  |  |  |  | 6351.2945 |  |  | 607,..,2007 | 607 | 2007
7th, 9th, 11th, 13th, 15th, 17th & 19th Floor (Refuge area at Staircase Mid landing)
1 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | 7th, 9th, 11th, 13th, 15th, 17th & 19th Floor (Refuge area at Staircase Mid landing) |  |  |  | 6288.8017 |  |  | 601,..,1901 | 601 | 1901
2 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | [7 empty] | 602,..,1902 | 602 | 1902
3 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 |  |  |  |  | 6312.8331 |  |  | 603,..,1903 | 603 | 1903
4 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 | [7 empty] | 604,..,1904 | 604 | 1904
5 | Sale | 3BHK | 881.9214 | 0 | 1366.9782 |  |  |  |  | 7171.292 |  |  | 605,..,1905 | 605 | 1905
6 | Sale | 3BHK | 881.9214 | 0 | 1366.9782 |  |  |  |  | 7315.4055 |  |  | 606,..,1906 | 606 | 1906
7 | Sale | 2BHK | 724.3634 | 0 | 1122.7632 |  |  |  |  | 6351.2945 |  |  | 607,..,1907 | 607 | 1907
22nd, 24th, 26th, 28th & 30th Floor
1 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | 22nd, 24th, 26th, 28th & 30th Floor | [6 empty] | 701,..,3001 | 701 | 3001
2 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | [7 empty] | 702,..,3002 | 702 | 3002
3 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 | [7 empty] | 703,..,3003 | 703 | 3003
4 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 |  |  |  |  | 5090.2805 |  |  | 704,..,3004 | 704 | 3004
5 | Sale | 3BHK | 881.2487 | 0 | 1365.9355 | [7 empty] | 705,..,3005 | 705 | 3005
6 | Sale | 3BHK | 881.2487 | 0 | 1365.9355 |  |  |  |  | 6625.4961 | 200000 |  | 706,..,3006 | 706 | 3006
7 | Sale | 2BHK | 724.3634 | 0 | 1122.7632 | [7 empty] | 707,..,3007 | 707 | 3007
21st, 23rd, 25th, 27th & 29th Floor (Refuge area at Staircase Mid landing)
1 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | 21st, 23rd, 25th, 27th & 29th Floor (Refuge area at Staircase Mid landing) |  |  |  | 10.764 |  |  | 701,..,2901 | 701 | 2901
2 | Sale | 2BHK | 725.8165 | 0 | 1125.0156 | [7 empty] | 702,..,2902 | 702 | 2902
3 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 | [7 empty] | 703,..,2903 | 703 | 2903
4 | Sale | 2BHK | 728.7766 | 0 | 1129.6038 |  |  |  |  | 5090.2805 |  |  | 704,..,2904 | 704 | 2904
5 | Sale | 3BHK | 881.2487 | 0 | 1365.9355 | [7 empty] | 705,..,2905 | 705 | 2905
6 | Sale | 3BHK | 881.2487 | 0 | 1365.9355 |  |  |  |  | 6625.4961 | 200000 |  | 706,..,2906 | 706 | 2906
7 | Sale | 2BHK | 724.3634 | 0 | 1122.7632 | [7 empty] | 707,..,2907 | 707 | 2907
B Wing
2nd, 3rd, 4th Floor for Podium Parking
5th Floor for Recreation Space | [7 empty] | 10.764
6th & 7th Floor For Residential
1 | Mhada | 2BHK | 622.9665 | 0 | 965.5981 | 6th & 7th Floor For Residential |  | 59.3485 |  | 7327.0651 |  |  | 601,..,701 | 601 | 701
2 | Mhada | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 602,..,702 | 602 | 702
3 | Mhada | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 603,..,703 | 603 | 703
4 | Mhada | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 604,..,704 | 604 | 704
5 | Mhada | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 13824.9855 |  |  | 605,..,705 | 605 | 705
6 | Mhada | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 10356.2758 |  |  | 606,..,706 | 606 | 706
7 | Mhada | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 7385.0603 |  |  | 607,..,707 | 607 | 707
8 | Mhada | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 608,..,708 | 608 | 708
9 | Mhada | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 609,..,709 | 609 | 709
8th, 10th, 12th, 14th, 16th, 18th & 20thFloor
1 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | 8th, 10th, 12th, 14th, 16th, 18th & 20thFloor |  |  |  | 7327.0651 |  |  | 601,..,2001 | 601 | 2001
2 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 602,..,2002 | 602 | 2002
3 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 603,..,2003 | 603 | 2003
4 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 604,..,2004 | 604 | 2004
5 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 13824.9855 |  |  | 605,..,2005 | 605 | 2005
6 | Sale | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 10356.2758 |  |  | 606,..,2006 | 606 | 2006
7 | Sale | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 7385.0603 |  |  | 607,..,2007 | 607 | 2007
8 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 608,..,2008 | 608 | 2008
9 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 609,..,2009 | 609 | 2009
9th, 11th, 13th, 15th, 17th & 19th Floor (Refuge area at Staircase Mid landing)
1 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | 9th, 11th, 13th, 15th, 17th & 19th Floor (Refuge area at Staircase Mid landing) |  |  |  | 7327.0651 |  |  | 601,..,1901 | 601 | 1901
2 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 602,..,1902 | 602 | 1902
3 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 603,..,1903 | 603 | 1903
4 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 604,..,1904 | 604 | 1904
5 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 13824.9855 |  |  | 605,..,1905 | 605 | 1905
6 | Sale | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 10356.2758 |  |  | 606,..,1906 | 606 | 1906
7 | Sale | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 7385.0603 |  |  | 607,..,1907 | 607 | 1907
8 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 608,..,1908 | 608 | 1908
9 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 10056.7145 |  |  | 609,..,1909 | 609 | 1909
22nd, 24th, 26th, 28th & 30th Floor
1 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | 22nd, 24th, 26th, 28th & 30th Floor | [6 empty] | 701,..,3001 | 701 | 3001
2 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 702,..,3002 | 702 | 3002
3 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 703,..,3003 | 703 | 3003
4 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 8109.1163 |  |  | 704,..,3004 | 704 | 3004
5 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 705,..,3005 | 705 | 3005
6 | Sale | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 9372.4296 | 200000 |  | 706,..,3006 | 706 | 3006
7 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 707,..,3007 | 707 | 3007
8 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 708,..,3008 | 708 | 3008
9 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 709,..,3009 | 709 | 3009
21st, 23rd, 25th, 27th & 29th Floor (Refuge area at Staircase Mid landing)
1 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | 21st, 23rd, 25th, 27th & 29th Floor (Refuge area at Staircase Mid landing) |  |  |  | 10.764 |  |  | 701,..,2901 | 701 | 2901
2 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 702,..,2902 | 702 | 2902
3 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 703,..,2903 | 703 | 2903
4 | Sale | 1BHK | 457.47 | 0 | 709.0785 |  |  |  |  | 8109.1163 |  |  | 704,..,2904 | 704 | 2904
5 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 705,..,2905 | 705 | 2905
6 | Sale | 2BHK | 622.9665 | 0 | 965.5981 |  |  |  |  | 9372.4296 | 200000 |  | 706,..,2906 | 706 | 2906
7 | Sale | 2BHK | 622.9665 | 0 | 965.5981 | [7 empty] | 707,..,2907 | 707 | 2907
8 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 708,..,2908 | 708 | 2908
9 | Sale | 1BHK | 457.47 | 0 | 709.0785 | [7 empty] | 709,..,2909 | 709 | 2909
Remarks:
1 | Construction work is in process at the time of Visit. Internal Visit was not allowed (Slow Speed).
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Balcony + E.P. Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | On Site, we meet Mr. Ashwin : 9987299302.
7 | On the ground floor, shops (1+2+3+4+5+6+7+8+9) are merged into a single shop.
8 | We have updated revised C.C & Approved Plan (on 01/11/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Krishna Kambali |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mahaavir Pride
Layout :
Google Map :
Formulas:
Bhopar = [Bhopar, row above]
Wing B
Wing A

## Old Plan Report
1302-ELLORA FIESTA, PLOT NO. 8, SECTOR 11, OPP. JUINAGAR RAILWAY STATION, SANPADA, NAVI MUMBAI 400 706. TEL: 022-27758396/95. FAX :022-27758394. E mail : axisbank@vsjadon.com. vsjcvaluer@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2021-07-14
Name of the builder group |  |  |  | M/s.Mahaavir Buildcon LLP
Name of the builder company |  |  |  | M/s.Mahaavir Buildcon LLP
Name of the Project |  |  |  | Mahaavir Pride
Contact Details ( Name & Contact No.) |  |  |  | 9892509416
Name / No of the Building |  |  |  | A & B Wings
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51700027307
Project location details |  | Mahaavir Pride, S No.42/2, 237/5, 259/4, near Sarvodaya Anand CHSL, Manpada Road, Bhopar, Kalyan, Kalyan, Thane.
S No |  | 42/2, 237/5, 259/4
Road |  | Manpada Road |  | Locality/Village |  | Bhopar
City |  | Kalyan |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Nearby Landmark |  | Sarvodaya Anand CHSL |  | Distance from city centre: |  | 4.7KM from Datiwali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Manpada Road
West | NA | NA |  |  | FDC Limited
North | NA | NA |  |  | Bhopar Road
South | NA | NA |  |  | Horizon Banquet
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1925 |  | Longitude |  | 73.0914
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6131.25
Permissible FSI |  |  |  | 0.95
Permissible TDR/Paid FSI |  |  |  | 0.34488
Total FSI availaible for the project |  |  |  | 1.2949
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7939.25
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | KDMP/NRV/BP/27village/2020-21/05 |  |  | Dated | 2020-11-09
Approved Floor plan No. |  | KDMP/NRV/BP/27village/2020-21/05 |  |  | Dated | 2020-11-09
Commencement Certificate No. |  | KDMP/NRV/BP/27village/2020-21/05 |  |  | Dated | 2020-11-09
Valid Up to: A Wing = LG + G + 1st Podium + 2nd to 11th Floor B Wing = LG + G + 1st Podium + 2nd to 5th Floor (2nd to 4th for MHADA)
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7939.25
Approved no of units |  |  | Sale Flats - 79, Mhada Flats - 27, Shops - 35, Offices - 33
Approved no of Floors |  |  | A Wing = G + 1st Commerical + 2nd to 11th Floor B Wing = G + 1st Commerical + 2nd to 5th Floor (2nd to 4th for MHADA)
Proposed no of Floors |  |  | A Wing = G + 1st Commerical + 2nd to 28th Floor
B Wing = G + 1st Commerical + 2nd to 28th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | A Wing = G + 1st Commerical + 2nd to 28th Floor | [5 empty] | Excavation work completed, Plinth work completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 28 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 10% |  | 45% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 16.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.4
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Construction details: |  | B Wing = G + 1st Commerical + 2nd to 28th Floor | [5 empty] | Excavation work completed, Plinth work completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 28 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 10% |  | 45% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 5.6
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 11.2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 16.8
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.4
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7500
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 14000
Society Charges |  |  |  |  | 1BHK - 60,000/- & 2BHK - 70,000/- 3BHK - 80,000/-
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 5,00,000/-
Distressed valuation of the Property |  |  |  |  | 6000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 35 |  | 16195.6253 |  | 25913.0004
Offices |  | 33 |  | 16546.3724 |  | 26474.1958
Total |  | 68 |  | 32741.9976 |  | 52387.1962
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing - Sale |  | 70 |  | 44262.4291 |  | 68740.4935
B Wing - Sale |  | 9 |  | 3778.164 |  | 6001.4682
B Wing - Mhada |  | 27 |  | 11334.492 |  | 18429.6723
Total |  | 106 |  | 59375.0851 |  | 93171.634
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
A & B Wing
Ground Floor for Commercial & Parking
1 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
2 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
3 |  | Shop | 461.668 | 0 | 738.6687 | Ground Floor
4 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
5 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
6 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
7 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
8 |  | Shop | 461.668 | 0 | 738.6687 | Ground Floor
9 |  | Shop | 584.0815 | 0 | 934.5305 | Ground Floor
10 |  | Shop | 492.5337 | 0 | 788.054 | Ground Floor
11 |  | Shop | 477.1143 | 0 | 763.3829 | Ground Floor
12 |  | Shop | 477.1143 | 0 | 763.3829 | Ground Floor
13 |  | Shop | 477.1143 | 0 | 763.3829 | Ground Floor
14 |  | Shop | 477.1143 | 0 | 763.3829 | Ground Floor
15 |  | Shop | 445.3874 | 0 | 712.6199 | Ground Floor
16 |  | Shop | 445.3874 | 0 | 712.6199 | Ground Floor
17 |  | Shop | 445.3874 | 0 | 712.6199 | Ground Floor
18 |  | Shop | 445.3874 | 0 | 712.6199 | Ground Floor
19 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
20 |  | Shop | 461.668 | 0 | 738.6687 | Ground Floor
21 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
22 |  | Shop | 423.0521 | 0 | 676.8834 | Ground Floor
23 |  | Shop | 461.668 | 0 | 738.6687 | Ground Floor
24 |  | Shop | 509.8907 | 0 | 815.8251 | Ground Floor
25 |  | Shop | 332.0263 | 0 | 531.2422 | Ground Floor
26 |  | Shop | 706.1916 | 0 | 1129.9066 | Ground Floor
27 |  | Shop | 328.4096 | 0 | 525.4554 | Ground Floor
28 |  | Shop | 411.4539 | 0 | 658.3262 | Ground Floor
29 |  | Shop | 425.6086 | 0 | 680.9737 | Ground Floor
30 |  | Shop | 425.6086 | 0 | 680.9737 | Ground Floor
31 |  | Shop | 425.6086 | 0 | 680.9737 | Ground Floor
32 |  | Shop | 552.5161 | 0 | 884.0258 | Ground Floor
33 |  | Shop | 552.5161 | 0 | 884.0258 | Ground Floor
34 |  | Shop | 552.5161 | 0 | 884.0258 | Ground Floor
35 |  | Shop | 552.5161 | 0 | 884.0258 | Ground Floor
1st Floor
101 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
102 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
103 |  | Office | 461.668 | 0 | 738.6687 | 1st Floor
104 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
105 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
106 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
107 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
108 |  | Office | 461.668 | 0 | 738.6687 | 1st Floor
109 |  | Office | 584.0815 | 0 | 934.5305 | 1st Floor
110 |  | Office | 492.5337 | 0 | 788.054 | 1st Floor
111 |  | Office | 477.1143 | 0 | 763.3829 | 1st Floor
112 |  | Office | 477.1143 | 0 | 763.3829 | 1st Floor
113 |  | Office | 477.1143 | 0 | 763.3829 | 1st Floor
114 |  | Office | 477.1143 | 0 | 763.3829 | 1st Floor
115 |  | Office | 445.3874 | 0 | 712.6199 | 1st Floor
116 |  | Office | 445.3874 | 0 | 712.6199 | 1st Floor
117 |  | Office | 445.3874 | 0 | 712.6199 | 1st Floor
118 |  | Office | 445.3874 | 0 | 712.6199 | 1st Floor
119 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
120 |  | Office | 461.668 | 0 | 738.6687 | 1st Floor
121 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
122 |  | Office | 423.0521 | 0 | 676.8834 | 1st Floor
123 |  | Office | 461.668 | 0 | 738.6687 | 1st Floor
124 |  | Office | 509.8907 | 0 | 815.8251 | 1st Floor
125 |  | Office | 1691.864 | 0 | 2706.9824 | 1st Floor
126 |  | Office | 414.0373 | 0 | 662.4596 | 1st Floor
127 |  | Office | 466.6194 | 0 | 746.591 | 1st Floor
128 |  | Office | 445.6296 | 0 | 713.0074 | 1st Floor
129 |  | Office | 445.6296 | 0 | 713.0074 | 1st Floor
130 |  | Office | 537.9847 | 0 | 860.7756 | 1st Floor
131 |  | Office | 537.9847 | 0 | 860.7756 | 1st Floor
132 |  | Office | 537.9847 | 0 | 860.7756 | 1st Floor
133 |  | Office | 537.9847 | 0 | 860.7756 | 1st Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
A Wing
2nd Floor
201 |  | 2BHK | 575.5511 | 0 | 834.5491 | 2nd Floor
202 |  | 2BHK | 575.5511 | 991.9026 | 999.8662 | 2nd Floor
203 |  | 2BHK | 554.1307 | 1047.3372 | 978.0457 | 2nd Floor
204 |  | 2BHK | 554.1307 | 1047.3372 | 978.0457 | 2nd Floor
205 |  | 3BHK | 719.8963 | 2055.3858 | 1386.414 | 2nd Floor
206 |  | 3BHK | 752.7265 | 1664.6526 | 1368.8956 | 2nd Floor
207 |  | 2BHK | 570.5996 | 0 | 827.3695 | 2nd Floor
3rd Floor
301 |  | 2BHK | 575.5511 | 58.1256 | 892.6747 | 3rd Floor
302 |  | 2BHK | 575.5511 | 0 | 834.5491 | 3rd Floor
303 |  | 2BHK | 554.1307 | 0 | 803.4895 | 3rd Floor
304 |  | 2BHK | 554.1307 | 0 | 803.4895 | 3rd Floor
305 |  | 3BHK | 719.8963 | 0 | 1043.8497 | 3rd Floor
306 |  | 3BHK | 752.7265 | 0 | 1091.4535 | 3rd Floor
307 |  | 2BHK | 570.5996 | 58.1256 | 885.4951 | 3rd Floor
4th, 6th, 8th, 10th Floor
401,..,1001 |  | 2BHK | 575.5511 | 60.0631 | 894.6122 | 4th, 6th, 8th, 10th Floor |  | 7908.4548 |  | 401,..,1001 | 401 | 1001
402,..,1002 |  | 2BHK | 575.5511 | 60.0631 | 894.6122 | 4th, 6th, 8th, 10th Floor |  |  |  | 402,..,1002 | 402 | 1002
403,..,1003 |  | 2BHK | 592.02 | 60.0631 | 918.4921 | 4th, 6th, 8th, 10th Floor |  | 7763.8118 |  | 403,..,1003 | 403 | 1003
404,..,1004 |  | 2BHK | 592.02 | 60.0631 | 918.4921 | 4th, 6th, 8th, 10th Floor |  |  |  | 404,..,1004 | 404 | 1004
405,..,1005 |  | 3BHK | 759.2926 | 60.0631 | 1161.0373 | 4th, 6th, 8th, 10th Floor |  | 8443.3116 |  | 405,..,1005 | 405 | 1005
406,..,1006 |  | 3BHK | 792.1228 | 60.0631 | 1208.6411 | 4th, 6th, 8th, 10th Floor |  | 8273.7546 |  | 406,..,1006 | 406 | 1006
407,..,1007 |  | 2BHK | 570.5996 | 60.0631 | 887.4326 | 4th, 6th, 8th, 10th Floor |  | 7713.2618 |  | 407,..,1007 | 407 | 1007
5th, 7th, 9th, 11th Floor
501,..,1101 |  | 2BHK | 575.5511 | 58.1256 | 892.6747 | 5th, 7th, 9th, 11th Floor |  |  |  | 501,..,1101 | 501 | 1101
502,..,1102 |  | 2BHK | 575.5511 | 58.1256 | 892.6747 | 5th, 7th, 9th, 11th Floor |  |  |  | 502,..,1102 | 502 | 1102
503,..,1103 |  | 2BHK | 592.02 | 58.1256 | 916.5546 | 5th, 7th, 9th, 11th Floor |  |  |  | 503,..,1103 | 503 | 1103
504,..,1104 |  | 2BHK | 592.02 | 58.1256 | 916.5546 | 5th, 7th, 9th, 11th Floor |  |  |  | 504,..,1104 | 504 | 1104
505,..,1105 |  | 3BHK | 759.2926 | 58.1256 | 1159.0998 | 5th, 7th, 9th, 11th Floor |  |  |  | 505,..,1105 | 505 | 1105
506,..,1106 |  | 3BHK | 792.1228 | 58.1256 | 1206.7036 | 5th, 7th, 9th, 11th Floor |  |  |  | 506,..,1106 | 506 | 1106
507,..,1107 |  | 2BHK | 570.5996 | 58.1256 | 885.4951 | 5th, 7th, 9th, 11th Floor |  |  |  | 507,..,1107 | 507 | 1107
B Wing
2nd Floor (For Mhada)
201 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 2nd Floor (For Mhada)
202 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 2nd Floor (For Mhada)
203 |  | 1BHK | 429.6989 | 991.9026 | 788.3805 | 2nd Floor (For Mhada)
204 |  | 1BHK | 429.6989 | 991.9026 | 788.3805 | 2nd Floor (For Mhada)
205 |  | 1BHK | 429.6989 | 991.9026 | 788.3805 | 2nd Floor (For Mhada)
206 |  | 1BHK | 414.8446 | 1377.792 | 831.1566 | 2nd Floor (For Mhada)
207 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 2nd Floor (For Mhada)
208 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 2nd Floor (For Mhada)
209 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 2nd Floor (For Mhada)
3rd Floor (For Mhada)
301 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 3rd Floor (For Mhada)
302 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 3rd Floor (For Mhada)
303 |  | 1BHK | 429.6989 | 58.1256 | 681.189 | 3rd Floor (For Mhada)
304 |  | 1BHK | 429.6989 | 58.1256 | 681.189 | 3rd Floor (For Mhada)
305 |  | 1BHK | 429.6989 | 58.1256 | 681.189 | 3rd Floor (For Mhada)
306 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 3rd Floor (For Mhada)
307 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 3rd Floor (For Mhada)
308 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 3rd Floor (For Mhada)
309 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 3rd Floor (For Mhada)
4th Floor (For Mhada)
401 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 4th Floor (For Mhada)
402 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 4th Floor (For Mhada)
403 |  | 1BHK | 429.6989 | 53.2818 | 676.3452 | 4th Floor (For Mhada)
404 |  | 1BHK | 429.6989 | 53.2818 | 676.3452 | 4th Floor (For Mhada)
405 |  | 1BHK | 429.6989 | 53.2818 | 676.3452 | 4th Floor (For Mhada)
406 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 4th Floor (For Mhada)
407 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 4th Floor (For Mhada)
408 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 4th Floor (For Mhada)
409 |  | 1BHK | 414.8446 | 53.2818 | 654.8064 | 4th Floor (For Mhada)
5th Floor
501 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 5th Floor
502 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 5th Floor
503 |  | 1BHK | 429.6989 | 58.1256 | 681.189 | 5th Floor
504 |  | 1BHK | 429.6989 | 58.1256 | 681.189 | 5th Floor
505 |  | 1BHK | 429.6989 | 58.1256 | 681.189 | 5th Floor
506 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 5th Floor
507 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 5th Floor
508 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 5th Floor
509 |  | 1BHK | 414.8446 | 58.1256 | 659.6502 | 5th Floor
Remarks:
1 | Construction work is in process at the time of Visit (labour found).
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | On Site, we meet Mr.Roy(9867311348).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Harshada..
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mahaavir Pride
Google Map :
Formulas:
Bhopar = [Bhopar, row above]
A Wing
A Wing
B Wing
B Wing

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted