## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | M/s.Vishnu Developers
Name of the builder company |  |  |  | M/s.Vishnu Developers
Name of the Project |  |  |  | Pardeshi Paradise
Contact Details ( Name & Contact No.) |  |  |  | Adil 9022922555 / 9594067777
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51700029987
Project location details |  | Pardeshi Paradise, Survey No.111, Hiss No.2/1/3/4/1., near Marathe building, Titwala-Ambivli Road, Manda, Titwala (East), Kalyan, Thane.
Survey No |  | 111, Hiss No.2/1/3/4/1.
Road |  | Titwala-Ambivli Road |  | Locality/Village |  | Manda
City |  | Titwala (East) |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421605
Nearby Landmark |  | Marathe building |  | Distance from city centre: |  | 1.9 Km from Titwala Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Titwala-Ambivli Road
West | NA | NA |  |  | Open plot
North | NA | NA |  |  | Open plot
South | NA | NA |  |  | Marathe building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2916 |  | Longitude |  | 73.2118
Location Link |  | https://goo.gl/maps/ACuwBNwKTZF6RWdB6?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 645.5
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1.1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 710.05
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval | [7 empty] | 0
Layout Approval No |  | KDMC/TPD/BP/KD/2021-22/15 |  |  | Dated | 2021-06-08
Approved Floor plan No. |  | KDMC/TPD/BP/KD/2021-22/15 |  |  | Dated | 2021-06-08 |  |  | 1.2
Commencement Certificate No. |  | KDMC/TPD/BP/KD/2021-22/15 |  |  | Dated | 2021-06-08
|  | Valid Up to: G/St + 1st to 6th Floor + 7th Floor (Pt). | [6 empty] | -2.61
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA |  |  | 9.4 | 8.2 | 5.1 |  |  |  | 2.49
Building wise Construction details | [8 empty] | 1.5 | 0.3 | 4.2 |  |  |  | 1.59
Approved area of building (Sq.Mt) |  |  | 710.05 | [5 empty] | 1 | -0.2 | 5 |  |  |  | 2.39
Approved no of units |  |  | Flats - 38 | [5 empty] | 5.8 | 4.6 | 4.8 |  |  |  | 2.19
Approved no of Floors |  |  | G/St + 1st to 6th Floor + 7th Floor (Pt). | [5 empty] | 3.5 | 2.3
Proposed no of Floors |  |  | G/St + 1st to 6th Floor + 7th Floor (Pt).
Expected Completion |  |  | As per RERA - 07/07/2023
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | G/St + 1st to 6th Floor + 7th Floor (Pt). | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 6.5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting upto 6.5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 89.64% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6.5 | 92.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3750
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 150000/-
Other Charges |  |  |  |  | 175000
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | 200000/-
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1,00,000/-
Distressed valuation of the Property |  |  |  |  | 3000
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 38 |  | 15173.408 |  | 22001.4416
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Ground Floor for Parking
1st to 6th Floor for Residential
1 |  | 1BHK | 445.974 | 0 | 646.6624 | 1st to 6th Floor for Residential | [5 empty] | 101 to 601 | 101 | 601
2 |  | 1RK | 298.1736 | 0 | 432.3517 | [6 empty] | 102 to 602 | 102 | 602
3 |  | 1BHK | 445.974 | 0 | 646.6624 | [6 empty] | 103 to 603 | 103 | 603
4 |  | 1BHK | 445.974 | 0 | 646.6624 | [6 empty] | 104 to 604 | 104 | 604
5 |  | 1RK | 298.1736 | 0 | 432.3517 | [6 empty] | 105 to 605 | 105 | 605
6 |  | 1BHK | 445.974 | 0 | 646.6624 |  |  | 3469.398 |  |  |  | 106 to 606 | 106 | 606
7th Floor
1 |  | 1BHK | 445.974 | 0 | 646.6624 | 7th Floor
6 |  | 1BHK | 445.974 | 0 | 646.6624 |  |  | 3556.7247
Remarks:
1 | Construction work is same as last visit (06/05/2024). The gate was locked.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Balcony + C.B Area.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
6 | As per RERA, the completion period of project Pardeshi Paradise has expired on 07/07/2023 but the project is still under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Krishna Kambali |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pardeshi Paradise
Google Map :
Formulas:
Manda = [Manda, row above]

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.27 | 2.74 | 11.6998 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.13 | 2.13 | 4.5369 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.28 | 2.74 | 8.9872 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.82 | 1.21 | 2.2022 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.05 | 1.3 | 1.365 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 2.13 | 2.13 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 332.8347 | 30.9211 |  |  | 0 | 0 |  | 0 | 0
|  |  | 332.8347 | 30.9211

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted