## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 13/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 11/08/2025.
Name of the builder group |  |  |  |  | M/s. Mirador Dewellers Pvt. Ltd. M/s. Aakar Corporation Pvt. Ltd.
Name of the builder company |  |  |  |  | M/s. Mirador Dewellers Pvt. Ltd. M/s. Aakar Corporation Pvt. Ltd.
Name of the Project |  |  |  |  | Mirador Utsav (F, G, H, I & J Wing)
Name & No. of the Building |  |  |  |  | F, G, H, I & J Wing
Contect Details ( Name & Contect No.) |  |  |  |  | Mr. Vaibhav Ahire 9987293567 Mrs. Chetna Panchal 83699 99601
RERA No. |  |  |  |  | P51700012454
Docouments Provided |  |  |  |  | Refer Data
Project location details |  | Mirador Utsav, Proposed Residential Building on Survey No.128/1, 182/2 & 128/3 of Village Vehloli, Taluka Shahapur, District Thane - 421 601
CTS No | 128/1, 182/2 & 128/3 |  |  | Plot No. | NA | Locality | Vehloli
Road | Mumbai - Agra National Hwy |  |  |  | District | Thane
City | Vasind |  |  |  | Pin Code | 421 601
Near by Landmark |  | MuktaJeevan Ashram |  |  | Distance from city centre: |  | About 5Km Distance From Vasind Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 19.4194 |  | Longitude |  | 73.2893
Location Link |  | https://goo.gl/maps/equV34nCDX8YZoQf6?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 13200
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0.87
Total FSI availaible for the project |  |  |  |  | 1.1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 13401.038
Total number of Buildings |  |  |  |  | 05 Building
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  |  | Dated | NA
Building plan approval No |  | N.A./Plotting/BP/VillageMehloli/Tal. Shahapur/S.S.Thane/1193 |  |  |  | Dated | 22/06/2017.
C.certificate No |  | NA Valid Up to: |  |  |  | Dated | NA | Expiry date: One year from date of issue
O. Certificate No.: |  | J.K.2017/18 Wing E, F, G & H = Gr/Stilt + 1st to 4th Floor (Total No. of Flats = 87 Nos.) |  |  |  | Dated | 22/01/2018.
Commencement date of construction |  |  | NA |  | Expected Completion |  | 31/12/2025.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 13401.038 |  | Approved no of units residential |  |  | NA
Approved no of Floors |  | Gr. (Pt) + 1st to 4th Floor |  |  | No of floors at site : See Construction details
Quality of construction: NA |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Nothing
Construction details: |  | Wing F, G & H = Gr. (Pt) + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Progress % |  | 100% |  |  | Disbursement % |  | 100% |  | Plinth completed | 4
Construction details: |  | Wing I = Gr. (Pt) + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 18% |  | 51% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 1 | 20% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Wing J = Gr. (Pt) + 1st to 4th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : NA
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 3200
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Club Hous Charges | [5 empty] | 40,000/-
Development Charges | [5 empty] | 2,00,000/-
Any Other Amenities | [5 empty] | 7,000/-
Mahanagar Gas connection Charges | [5 empty] | NA
Society Formation Charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 100000/-
Distress valuation of the property Per Sq. Ft. | [5 empty] | 2560
Remarks: 1. F, G, H Wing = All work completed. OC Received. I Wing = Construction work was stopped. Work is same as visit (31/03/2021). J Wing = Work not yet started. 2. We considered given rate verify by market inquire. 3. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 4. Car parking is subjected to authentic documentation. 5. We have updated OC from Rera for Wing F, G & H (On 13/02/2024). 6. As building have received CC on 22/06/2017, still project work is pending. 5. As per RERA, completion period of project Mirador Utsav is expired on 30/12/2022 but still project is under construction. 5.On Site We Meet With Mr. Sanket 9168602584. 5. As per RERA, completion period of Mirador Utsav is expired on 30/12/2021 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mirador Utsav (F, G, H, I & J Wing)
Google Map :
F & G

## I
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 1 | 20% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 8 | 0 | 0 | 0 | 0 | 0
RCC | 8 | 6 |  | Recommended |  | 30 | 6 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 18% | 36% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B.
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C, D
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 75% | 85% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## E
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 4 | 100% |  | Panvel |  | 300000/-
Wood & painting | 4 | 4 | 100% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 4 | 100% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 5 | 5
Finishing | 5 | 5
total | 95% | 100% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Valuation
2020-10-17 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing | Mirador Utsav | 1BHK | 310 | 449.5 | 4004.4494 | 1800000
| Housing | Mirador Utsav | 2BHK | 637 | 923.65 | 3681.048 | 3400000
| Commonfloor | Mirador Utsav | 1RK | 261 | 378.45 | 4489.3645 | 1699000
| Commonfloor | Mirador Utsav | 1BHK | 381 | 552.45 | 4161.4626 | 2299000
| Commonfloor | Mirador Utsav | 2BHK | 510 | 739.5 | 3968.8979 | 2935000
| Average |  |  |  |  | 4061.0445
| Valuation Adopted |  |  |  |  | 4100

## Note
22/01/2021 | Pratiksha
31/03/2021 | Pratiksha

## B
Basement | Podium | Ground | Upper Floor
2 | 6 | 1 | 34
Particulars | total floor | 34
plinth | 10 | 10 | 100%
slab | 43 | 39 | 90.7% |  | Parking |  | Rate
Bricks | 34 | 27 | 79.41% |  | Palghar |  | 100000/-
plaster | 34 | 13.5 | 39.71% |  | Ulwe, karanjade |  | 200000/-
Flooring | 34 | 16 | 47.06% |  | Panvel |  | 300000/-
Wood & painting | 34 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 34 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 36.2791 | 11.9118 | 3.9706 | 4.7059 | 0 | 0
RCC | 36.2791 | 27.2093 |  | Recommended |  | 30 | 27.2093 | 11.9118 | 3.9706 | 2.3529 | 0 | 0
Bricks | 11.9118 | 11.9118
Plaster | 3.9706 | 3.9706
Flooring | 4.7059 | 2.3529
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 66.87% | 75.44% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0