## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder group |  |  |  |  | M/s.Laabh Buildcon
Name of the builder company |  |  |  |  | M/s.Laabh Buildcon
Name of the Project |  |  |  |  | Pehla Ghar- Divekar Complex
Contact Details ( Name & contact No.) |  |  |  |  | 2267937466
Site Meet Person ( Name & contact No.) |  |  |  |  | Mr. Monish Singh 8850281014
Name / No of the Building |  |  |  |  | Building A Building B Building C
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P51700004024
Project location details |  | Pehla Ghar- Divekar Complex, Survey No.69, H No.1 (PT), Sonale Bapgaon Road, Bhadwad, Bhiwandi, Bhiwandi, Thane.
Survey No |  | 69 |  |  | H No |  | 1 (PT)
Road |  | Sonale Bapgaon Road |  |  | Village |  | Bhadwad
City |  | Bhiwandi |  |  | District |  | Thane
Taluka |  | Bhiwandi |  |  | Pin Code |  | 421302
Near by Landmark |  | Royal Flora Shri Aadinath Realty |  |  | Distance from city centre: |  | About 5.3 Km from Bhivandi Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Open Space |  | Road |  | Open Space
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.2882 |  | Longitude |  | 73.0855
Location Link |  | https://goo.gl/maps/9kpCJnatfrk4sLL48
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 2998.78
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.72852
Total FSI availaible for the project |  |  |  |  | 1.7285
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5183.46
Total number of Buildings |  |  |  |  | 03 Buildings
Approval Detail : Plan approval
Layout Approval No |  | J.K.N.R.V.1526 |  |  |  | Dated | 22/09/2015.
Approved Floor plan No. |  | J.K.N.R.V.1526 |  |  |  | Dated | 22/09/2015.
Commencement Certificate No. |  | BPK/23/BHADWAD/2015-2016/JKNRV/PP/1526 Valid Up to: Building A, B, C = G + 1st to 7th Floor |  |  |  | Dated | 22/09/2015. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 22/09/2015. |  | Expected Completion |  | 2024-12-29
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5183.46 |  | Approved no of units |  | Flats = 186 & shop = 06
Approved no of Floors |  | Building A, B, C = G + 7th Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Building A = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 7 Floor completed, Painting upto 5 Floor completed, Finishing upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 7 Floor completed, Painting upto 5 Floor completed, Finishing upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 90% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75 | a wing rcc breck work complete b rcc breck work plaster in out complete windows and doors fram complete 1side panting complete
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 28.57% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building B = G + 1st to 7th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 6 Floor completed, Painting upto 6 Floor completed, Finishing upto 3 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 8 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 6 Floor completed, Painting upto 6 Floor completed, Finishing upto 3 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 90% |  | 94.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 85.71% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 42.86% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building C = G + 1st to 7th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 7 | All work Completed. Provide OC.
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities: |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4000
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6500
Development charges | [5 empty] | 200000/-
Society formation charges | [5 empty] | 125000/-
Recommended rate of Parking | [5 empty] | 150000/-
Advance Maintenance Charges (For 12 Months) | [5 empty] | 35000/-
Distressed valuation of the Property | [5 empty] | 3200
Commercial Area Details :
Building & Wing |  | No. of Shops | Total Carpet Area |  |  | Total Saleable Area
C Building |  | 6 | 1913.6831 |  |  | 2870.5247
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
A Building |  | 65 | 23965.9491 |  |  | 32435
B Building |  | 65 | 23710.0673 |  |  | 32435
C Building |  | 56 | 15478.5889 |  |  | 22443.954
Total |  | 186 | 63154.6054 |  |  | 87313.954
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
A Building
Ground Floor is for Parking & Residential
1 |  | 1 RK | 343.4792 |  | 0 | 600 | N | Ground Floor
2 |  | Multipurpose Room | 230.4572 |  | 0 | 405 | N
1st Floor
1 |  | 1 RK | 453.8102 |  | 0 | 600 | N | 1st Floor
2 |  | Multipurpose Room | 296.8711 |  | 0 | 405 | N
3 |  | 1 BHK | 439.0636 |  | 0 | 565 | N
4 |  | 1 RK | 287.3988 |  | 0 | 400 | N | 1st Floor
5 |  | 1 RK | 317.5541 |  | 0 | 420 | N
6 |  | 1 BHK | 475.9141 |  | 0 | 610 | N
7 |  | Multipurpose Room | 262.2972 |  | 0 | 355 | N
8 |  | 1 BHK | 398.5909 |  | 0 | 560 | N
9 |  | 1 BHK | 410.216 |  | 0 | 575 | N
2nd to 7th Floor
1 |  | 1 RK | 453.8102 |  | 0 | 600 | N | 2nd to 7th Floor
2 |  | Multipurpose Room | 296.8711 |  | 0 | 405 | N
3 |  | 1 BHK | 439.0636 |  | 0 | 565 | N
4 |  | 1 RK | 287.3988 |  | 0 | 400 | N
5 |  | 1 RK | 317.5541 |  | 0 | 420 | N
6 |  | 1 BHK | 475.9141 |  | 0 | 610 | N
7 |  | Multipurpose Room | 262.2972 |  | 0 | 355 | N
8 |  | 1 BHK | 398.5909 |  | 0 | 560 | N
9 |  | 1 BHK | 410.216 |  | 0 | 575 | N
B Building
Ground Floor is for Parking & Reaidential
1 |  | 1 BHK | 373.1879 |  | 0 | 600 | N | Ground Floor
2 |  | Multipurpose Room | 294.9336 |  | 0 | 405 | N
1st Floor
1 |  | 1 RK | 399.0215 |  | 0 | 600 | N | 1st Floor
2 |  | Multipurpose Room | 295.5794 |  | 0 | 405 | N
3 |  | 1 BHK | 439.0636 |  | 0 | 565 | N
4 |  | Multipurpose Room | 286.1071 |  | 0 | 400 | N
5 |  | 1 RK | 316.2625 |  | 0 | 420 | N
6 |  | 1 BHK | 484.5684 |  | 0 | 610 | N
7 |  | Multipurpose Room | 262.2972 |  | 0 | 355 | N
8 |  | 1 BHK | 398.5909 |  | 0 | 560 | N
9 |  | 1 BHK | 410.216 |  | 0 | 575 | N
2nd to 7th Floor
1 |  | 1 RK | 399.0215 |  | 0 | 600 | N | 2nd to 7th Floor
2 |  | Multipurpose Room | 295.5794 |  | 0 | 405 | N
3 |  | 1 BHK | 439.0636 |  | 0 | 565 | N
4 |  | Multipurpose Room | 286.1071 |  | 0 | 400 | N
5 |  | 1 RK | 316.2625 |  | 0 | 420 | N | 2nd to 7th Floor
6 |  | 1 BHK | 484.5684 |  | 0 | 610 | N
7 |  | Multipurpose Room | 262.2972 |  | 0 | 355 | N
8 |  | 1 BHK | 398.5909 |  | 0 | 560 | N
9 |  | 1 BHK | 410.216 |  | 0 | 575 | N
C Building
Ground Floor is for Parking & Commercial
1 |  | Shop | 349.0227 |  | 0 | 523.5341 | N | Ground Floor
2 |  | Shop | 91.5478 |  | 0 | 137.3217 | N
3 |  | Shop | 488.4434 |  | 0 | 732.6651 | N
4 |  | Shop | 489.3099 |  | 0 | 733.9649 | N
5 |  | Shop | 108.5011 |  | 0 | 162.7517 | N
6 |  | Shop | 386.8582 |  | 0 | 580.2872 | N
1st to 5th Floor
1 |  | Multipurpose Room | 250.0477 |  | 0 | 362.5692 | N | 1st to 5th Floor
2 |  | 1 RK | 347.3758 |  | 0 | 503.6949 | N
3 |  | Multipurpose Room | 265.1173 |  | 0 | 384.4201 | N
4 |  | Multipurpose Room | 265.1173 |  | 0 | 384.4201 | N
5 |  | 1 RK | 347.3758 |  | 0 | 503.6949 | N
6 |  | Multipurpose Room | 250.6936 |  | 0 | 363.5057 | N
7 |  | Multipurpose Room | 252.5665 |  | 0 | 366.2214 | N
8 |  | Multipurpose Room | 252.5665 |  | 0 | 366.2214 | N
6th & 7th Floor
1 |  | Multipurpose Room | 209.6827 |  | 0 | 304.0399 | N | 6th & 7th Floor
2 |  | 1 RK | 319.4755 |  | 0 | 463.2395 | N
3 |  | Multipurpose Room | 299.3468 |  | 0 | 434.0529 | N
4 |  | Multipurpose Room | 299.3468 |  | 0 | 434.0529 | N
5 |  | 1 RK | 319.4755 |  | 0 | 463.2395 | N
6 |  | Multipurpose Room | 209.6827 |  | 0 | 304.0399 | N
7 |  | Multipurpose Room | 252.5665 |  | 0 | 366.2214 | N
8 |  | Multipurpose Room | 252.5665 |  | 0 | 366.2214 | N
Remarks:
1. Wing A |  |  | Work is same as last visit (10/07/2024). Some Tenants have occupied flats in building.
2. Wing B |  |  | Finishing work is pending (Slow Speed).
3. Wing C |  |  | Work not started yet.
3. We considered Building A & B Saleable area as per Builder area Sheet & Building C as per our calculation. 4. We considered Carpet area as per Approved Plan. 5. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area. 6. We considered rate as per Market Inquire. 7. Car parking is subjected to authentic documentation. 8. Since Wing C have received CC on 22/09/2015, but as of construction work is not started. 9. As per RERA, completion period of project Pehla Ghar- Divekar Complex is expired on 29/12/2024 but still project is under construction. 10.As checked on RERA portal on date 14/08/2025, we have observed that above project "Pehla Ghar- Divekar Complex " is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Mangesh Bapardekar |  | Report Prepared By : |  |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Pehla Ghar- Divekar Complex
vg
Google Map :
Wing A
Wing A
Wing B
Wing C

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 1 | 14.29% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 7 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 1.4286 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 1.4286 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 1.4286 | 1.4286
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 66.43% | 76.43% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 7
Particulars | total floor | 7
plinth | 10 | 10 | 100%
slab | 8 | 8 | 100% |  | Parking |  | Rate
Bricks | 7 | 7 | 100% |  | Palghar |  | 100000/-
plaster | 7 | 7 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 7 | 1 | 14.29% |  | Panvel |  | 300000/-
Wood & painting | 7 | 3 | 42.86% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 7 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 1.4286 | 2.1429 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 0.71429 | 2.1429 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 1.4286 | 0.71429
Wood & painting | 2.1429 | 2.1429
Finishing | 0 | 0
total | 78.57% | 87.86% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-10-19 | Pratiksha
2021-02-12 | Pratiksha | direct visit external visit complete side off closed side var koni available nahi hot wing identify hot nahi rate 4000per sq (box price 1bhk 30 laks )

## Valuation
2020-10-17 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| 99 Acres | Pehla Ghar- Divekar Complex | 1BHK | 310 | 449.5 | 6229.1435 | 2800000
| Average |  |  |  |  | 6229.1435
| Valuation Adopted |  |  |  |  | 6300

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.55 | 2.9 | 10.295 | CB | 0 | 0 | 0 |  |  | 0
|  | 2.35 | 1.22 | 2.867 | FB |  |  | 0 |  |  | 0
|  | 2.25 | 2.16 | 4.86 |  |  |  | 0 |  |  | 0
| kitch | 2.2 | 1.43 | 3.146 | CB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 | FB |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 0 | 0 | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 227.8524 | 21.168 |  |  | 0 | 0 |  | 0 | 0
|  |  | 227.8524 | 21.168
0