## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-14
Name of the builder |  |  |  |  | M/s.Puranik Builders Limited
Name of the builder company |  |  |  |  | M/s.Puranik Builders Limited
Name of the Project |  |  |  |  | Puranik City - Sector 1
Contect Details ( Name & Contact No.) |  |  |  |  | 2225988888
Site meet Person Details ( Name & Contact No.) |  |  |  |  | Mr. Sameer 9284439176
Docouments Provided |  |  |  |  | Approved Layout, Approved Plan, NA order cum CC.
RERA No. |  |  |  |  | P52000017996
Project location details |  | Puranik City,S.No. 58, 60/78, 64/7, 134/1,2,3,4,5, Neral-Gdhawan Road, Village - Pimploli, Neral, Post- Sugawe, Taluka- Karjat, Raigad.
Plot No | 2 | S No /G. No | S.No. 58, 60/78, 64/7, 134/1,2,3,4,5 |  |  |  | Locality | Pimploli
Road | Neral-Gdhawan Road |  |  |  | District | Karjat
City | Neral |  |  |  | Pin Code | 410201
RERA Number : |  | SubPlot no. 02 - Sector 1 : P52000017996
No of the Buildings |  | Sub Plot no.2 (04 Buildings) = |  |  | Building Type HB (G + 7 Floors) Building Type JBC (G + 7 Floors) Building Type MB1 (G + 7 Floors) Building Type LBS (G + 7 Floors)
Near by Landmark |  | Puranik Future City |  |  | Distance from city centre: |  | 4.8 KM from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 5 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot |  | Road |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.0291713, 73.3490677
Location link |  | https://goo.gl/maps/kCpqkjQEDQAbLdhc7
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 33953.56
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.2
Total FSI availaible for the project |  |  |  |  | 1.3
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 428667.86
Total number of Buildings |  |  |  |  | 04 Buildings
Approval Detail : Plan approval
Layout Approval No |  | SSNR.R.A/BISHEP/BP/PIMPOLI/KARJAT/1626. |  |  |  | Dated | 2017-08-14
Building plan approval No |  | SSNR.R.A/BISHEP/BP/PIMPOLI/KARJAT/1626. |  |  |  | Dated | 2017-08-14 | Expiry date:NA
NA Order Cum Commencement Certificate |  | MSHA/L.N.A.1(B)/P.NO.95/2016. Valid Upto : All buildings =G +1st to 7th Floor |  |  |  | Dated | 2018-02-12 | Expiry date: One year from date of issue
O. Certificate No.: |  | NA |  |  |  | Dated | NA
Commencement date of construction |  |  | 2018-02-12 |  | Expected Completion |  | 2028-01-01
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 428667.86 |  | Approved no of units |  | Shops = 12 Flats = 211
Approved no of Floors |  | JBC, HB, LBS, MB1 = G +1st to 7th Floor
Proposed no of Floors |  | JBC, HB, LBS, MB1 = G +1st to 7th Floor
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: : Brick, sand, cement etc
Construction details: |  | Building Type HB = G +1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor, Flooring upto 2 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor, Flooring upto 2 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 76.79% |  | 90% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 28.57% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 28.57% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type JBC = G +1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 4 Floor, Painting upto 5 Floor, Finishing upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 4 Floor, Painting upto 5 Floor, Finishing upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 85% |  | 92.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 57.14% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 1 | 14.29% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type MB1 = G +1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 5 Floor, Painting upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 85.71% |  | 93.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 71.43% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type LBS = G +1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor, Painting upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor, Painting upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 74.64% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 71.43% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4300
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000
General charges | [5 empty] | 40,000/-
Maintenence charges | [5 empty] | 18,000/-
Society formation charges | [5 empty] | NA
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3440
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Sub Plot no. 02 - Sector 1
Building Type HB (G + 7 Floors)
Ground Floor for Residential
1 |  | 2 BHK | 491.54 |  | 0 | 712.733 | N | Ground
2 |  | 2 BHK | 491.17 |  | 0 | 712.1965 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 2 BHK | 436.99 |  | 0 | 633.6355 | N | Ground
5 |  | 2 BHK | 437.35 |  | 0 | 634.1575 | N | Ground
6 |  | 2 BHK | 491.17 |  | 0 | 712.1965 | N | Ground
1st to 7th Floors
1 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
2 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
3 |  | 2 BHK | 514.8 |  | 0 | 746.46 | N | 1st to 7th
4 |  | 2 BHK | 464.2 |  | 0 | 673.09 | N | 1st to 7th
5 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
6 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
Building Type JBC (G + 7 Floors)
Ground Floor
1 |  | Shop | 90.2777 |  | 0 | 135.4165 | N | Ground
2 |  | Shop | 187.9825 |  | 0 | 281.9737 | N | Ground
3 |  | Shop | 176.099 |  | 0 | 264.1486 | N | Ground
4 |  | Shop | 185.7328 |  | 0 | 278.5992 | N | Ground
5 |  | Shop | 128.3069 |  | 0 | 192.4603 | N | Ground
6 |  | Shop | 109.2546 |  | 0 | 163.8819 | N | Ground
7 |  | Shop | 109.2546 |  | 0 | 163.8819 | N | Ground
8 |  | Shop | 128.3069 |  | 0 | 192.4603 | N | Ground
9 |  | Shop | 185.7328 |  | 0 | 278.5992 | N | Ground
10 |  | Shop | 176.099 |  | 0 | 264.1486 | N | Ground
11 |  | Shop | 187.9825 |  | 0 | 281.9737 | N | Ground
12 |  | Shop | 90.2777 |  | 0 | 135.4165 | N | Ground
1 |  | 2 BHK | 368.43 |  | 0 | 534.2235 | N | Ground
2 |  | 2 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
7 |  | 2 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
2 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
3 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
4 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
5 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
6 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
7 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
8 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
Building Type MB1 (G + 7 Floors)
Ground Floor
1 |  | Entrance Lobby & Society Office | [5 empty] | Ground
2 |  | 1 RK | 214.2 |  | 0 | 310.59 | N | Ground
3 |  | 1 RK | 214.2 |  | 0 | 310.59 | N | Ground
4 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | Ground
5 |  | 1 BHK | 323.87 |  | 0 | 469.6115 | N | Ground
6 |  | 1 BHK | 323.63 |  | 0 | 469.2635 | N | Ground
1st to 7th Floors
1 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
2 |  | 1 RK | 214.2 |  | 0 | 310.59 | N | 1st to 7th
3 |  | 1 RK | 214.2 |  | 0 | 310.59 | N | 1st to 7th
4 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | 1st to 7th
5 |  | 1 BHK | 323.87 |  | 0 | 469.6115 | N | 1st to 7th
6 |  | 1 BHK | 323.63 |  | 0 | 469.2635 | N | 1st to 7th
Building Type LBS (G + 7 Floors)
Ground Floor
1 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
2 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | Ground
5 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
6 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | Ground
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 352.16 |  | 0 | 510.632 | N | 1st to 7th
2 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
3 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | 1st to 7th
5 |  | 1 BHK | 352.05 |  | 0 | 510.4725 | N | 1st to 7th
6 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th |  |  | 2022-09-21
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | 1st to 7th
Remarks: 1. Building Type HB - Construction work is same since visit (14/08/2024) But work is in process at the time of visit.(Slow Speed) Building Type JBC & LBS - Construction work is in process at the time of visit.(Slow Speed) Building Type MB1 - Construction work is same as last visit (21/09/2022). (Internal Visit Not Allowed). 2. Saleable Area is as per our calculation. 3. We considered carpet area as per approved plan. 4. Shop rate is given as per our valuation. 5. We considered Flat rate as per Market inquiry. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. General Chargers as in cost sheet are not same for all flats so it is not mentioned in report. 8. We are not considering ground floor of HB because Entance Lobby in Approved plan is placed on place of Flat no.3 & in sale Plan it is placed on place of Flat no.6. 9. In Sector 1, MB2 is proposed & Sale Plan of it is not provided to us so area details are not mentioned in report. 10. We have considered construction percent as per proposed no of floor 11. The project has received Complete CC on 12/02/2018, But Construction work is still incomplete. 13. On site, we meet Mr. Pankaj Chavan - 8976378372. | [8 empty] | Building Type JBC - Construction work is same as last visit (12/04/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The Saleable Area is as per our calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  |  | Puranik City - Sector 1
Google Map :
Formulas:
Locality = [Locality, row above]
HB
LBS
JBC
MB1
HB
MB1
LBS
JBC

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
magicbricks | Puranik City | 1BHK | 0 | 322 | 5776.3975 | 1860000
magicbricks | Puranik City | 2BHK | 0 | 427 | 5620.6089 | 2400000
magicbricks | Puranik City | 1BHK | 0 | 378 | 6058.2011 | 2290000
magicbricks | Puranik City | 2BHK | 0 | 750 | 4666.6667 | 3500000
housing | Puranik City | 1BHK | 367 | 532.15 | 4697.9235 | 2500000
housing | Puranik City | 1BHK | 368 | 533.6 | 4696.4018 | 2506000
housing | Puranik City | 5BHK | 427 | 619.15 | 4603.0849 | 2850000
housing | Puranik City | 5BHK | 437 | 633.65 | 4603.4877 | 2917000
Average |  |  | 0 | 0 | 5090.3465
Valuation Adopted |  |  |  |  | 5000

## Note
03/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.

## Construction % (2) (hidden)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress | 10 | 40 | 15 | 10 | 1.4286 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 30 | 15 | 10 | 0.71429 | 0 | 0
| 7 | 7 | 100
plaster | Total Floor | completed Floor
| 7 | 7 | 100
Flooring | Total Floor | completed Floor
| 7 | 1 | 14.2857 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 7 | 0 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  |  | Bricks | 15 | 15
| 7 | 0 | 0 |  | Plaster | 10 | 10
[5 empty] | Flooring | 1.4286 | 0.71429
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 76.4286 | 85.7143

## Construction % (3) (hidden)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 0 | 20
| 4 | 0 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 0 | 20