## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-14
Name of the builder |  |  |  |  | M/s.Puranik Builders Limited
Name of the builder company |  |  |  |  | M/s.Puranik Builders Limited
Name of the Project |  |  |  |  | Puranik City - Sector 2
Contect Details ( Name & Contect No.) |  |  |  |  | 2225988888
Site Met Person Details ( Name & Contect No.) |  |  |  |  | Mr.Sameer Jamghere - 9284439176
No of the Buildings |  | Sub Plot no.3 - sector 2 (08 Buildings) = |  |  | Building Type HBC1 (G + 7 Floors) Building Type HBC2 (G + 7 Floors) Building Type JB1 (G + 7 Floors) Building Type JB2 (G + 7 Floors) Building Type KB (G + 7 Floors) Building Type LB1 (G + 7 Floors) Building Type PB1 (G + 7 Floors) Building Type PB2 (G + 7 Floors)
Docouments Provided |  |  |  |  | Approved Layout, Approved Plan, NA order cum CC.
RERA No. |  |  |  |  | SubPlot no. 03 - Sector 2 : P52000017954
Project location details |  | Puranik City, SubPlot no. 03 - Sector 2, S.No. 58, 60/78, 64/7, 134/1,2,3,4,5, Neral-Gdhawan Road, Village - Pimploli, Neral, Post- Sugawe, Taluka- Karjat, Raigad.
Plot No |  | 3, S.No. 58, 60/78, 64/7, 134/1, 2, 3, 4, 5 |  |  | Locality |  | Pimploli
Road |  | Neral-Gdhawan Road |  |  | District |  | Karjat
City |  | Neral |  |  | Pin Code |  | 410201
Near by Landmark |  | Puranik Future City |  |  | Distance from city centre: |  | About 4.8 KM from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 5 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot |  | Road |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.029459,73.349686
Location Link |  | https://goo.gl/maps/351hZrBRdkxxXrBi9
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 33953.56
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.2
Total FSI availaible for the project |  |  |  |  | 1.3
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 428667.86
Total number of Buildings |  |  |  |  | 08 Buildings
Approval Detail : Plan approval
Layout Approval No |  | MSHA/L.N.A.1(B)/P.NO.95/2016. |  |  |  | Dated | 2018-02-12
Building plan approval No |  | MSHA/L.N.A.1(B)/P.NO.95/2016. |  |  |  | Dated | 2018-02-12
NA Order Cum Commencement Certificate |  | MSHA/L.N.A.1(B)/P.NO.95/2016. Valid Upto : All Bldgs = G + 1st to 7th Floor |  |  |  | Dated | 2018-02-12
O. Certificate No.: |  | NA |  |  |  | Dated | NA
Commencement date of construction |  |  | 2018-02-12 |  | Expected Completion |  | 2027-07-01
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 428667.86 |  | Approved no of units |  | Shops = 15 Flats = 443
Approved no of Floors |  | All buildings = G + 1st to 7th Floor |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: : Brick, sand, cement etc
Construction details: |  | Building Type HBC1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 72.5% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type HBC2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 57.5% |  | 80% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7 | *
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type JB1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 5 Floor, External Plaster upto 6 Floor, Painting upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 5 Floor, External Plaster upto 6 Floor, Painting upto 4 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75 |  | Painiting done
Excavation |  | 7 | 100% |  | 74.29% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 71.43% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 57.14% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type JB2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 56.43% |  | 79.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 6 | 85.71% | [5 empty] | Footing Completed | 3.5 | *
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type KB = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 6 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 75% |  | 89.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 28.57% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type LB1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 55.36% |  | 78.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7 | Brickwork done
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 5 | 71.43% | [5 empty] | Footing Completed | 3.5 | *
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type PB1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 5 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 35% |  | 63.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 5 | 62.5% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type PB2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 66.07% |  | 84.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 7 | 100% | [5 empty] | Footing Completed | 3.5 | Plaster done
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4300
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Maintenence charges | [5 empty] | 18,000/-
Society formation charges | [5 empty] | NA
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3440
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
HBC1 |  | 8 | 1772.9384 |  |  | 2659.4077
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
HBC1 |  | 44 | 21867.26 |  |  | 31707.527
HBC2 |  | 42 | 20939.1 |  |  | 30361.695
JB1 |  | 56 | 23886.24 |  |  | 34635.048
JB2 |  | 63 | 26696.93 |  |  | 38710.5485
KB |  | 47 | 17908.67 |  |  | 25967.5715
LB1 |  | 63 | 17779.12 |  |  | 25779.724
PB1 |  | 63 | 23636.79 |  |  | 34273.3455
PB2 |  | 63 | 23636.79 |  |  | 34273.3455
Total |  | 441 | 176350.9 |  |  | 255708.805
Grand Total |  | 449 | 178123.8384 |  |  | 258368.2127
Building details Floor Wise
Details of Flats in Building
Flat No. As per Sale Plan | Flat No. As per Approved Plan | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Sub Plot no. 03 - Sector 2
Buildings of Type HBC1 (G + 7 Floors)
Ground Floor for Commercial & Residential
1 |  | Shop | 127.8763 |  | 0 | 191.8145 | N | Ground
2 |  | Shop | 223.353 |  | 0 | 335.0295 | N | Ground
3 |  | Shop | 217.5404 |  | 0 | 326.3107 | N | Ground
4 |  | Shop | 319.2602 |  | 0 | 478.8904 | N | Ground
5 |  | Shop | 319.2602 |  | 0 | 478.8904 | N | Ground
6 | 6 | Shop | 217.5404 |  | 0 | 326.3107 | N | Ground
| 7 | Shop | 177.9289 |  | 0 | 266.8934 | N | Ground
7
| 8 | Shop | 170.1788 |  | 0 | 255.2683 | N | Ground
2 |  | 2 BHK | 491.17 |  | 0 | 712.1965 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 2 BHK | 436.99 |  | 0 | 633.6355 | N | Ground
1st to 7th Floors
1 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
2 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
3 |  | 2 BHK | 514.8 |  | 0 | 746.46 | N | 1st to 7th
4 |  | 2 BHK | 464.2 |  | 0 | 673.09 | N | 1st to 7th
5 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
6 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
Buildings of Type HBC2 (G + 7 Floors)
Ground Floor for Commercial & Residential
1 |  | Shop | 127.8763 |  | 0 | 191.8145 | N | Ground
2 |  | Shop | 223.353 |  | 0 | 335.0295 | N | Ground
3 |  | Shop | 217.5404 |  | 0 | 326.3107 | N | Ground
4 |  | Shop | 319.2602 |  | 0 | 478.8904 | N | Ground
5 |  | Shop | 319.2602 |  | 0 | 478.8904 | N | Ground
6 | 6 | Shop | 217.5404 |  | 0 | 326.3107 | N | Ground
| 7 | Shop | 177.9289 |  | 0 | 266.8934 | N | Ground
7
| 8 | Shop | 170.1788 |  | 0 | 255.2683 | N | Ground
2 |  | 2 BHK | 491.17 |  | 0 | 712.1965 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 2 BHK | 436.99 |  | 0 | 633.6355 | N | Ground
1st to 7th Floors
1 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
2 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
3 |  | 2 BHK | 514.8 |  | 0 | 746.46 | N | 1st to 7th
4 |  | 2 BHK | 464.2 |  | 0 | 673.09 | N | 1st to 7th
5 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
6 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
Flat No. As per Sale Plan | Flat No. As per Approved Plan | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Buildings of Type JB1
Ground Floor for Residential
1 |  | 1 BHK | 368.43 |  | 0 | 534.2235 | N | Ground
2 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
3 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
4 |  | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
- | 5 | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
5 | - | Entrance Lobby & Society Office | [5 empty] | Ground
6 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
7 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
- | 8 | Entrance Lobby & Society Office | [5 empty] | Ground
8 | - | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
2 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
3 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
4 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
5 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
6 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
7 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
8 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
Buildings of Type JB2
Ground Floor
1 |  | 1 BHK | 368.43 |  | 0 | 534.2235 | N | Ground
2 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
3 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
4 |  | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
5 |  | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
6 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
7 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
8 |  | Entrance Lobby & Society Office | [5 empty] | Ground
1st to 7th Floors
1 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
2 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
3 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
4 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
5 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
6 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
7 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
8 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
Building Type KB
Ground Floor
1 |  | Entrance Lobby & Society Office | [5 empty] | Ground
2 |  | 2 BHK | 418.79 |  | 0 | 607.2455 | N | Ground
3 |  | 2 BHK | 419.04 |  | 0 | 607.608 | N | Ground
4 |  | 1 BHK | 322.11 |  | 0 | 467.0595 | N | Ground
5 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
6 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 350.8 |  | 0 | 508.66 | N | 1st to 7th
2 |  | 2 BHK | 447.27 |  | 0 | 648.5415 | N | 1st to 7th
3 |  | 2 BHK | 447.51 |  | 0 | 648.8895 | N | 1st to 7th
4 |  | 1 BHK | 350.58 |  | 0 | 508.341 | N | 1st to 7th
5 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
6 |  | 1 BHK | 352.16 |  | 0 | 510.632 | N | 1st to 7th
Building Type LB1
Ground Floor
1 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
2 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | Ground
5 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
6 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | Ground
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 352.16 |  | 0 | 510.632 | N | 1st to 7th
2 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
3 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | 1st to 7th
5 |  | 1 BHK | 352.05 |  | 0 | 510.4725 | N | 1st to 7th
6 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | 1st to 7th
Buildings of Type PB1
Ground Floor
1 |  | Entrance Lobby & Society Office | [5 empty] | Ground
2 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
3 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
4 |  | 1 BHK | 329.49 |  | 0 | 477.7605 | N | Ground
5 |  | 1 BHK | 329.49 |  | 0 | 477.7605 | N | Ground
6 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
7 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
8 |  | 1 BHK | 329.59 |  | 0 | 477.9055 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 357.96 |  | 0 | 519.042 | N | 1st to 7th
2 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
3 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
4 |  | 1 BHK | 357.85 |  | 0 | 518.8825 | N | 1st to 7th
5 |  | 1 BHK | 357.85 |  | 0 | 518.8825 | N | 1st to 7th
6 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
7 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
8 |  | 1 BHK | 357.96 |  | 0 | 519.042 | N | 1st to 7th
Buildings of Type PB2
Ground Floor
1 |  | Entrance Lobby & Society Office | [5 empty] | Ground
2 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
3 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
4 |  | 1 BHK | 329.49 |  | 0 | 477.7605 | N | Ground
5 |  | 1 BHK | 329.49 |  | 0 | 477.7605 | N | Ground
6 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
7 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
8 |  | 1 BHK | 329.59 |  | 0 | 477.9055 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 357.96 |  | 0 | 519.042 | N | 1st to 7th
2 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
3 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
4 |  | 1 BHK | 357.85 |  | 0 | 518.8825 | N | 1st to 7th
5 |  | 1 BHK | 357.85 |  | 0 | 518.8825 | N | 1st to 7th
6 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
7 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
8 |  | 1 BHK | 357.96 |  | 0 | 519.042 | N | 1st to 7th
Remarks: 1. Type HBC1 & KB - Construction work increased compared to the previous visit. Type LB1 & PB2- Construction work is same as last visit (dtd. 13/05/2025), But work is in process at the time of visit. Type JB1 & PB1 - Construction work is in process at the time of visit. (Slow Speed) Type HBC2, JB2 - Construction work is same as last visit (10/02/2025). 2. Saleable Area & Built-up area is as per our calculation. 3. We considered carpet area as per approved plan. 4. Shop rate is given as per our valuation. 5. We considered Flat rate as per Market inquiry. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. General Chargers as in cost sheet are not same for all flats so it is not mentioned in report. 8. We are not considering ground floor of HBC1 & HBC2 three shops (6, 7, 8) are merged and divided into two Shops (6 & 7). 9. We are not considering ground floor of JB1, Entance Lobby in Approved plan is placed on place of Flat no.8 & in sale Plan it is placed on place of Flat no.5. 10. In Sector 2, LB2 and MA are proposed & Sale Plan of it are not provided to us so area details are not mentioned in report. 11. The project has received Complete CC on 12/02/2018, But Construction work is still incomplete. 11. On site, we meet Mr. Pankaj Chavan - 8976378372. | [8 empty] | Type LB1, PB2 - Construction work is same since visit (07/07/2023).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The Saleable Area is as per our calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY OF CUSTOMER: |  |  |  |  | Puranik City - Sector 2
Google Map :
LB1
HBC1
HBC2
JB1
JB2
LB1
PB1
PB2
KB
JB1
JB2
KB
HBC1
LB1
PB1
PB2
HBC2

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
magicbricks | Puranik City | 1BHK | 0 | 322 | 5776.3975 | 1860000
magicbricks | Puranik City | 2BHK | 0 | 427 | 5620.6089 | 2400000
magicbricks | Puranik City | 1BHK | 0 | 378 | 6058.2011 | 2290000
magicbricks | Puranik City | 2BHK | 0 | 750 | 4666.6667 | 3500000
housing | Puranik City | 1BHK | 367 | 532.15 | 4697.9235 | 2500000
housing | Puranik City | 1BHK | 368 | 533.6 | 4696.4018 | 2506000
housing | Puranik City | 5BHK | 427 | 619.15 | 4603.0849 | 2850000
housing | Puranik City | 5BHK | 437 | 633.65 | 4603.4877 | 2917000
Average |  |  | 0 | 0 | 5090.3465
Valuation Adopted |  |  |  |  | 5000

## NOTE
03/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.

## Construction % (2) (hidden)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress | 10 | 40 | 15 | 10 | 1.4286 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 30 | 15 | 10 | 0.71429 | 0 | 0
| 7 | 7 | 100
plaster | Total Floor | completed Floor
| 7 | 7 | 100
Flooring | Total Floor | completed Floor
| 7 | 1 | 14.2857 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 7 | 0 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  |  | Bricks | 15 | 15
| 7 | 0 | 0 |  | Plaster | 10 | 10
[5 empty] | Flooring | 1.4286 | 0.71429
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 76.4286 | 85.7143

## Construction % (3) (hidden)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 0 | 20
| 4 | 0 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 0 | 20