## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-09
Name of the builder group |  |  |  | M/s.Rikki Ronie Developers
Name of the builder company |  |  |  | M/s.Rikki Ronie Developers
Name of the Project |  |  |  | Royal Lagoon E Wing
Contact Details ( Name & Contact No.) |  |  |  | Premji Shah - 022-67193333 Rahul -9819658344
Site Person - Contact Details ( Name & Contact No.) |  |  |  | 7053073333
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51800026297
Project location details |  | Royal Lagoon E Wing, CTS No.6A/16, near Royal Oasis, Jankalyan-Charkop Road, Malvani, Kandivali, Borivali, Mumbai - 400095.
CTS No |  | 6A/16
Road |  | Jankalyan-Charkop Road |  | Locality/Village |  | Malvani
City |  | Kandivali |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400095
Nearby Landmark |  | Royal Oasis |  | Distance from city centre: |  | 4Km from Kandivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Jankalyan-Charkop Road
West | NA | NA |  |  | Royal Oasis
North | NA | NA |  |  | Royal Nest
South | NA | NA |  |  | Royal Oasis Phase 1
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.2039809703,72.821324984
Location Link |  | https://goo.gl/maps/QTGy4zbBReV1geFg7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 14925.9
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.93492
Total FSI availaible for the project |  |  |  | 1.9349
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 28880.43
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | CHE/A-0432/ BP(WS)/AP |  |  | Dated | 2022-12-29
Approved Floor plan No. |  | CHE/A-0432/ BP(WS)/AP |  |  | Dated | 2022-12-29
Commencement Certificate No. |  | CHE/A-0432/BP(WS)/AP/ FCC/6/Amend |  |  | Dated | 2021-05-21
|  | Valid Up to: This C.C is now re - endorse for Wing E & F comprising of stilt for parking + 1st to 5th level podiums for parking + 6th level (E-deck for 40% LOS with swimming pool /1st floor (Amenity area + Entrance lobby + Refuge area) for wing E & F as per approved amended plan dtd. 28.04.2021. |  |  | Valid Upto Date | 2022-02-19
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 28880.43
Approved no of units |  |  | Flats - 202.
Approved no of Floors |  |  | E Wing = Gr + P1 to P5 + 1st/E Deck Floor + 2nd to 31st Floor
Proposed no of Floors |  |  | E Wing = Gr + P1 to P5 + 1st/E Deck Floor + 2nd to 33rd Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | E Wing = Gr + P1 to P5 + 1st/E Deck Floor + 2nd to 33rd Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed
Basement | 0 | Ground | 1 | Podium | 5 | Floors | 33 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.25
Excavation |  | 33 | 100% | 16.15% |  | 49.62% |  | Excavation in process | 16.5
Plinth |  | 33 | 100% |  |  |  |  | Excavation Completed | 33
RCC (Including podiums) |  | 6 | 15.38% |  |  |  |  | Footing in Process | 8.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 16.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 33
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 14700
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 8,00,000/-
Distressed valuation of the Property |  |  |  |  | 11760
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flat |  | 202 |  | 135700.6716 |  | 217121.0746
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
6 |  |  |  | 0 | 0 | Ground Floor
7 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing E
Ground Floor for Parking
1st to 5th Podium Floor for Parking
E Deck/1st Floor Part Amenties & Part Refuge Area
2nd Floor for Residential
1 |  | 2BHK | 701.4899 | 0 | 1122.3838 | 2nd Floor for Residential |  | 14611.7575
2 |  | 2BHK | 701.4899 | 0 | 1122.3838
3 |  | 2BHK | 591.0512 | 0 | 945.682
4 |  | 2BHK | 640.0274 | 0 | 1024.0439 |  |  | 14550.1574
5 |  | 2BHK | 633.9996 | 0 | 1014.3994
6 |  | 2BHK | 614.9473 | 0 | 983.9157
7 |  | 2BHK | 614.9473 | 0 | 983.9157
3rd to 7th & 9th Floor
1 |  | 2BHK | 701.4899 | 0 | 1122.3838 | 3rd to 7th & 9th Floor
2 |  | 2BHK | 701.4899 | 0 | 1122.3838
3 |  | 2BHK | 591.0512 | 0 | 945.682
4 |  | 2BHK | 640.0274 | 0 | 1024.0439
5 |  | 2BHK | 633.9996 | 0 | 1014.3994
6 |  | 2BHK | 614.9473 | 0 | 983.9157
7 |  | 2BHK | 614.9473 | 0 | 983.9157
8th Floor (Part Refuge Area)
1 |  | 2BHK | 701.4899 | 0 | 1122.3838 | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 701.4899 | 0 | 1122.3838
3 |  | 2BHK | 591.0512 | 0 | 945.682
4 |  | 2BHK | 640.0274 | 0 | 1024.0439
5 |  | 2BHK | 633.9996 | 0 | 1014.3994
6 |  | Refuge Area
7
10th Floor
1 |  | 2BHK | 702.0281 | 0 | 1123.2449 | 10th Floor
2 |  | 2BHK | 702.0281 | 0 | 1123.2449
3 |  | 2BHK | 637.0135 | 0 | 1019.2216
4 |  | 2BHK | 698.0454 | 0 | 1116.8726
5 |  | 2BHK | 692.0176 | 0 | 1107.2281
6 |  | 2BHK | 668.9826 | 0 | 1070.3722
7 |  | 2BHK | 668.9826 | 0 | 1070.3722
11th to 14th, 16th to 20th Floor
1 |  | 2BHK | 702.0281 | 0 | 1123.2449 | 11th to 14th, 16th to 20th Floor
2 |  | 2BHK | 702.0281 | 0 | 1123.2449
3 |  | 2BHK | 638.951 | 0 | 1022.3217
4 |  | 2BHK | 698.0454 | 0 | 1116.8726
5 |  | 2BHK | 692.0176 | 0 | 1107.2281
6 |  | 2BHK | 668.9826 | 0 | 1070.3722
7 |  | 2BHK | 668.9826 | 0 | 1070.3722
15th Floor (Part Refuge Area)
1 |  | 2BHK | 702.0281 | 0 | 1123.2449 | 15th Floor (Part Refuge Area)
2 |  | 2BHK | 702.0281 | 0 | 1123.2449
3 |  | 2BHK | 638.951 | 0 | 1022.3217
4 |  | 2BHK | 698.0454 | 0 | 1116.8726
5 |  | 2BHK | 692.0176 | 0 | 1107.2281
6 |  | Refuge Area
7
21st, 23rd to 28th & 30th & 31st Floor
1 |  | 2BHK | 702.0281 | 0 | 1123.2449 | 21st, 23rd to 28th & 30th & 31st Floor
2 |  | 2BHK | 702.0281 | 0 | 1123.2449
3 |  | 2BHK | 638.951 | 0 | 1022.3217
4 |  | 2BHK | 698.0454 | 0 | 1116.8726
5 |  | 2BHK | 692.0176 | 0 | 1107.2281
6 |  | 2BHK | 668.9826 | 0 | 1070.3722
7 |  | 2BHK | 668.9826 | 0 | 1070.3722
22nd & 29th Floor (Part Refuge Area)
1 |  | 2BHK | 702.0281 | 0 | 1123.2449 | 22nd & 29th Floor (Part Refuge Area)
2 |  | 2BHK | 702.0281 | 0 | 1123.2449
3 |  | 2BHK | 638.951 | 0 | 1022.3217
4 |  | 2BHK | 698.0454 | 0 | 1116.8726
5 |  | 2BHK | 692.0176 | 0 | 1107.2281
6 |  | Refuge Area
7
Remarks:
1 | Construction work same as last Visit (dtd 05/02/2024).
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclosed Balcony.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | On Site, we meet Ms. Purva - 9355881133.
8 | On RERA, only E Wing is registered.
9 | We have updated revised approved floor plan (on 06/01/2023).
10 | Validity of the C.C. is expired (on date 19/02/2022). Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Royal Lagoon E Wing
Google Map :
Formulas:
Malvani = [Malvani, row above]

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted