## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-09
Name of the builder group |  |  |  | M/s. Greenery Rock LLP
Name of the builder company |  |  |  | M/s. Greenery Rock LLP
Name of the Project (As per Builder) |  |  |  | VKG Amazon
Name of the Project (As per RERA) |  |  |  | VKG Estates
Contact Details ( Name & Contact No.) |  |  |  | 022-61898000
Site Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Ajit : 7507807006
Name / No of the Building |  |  |  | Wing A, B, C & D
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51800001980
Project location details |  | VKG Amazon, CTS No.116/A, Customs Colony Road, Marol, Andheri (East), Andheri, Mumbai, 400059.
CTS No |  | 116/A
Road |  | Customs Colony Road |  | Locality/Village |  | Marol
City |  | Andheri (East) |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400059
Near by Landmark |  | Rockview Apartment CHS |  | Distance from city centre: |  | 5.3KM from Andheri Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Lok Yamuna
West | NA | 9.15 Mt. Wide Right of the way |  |  | Customs Colony Road
North | NA | 9.00 Mt wide Internal Layout Road |  |  | Internal Road/Kanakia Rainforest |  |  | i
South | NA | Other Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.121917,72.884028
Location Link |  | https://goo.gl/maps/GfhaRP65sM8ameeY6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4180.19
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1
Total FSI availaible for the project |  |  |  | 2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8360.38
Total number of Buildings |  |  |  | 4 Wings
Approval Detail : Plan approval
Layout Approval No |  | CHE/WS/1608/K/337(NEW)/337/8/Amend |  |  | Dated | 2024-08-06
Approved Floor plan No. Wing (A, B & D) |  | CHE/WS/1608/K/337(NEW) |  |  | Dated | 2021-08-19
Approved Floor plan No. (Wing C) |  | CHE/WS/1608/K/337(NEW)/337/8/Amend |  |  | Dated | 2024-08-06
Commencement Certificate No. Valid Up to: |  | CHE/WS/1608/K/337(NEW)/FCC/ 3/Amend |  |  | Dated | 2024-08-14
|  | Re endorsement of earlier .C.C. for Wing 'A' till top of 6th(pt) residential upper floor + staircase core up to top of 15th floor + LMR + OHT i.e. ht. 50.15mt. AGL, And FCC for Wing 'B' upto 15th residential upper floor + LMR + OHT i.e. ht. 50.15mt. AGL, Re endorsement of earlier .C.C. for Wing 'C' & Wing ‘D’ upto 15th residential upper floor + LMR + OHT i.e. ht. 50.15mt. AGL, as per approved plan dated 06/08/2024. |  |  | Valid upto date: | 2026-02-27
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8360.38
Approved no of units |  |  | Sale Flats - 159, Rehab Flats - 12, EWS Flat - 6
Approved no of Floors |  |  | Wing A & B= 1B + Gr + 1st & 11th Floor Wing C = 1B + Gr + 1st & 15th Floor Wing D = 1B + Gr + 1st to 12th Floor
Proposed no of Floors |  |  | (Wing A, B, C & D) = 1B + Gr + 1st to 15th Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | (Wing A) = 1B + Gr + 1st to 15th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed, Brickwork upto 5 Floor completed, Internal Plaster upto 3.75 Floor completed, External Plaster upto 3 Floor completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 15 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed, Brickwork upto 5 Floor completed, Internal Plaster upto 3.75 Floor completed, External Plaster upto 3 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 3.75
Excavation |  | 15 | 100% | 30.49% |  | 59.5% |  | Excavation in process |  | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed |  | 15
RCC (Including podiums) |  | 6 | 35.29% |  |  |  |  | Footing in Process |  | 3
Brickwork | Brickwork & Internal Plaster | 5 | 33.33% |  |  |  |  | Footing Completed |  | 6
Internal Plaster | Brickwork & Internal Plaster | 3.75 | 25% |  |  |  |  | Basement 1 |  | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 20% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 15
Construction details: |  | (Wing B) = 1B + Gr + 1st to 15th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 16 Slab completed, Brickwork upto 15 Floor completed, Internal Plaster upto 13 Floor completed, External Plaster upto 9 Floor completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 15 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 16 Slab completed, Brickwork upto 15 Floor completed, Internal Plaster upto 13 Floor completed, External Plaster upto 9 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 3.75
Excavation |  | 15 | 100% | 67.65% |  | 85.57% |  | Excavation in process |  | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed |  | 15
RCC (Including podiums) |  | 16 | 94.12% |  |  |  |  | Footing in Process |  | 3
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed |  | 6
Internal Plaster | Brickwork & Internal Plaster | 13 | 86.67% |  |  |  |  | Basement 1 |  | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 60% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 15
Construction details: |  | (Wing C & D ) = 1B + Gr + 1st to 15th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 16 Slab completed, Brickwork upto 15 Floor completed, Internal Plaster upto 15 Floor completed, External Plaster upto 15 Floor completed, Flooring upto 11 Floor completed, Painting upto 9 Floor completed, Finishing upto 3 Floor completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 15 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 16 Slab completed, Brickwork upto 15 Floor completed, Internal Plaster upto 15 Floor completed, External Plaster upto 15 Floor completed, Flooring upto 11 Floor completed, Painting upto 9 Floor completed, Finishing upto 3 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 3.75
Excavation |  | 15 | 100% | 83.98% |  | 91.9% |  | Excavation in process |  | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed |  | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process |  | 3
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed |  | 6
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 |  | 9
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 11 | 73.33% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 9 | 60% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 3 | 20% |  |  |  |  | Plinth in process |  | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 15
Construction details: |  | (Wing D) = B + Gr + 1st to 14th Floor | [5 empty] | Excavation work completed,
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 14 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 3.5
Excavation |  | 14 | 100% | 0% |  | 20% |  | Excavation in process |  | 7
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed |  | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process |  | 2.8
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed |  | 5.6
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 |  | 8.4
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 11.2
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 14
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | Vitrified tiles flooring,Granite Kitchen Platform, Decorative Entarnace, Swimming Pool, Childerns Play Area, Garden, Parking, Lift etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 15600 |  |  | 15625
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Share Money |  |  |  |  | 600/-
Dish TV |  |  |  |  | 3000/-
Maintenance Fees |  |  |  |  | 95760/-
Society Formation Charges |  |  |  |  | 6000/-
Electricity & Water Charges |  |  |  |  | 30000/-
Development Charges |  |  |  |  | 119700/-
Club Membership |  |  |  |  | 250000/-
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 1000000/-
Distressed valuation of the Property |  |  |  |  | 12480
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :(Sale Flat)
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 36 |  | 18282.8693 |  | 29252.5908
Wing B |  | 35 |  | 21146.4162 |  | 33834.2659
Wing C |  | 51 |  | 25942.747 |  | 37616.9831
Wing D |  | 37 |  | 22904.0698 |  | 33210.9012
Total |  | 159 |  | 88276.1022 |  | 133914.741
Residential Area Details :(Rehab & EWS Flat)
Wing A (Rehab) |  | 4 |  | 1673.1562 |  | 2677.0499
Wing B (Rehab) |  | 6 |  | 2881.3075 |  | 4610.092
Wing C (EWS) |  | 6 |  | 2732.7643 |  | 4372.4229
Wing D (Rehab) |  | 2 |  | 979.9546 |  | 1420.9341 |  | 161
Total |  | 18 |  | 8267.1826 |  | 13080.4989 |  | 161
Grand Total |  | 177 |  | 96543.2848 |  | 146995.2399 |  | 41
Building Details Floor Wise
Details of Residential in Building
Flats No. | Flats (Sale or Rehab)/ EWS | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A
Basement Floor For Parking
Ground Floor for Parking & Residential
1 | Sale | 1BHK | 403.8653 | 0 | 646.1844 | Ground Floor for Parking & Residential
1st Floor for Residential & Parking
1 | Rehab | 1BHK | 429.4836 | 0 | 687.1738 | 1st Floor for Residential & Parking
2 | Rehab | 1BHK | 407.0945 | 0 | 651.3512
2nd Floor for Residential & Entrance Lobby
1 | Rehab | 1BHK | 429.4836 | 0 | 687.1738 | 2nd Floor for Residential & Entrance Lobby
2 | Rehab | 1BHK | 407.0945 | 0 | 651.3512
3rd to 8th, 10th & 11th Floor
1 | Sale | 1BHK | 429.4836 | 0 | 687.1738 | 3rd to 8th, 10th & 11th Floor
2 | Sale | 1BHK | 407.0945 | 0 | 651.3512
3 | Sale | 2BHK | 610.5341 | 0 | 976.8545
4 | Sale | 2BHK | 606.8743 | 0 | 970.9989
9th Floor (Part Refuge Area)
1 | Sale | 1BHK | 429.4836 | 0 | 687.1738 | 9th Floor (Part Refuge Area)
2 | Sale | 1BHK | 407.0945 | 0 | 651.3512
3 | Sale | 2BHK | 610.5341 | 0 | 976.8545
Wing B
Basement Floor For Amenities & Parking
Ground Floor for Parking & Fitness Center
1st Floor for Residential & Parking
1 |  | Parking Area |  |  |  | 1st Floor for Residential & Parking |  | 15217.2981
2 | Rehab | 1BHK | 472.3243 | 0 | 755.7189
3 | Rehab | 1BHK | 484.1647 | 0 | 774.6636
4 | Rehab | 1BHK | 484.1647 | 0 | 774.6636
2nd Floor for Residential & Entrance Lobby
1 |  | Entrance Lobby |  |  |  | 2nd Floor for Residential & Entrance Lobby |  | 15217.2981
2 | Rehab | 1BHK | 472.3243 | 0 | 755.7189
3 | Rehab | 1BHK | 484.1647 | 0 | 774.6636
4 | Rehab | 1BHK | 484.1647 | 0 | 774.6636
3rd to 8th, 10th & 11th Floor
1 | Sale | 2BHK | 610.9646 | 0 | 977.5434 | 3rd to 8th, 10th & 11th Floor
2 | Sale | 2BHK | 591.9124 | 0 | 947.0598
3 | Sale | 2BHK | 607.3049 | 0 | 971.6878
4 | Sale | 2BHK | 607.3049 | 0 | 971.6878
9th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 9th Floor (Part Refuge Area)
2 | Sale | 2BHK | 591.9124 | 0 | 947.0598
3 | Sale | 2BHK | 607.3049 | 0 | 971.6878
4 | Sale | 2BHK | 607.3049 | 0 | 971.6878 | [5 empty] | to |  | 1st | 1
Wing C | [10 empty] | 101 to 101 | 1 | 101 | 101
Basement Floor For Domestic Watertank, Rainwater Tank, Flushing Water Tank & Parking | [10 empty] | 102 to 102 | 2 | 102 | 102
Ground Floor For Amenities & Parking
1st Floor For Residential & Parking | [10 empty] | #REF! | #REF! | #REF! | #REF!
1 | EWS | 1BHK | 484.1647 | 0 | 774.6636 | 1st Floor For Residential & Parking |  |  |  |  | #REF! | #REF! | #REF! | #REF!
2 | EWS | 1BHK | 484.1647 | 0 | 774.6636 | [5 empty] | #REF! | #REF! | #REF! | #REF!
3 | EWS | 1BHK | 398.0527 | 0 | 636.8844 | [5 empty] | #REF! | #REF! | #REF! | #REF!
2nd Floor For Residential & Part Society Office, Entrance Lobby & Parking | [7 empty] | 14845.1544 |  |  | #REF! | #REF! | #REF! | #REF!
1 | EWS | 1BHK | 484.1647 | 0 | 774.6636 | 2nd Floor For Residential & Part Society Office, Entrance Lobby & Parking |  |  |  |  | #REF! | #REF! | #REF! | #REF!
2 | EWS | 1BHK | 484.1647 | 0 | 774.6636 | [5 empty] | #REF! | #REF! | #REF! | #REF!
3 | EWS | 1BHK | 398.0527 | 0 | 636.8844
- | Society Office, Entrance Lobby & Parking
3rd to 8th Floor For Residential | [7 empty] | 50.3301
1 | Sale | 2BHK | 607.3049 | 0 | 880.5921 | 3rd to 8th Floor For Residential
2 | Sale | 2BHK | 607.3049 | 0 | 880.5921
3 | Sale | 1BHK | 398.0527 | 0 | 577.1764 |  |  | 18286.866 | 1.6039
4 | Sale | 1BHK | 414.8446 | 0 | 601.5246
9th Floor For Part Refuge Area
1 | Sale | 2BHK | 607.3049 | 0 | 880.5921 | 9th Floor For Part Refuge Area
2 | Sale | 2BHK | 607.3049 | 0 | 880.5921
3 | Sale | 1BHK | 398.0527 | 0 | 577.1764
4 | Refuge Area | [9 empty] | #REF! | #REF! | #REF! | #REF!
10th to 15th Floor | [10 empty] | & |  | #REF! | #REF!
1 | Sale | 2BHK | 607.3049 | 0 | 880.5921 | 10th to 15th Floor |  |  |  |  | #REF! | 1 | #REF! | #REF!
2 | Sale | 2BHK | 607.3049 | 0 | 880.5921 | [5 empty] | #REF! | #REF! | #REF! | #REF!
3 | Sale | 1BHK | 398.0527 | 0 | 577.1764 | [5 empty] | #REF! | #REF! | #REF! | #REF!
4 | Sale | 1BHK | 414.8446 | 0 | 601.5246 | [5 empty] | #REF! | #REF! | #REF! | #REF!
Wing D | [10 empty] | #REF! | #REF! | #REF! | #REF!
Basement Floor For Amenities & Parking | [10 empty] | #REF! | #REF! | #REF! | #REF!
Ground Floor for Parking | [10 empty] | #REF! | #REF! | #REF! | #REF!
1st Floor for Residential & Parking Area | [10 empty] | #REF! | #REF! | #REF! | #REF!
1 |  | Parking Area |  |  |  | 1st Floor for Residential & Parking Area |  |  |  |  | #REF! | #REF! | #REF! | #REF!
2 | [10 empty] | #REF! | #REF! | #REF! | #REF!
3 | [10 empty] | #REF! | #REF! | #REF! | #REF!
4 | Rehab | 1BHK | 489.9773 | 0 | 710.4671 | [5 empty] | #REF! | #REF! | #REF! | #REF!
2nd Floor for Residential, Entrance Lobby & Parking | [10 empty] | #REF! | #REF! | #REF! | #REF!
1 |  | Parking Area |  |  |  | 2nd Floor for Residential, Entrance Lobby & Parking |  |  |  |  | #REF! | #REF! | #REF! | #REF!
2 | [10 empty] | #REF! | #REF! | #REF! | #REF!
3 | [10 empty] | #REF! | #REF! | #REF! | #REF!
4 | Rehab | 1BHK | 489.9773 | 0 | 710.4671 | [5 empty] | #REF! | #REF! | #REF! | #REF!
3rd to 8th, 10th & 11th Floor | [10 empty] | #REF! | #REF! | #REF! | #REF!
1 | Sale | 2BHK | 610.5341 | 0 | 885.2744 | 3rd to 8th, 10th & 11th Floor |  |  |  |  | #REF! | #REF! | #REF! | #REF!
2 | Sale | 2BHK | 610.5341 | 0 | 885.2744 |  |  | 19222.2762 | 618 |  | #REF! | #REF! | #REF! | #REF!
3 | Sale | 2BHK | 617.1001 | 0 | 894.7952 |  |  | 16823.5337 | 639 |  | #REF! | #REF! | #REF! | #REF!
4 | Sale | 2BHK | 635.3989 | 0 | 921.3284 | [5 empty] | #REF! | #REF! | #REF! | #REF!
9th Floor (Part Refuge Area ) | [10 empty] | #REF! | #REF! | #REF! | #REF!
1 | Sale | Refuge Area |  |  |  | 9th Floor (Part Refuge Area ) |  |  |  |  | #REF! | #REF! | #REF! | #REF!
2 | Sale | 2BHK | 610.5341 | 0 | 885.2744 |  |  | 19222.2762 | 618 |  | #REF! | #REF! | #REF! | #REF!
3 | Sale | 2BHK | 617.1001 | 0 | 894.7952 |  |  | 16823.5337 | 639 |  | #REF! | #REF! | #REF! | #REF!
4 | Sale | 2BHK | 635.3989 | 0 | 921.3284
12th Floor (Part Terrace Area )
1 | Sale | Terrace Area |  |  |  | 12th Floor (Part Terrace Area )
2 | Sale
3 | Sale | 2BHK | 617.1001 | 0 | 894.7952
4 | Sale | 2BHK | 635.3989 | 0 | 921.3284
Remarks:
1. Wing A = Construction work is in process at the time of the visit. (Slow Speed) Wing B, C & D = Construction work is in process at the time of the visit. Internal visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet Area 5. We have considered rate by verifying it from market inquire. 7. Car parking is subjected to authentic documentation. 8. We have updated revised approved floor plan (on 10/12/2021). 9. We have updated revised C.C (on 16/03/2024). 10. We have considered construction percent as per proposed no. of floor ( B + Gr.+ 15th Floor). 11. We have updated revised C.C from MCGM Site (on 21/09/2024). 12. Please provide revised approved plans. 13. We have updated revised approved plan for Wing C from MCGM site on 23/11/2024. 14. Validity of CC is expired on 27/02/2025. Please provide latest CC. | [7 empty] | 1. Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | VKG Amazon
Layout:
Google Map :
Wing A
Wing B
Wing C
Wing D
A
C
D

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | VKG Amazon | 1BHK | 415 | 622.5 | 15662.6506 | 9750000
housing. | VKG Amazon | 2BHK | 615 | 922.5 | 15718.1572 | 14500000
Average |  |  |  |  | 15690.4039
Valuation Adopted |  |  |  |  | 15700