## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Goregoan
Date Of Property Visit |  |  |  |  | 2025-08-09
Name of the builder group |  |  |  |  | M/s.SRA Project Developers Private Limited
Name of the builder company |  |  |  |  | M/s.SRA Project Developers Private Limited
Name of the Project |  |  |  |  | Vrindavan City (A, B, C Wings)
Contect Details ( Name & Contect No.) |  |  |  |  | 2502390516
Name / No of the Building |  |  |  |  | Building No. 1 = Type A Building No. 2 = Type B Building No. 3 = Type C
Docouments Provided |  |  |  |  | Approved Plans, NA Cum CC
RERA No. |  |  |  |  | Wing A-P99000019715 Wing B-P99000019770 Wing C-P99000019702
Project location details |  | Vrindavan City Wing A,B,C, S.No. 28/3/1,30/3, Kurgoan, Palghar.
S No |  | 28/3/1, 30/3 |  |  | Locality |  | Kurgoan
Road |  | Boisar- Tarapur Road |  |  | District | Palghar | Palghar
City |  | Palghar |  |  | Pin Code | 401501 | 401501
Near by Landmark |  | Viraj Shiriram centennial School |  |  | Distance from city centre: |  | 6.2 Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | S.R.A.-2 |  | Open |  | Under Construction Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.8392366,72.7238103
Location Link |  | https://goo.gl/maps/JA5zuSqokdvnsURS7
Approval details:
Approved usage of the Property: Residential + Commericial (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 5475
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 4927.5
Total number of Buildings |  |  |  |  | 3 Buildings
Approval Detail : Plan approval
Layout Approval No |  | MHSL/KS.1/T.1/NP/SR-69/2018. |  |  |  | Dated | 2018-08-31
Approved Floor plan No. |  | MHSL/KS.1/T.1/NP/SR-69/2018. |  |  |  | Dated | 2018-08-31
NA Cum Commencement Certificate No. |  | MHSL/KS.1/T.1/NP/SR-69/2018. Valid upto: Building no.1,2 & 3 = G + 1st to 4th Floor |  |  |  | Dated | 2018-08-31
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2018-08-31 |  | Expected Completion |  | Completed
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 4927.5 |  | Approved no of units |  | Flats = 165 & Shops = 04
Approved no of Floors |  | G + 1st to 4th Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years
Material laying at Site: : Nothing
Construction details: |  | Building No.1 (Type A) = G + 1st to 4th Floor Building No.2 (Type B) = G + 1st to 4th Floor Building No.3 (Type C) = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.2 (Type B) = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 85% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building No.3 (Type C) = G + 1st to 4th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 92.5% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 50% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3800
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6700
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 100000/-
Society formation charges | [5 empty] | 55000/-
Recommended rate of Parking | [5 empty] | NA
Development charges | [5 empty] | 95000/-
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3040
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1 (Type A)
Ground Floor is for parking, residential & Commercial
1 |  | Shop | 334.2222 |  | 0 | 501.3333 | N | Ground Floor. | 1.5
2 |  | Shop | 302.4684 |  | 0 | 453.7026 | N
3 |  | Shop | 302.4684 |  | 0 | 453.7026 | N
4 |  | Shop | 158.769 |  | 0 | 238.1535 | N
1 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
2 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
3 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
4 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
5 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
6 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
7 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
1st to 4th Floor
1 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N | 1st to 4th Floor
2 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
3 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
4 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
5 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
6 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
7 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
8 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
9 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
10 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
11 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
12 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
13 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
14 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
Building No.2 (Type B)
Ground Floor is for residential & Parking
1 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N | Ground Floor.
2 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
3 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
4 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
5 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
6 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
7 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
8 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
9 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
10 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
1st to 4th Floor
1 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N | 1st to 4th Floor
2 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
3 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
4 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
5 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
6 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
7 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
8 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
9 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
10 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
11 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
12 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
13 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
14 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
Building No.3 (Type C)
Ground Floor is for residential & Parking
1 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N | Ground Floor.
2 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
3 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
4 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
1st to 4th Floor
1 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N | 1st to 4th Floor
2 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
3 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
4 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
5 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
6 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
7 |  | 1RK | 276.4195 |  | 0 | 400.8083 | N
8 |  | 1RK | 274.8049 |  | 0 | 398.4671 | N
Remarks: 1. Wing A, B & C = All work Completed. Please provide OC. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. . We have considered rate by verifying it from market inquire. 5. Car parking is subjected to authentic documentation. 6. Layout downloaded from rera site for update. 7. As per RERA, completion period of project name Vrindavan City A, B, C Wing is expired on Date 28/02/2023 but still project is under construction
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vrindavan City (A, B, C Wings)
Google Map :
Formulas:
Kurgoan = [Kurgoan, row above]
B Wing
C Wing
A
B
C

## 1
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 1 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 10 | Recommended |  |  | 30 | 30 | 15 | 1 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0.5 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 1 | 1
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 66 | 76

## 2
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## 3
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 0
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 0
| 5 | 5 | 100
plaster | Total Floor | completed Floor | 100
| 5 | 5 | 0
Flooring | Total Floor | completed Floor
| 5 | 5 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 5 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 90 | 95

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.05 | 4.04 | 12.322 | CB | 1.98 | 0.8 | 1.584 |  |  | 0
|  |  |  | 0 | FB | 1.98 | 1 | 1.98 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.44 | 1.91 | 4.6604 | CB | 2.44 | 1 | 2.44 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.22 | 1.24 | 1.5128 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 199.0823 | 18.4952 |  |  | 64.6271 | 6.004 |  | 0 | 0
24.4992

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0