## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-09
Name of the builder group |  |  |  | M/s. Prabhav Realty and Infrastructure Pvt Ltd
Name of the builder company |  |  |  | M/s. Prabhav Realty and Infrastructure Pvt Ltd
Name of the Project |  |  |  | Silver Skyline
Contact Details ( Name & Contact No.) |  |  |  | Mr. Sachin 9082457990
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Santosh 7718939219
Name / No of the Building |  |  |  | Wing A & B
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800004072
Project location details |  | Silver Skyline, CTS No.826, Plot No.38 & (As per CC, C.T.S No 826B), near Shiv Shakti Chs , J.P.Road, Andheri, Andheri, Andheri, Mumbai - 400053.
CTS No |  | 826, Plot No.38 & (As per CC, C.T.S No 826B)
Road |  | J.P.Road |  | Locality/Village |  | Andheri
City |  | Andheri |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400053
Nearby Landmark |  | Shiv Shakti Chs |  | Distance from city centre: |  | 1.3 Km from D N Nagar Metro Statio
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Manisha School
West | NA | NA |  |  | Bldg No.34
North | NA | NA |  |  | Bharat Vishwa Society
South | NA | NA |  |  | D.N. Nagar Station
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.1263454,72.8278878
Location Link |  | https://goo.gl/maps/DzqgaVTAQ5Uf1ZZDA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2596
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.88502
Total FSI availaible for the project |  |  |  | 1.885
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4893.5
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | CE/9331/WS/AK |  |  | Dated | 2022-01-14
Approved Floor plan No. |  | CE/9331/WS/AK |  |  | Dated | 2022-01-14
Commencement Certificate No. Valid Up to: |  | CE/9331/WS/AK/FCC/2/Amend |  |  | Dated | 2022-03-10
|  | Further C.C. up to top of 17th floor for both the wings & top of 18th (pt) floor for wing ‘A’ i.e. total height 55.95 mtr. AGL, as per approved plans dated 14/01/2022 by restricting C.C. of 18th floor of wing ‘B’ + 19th floor along with LMR & OHT of the building against availed installment facility is approved. |  |  | Valid Upto Date | 2022-04-17
O. Certificate No.: (Part OC) |  | CE/9331/WS/AK/OCC/1/New Approved upto : Part OC for part stilt + 2nd to 11th floors for wings ‘A’ & ‘B’ |  | Date of approval: | Dated | 2022-05-09
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4893.5
Approved no of units |  |  | Flats - 117
Approved no of Floors |  |  | A Wing = Stilt+ 1st Floor ( Podium) + 2nd to 19th Floor B Wing = Stilt+ 1st Floor ( Podium) + 2nd to 18th Floor
Proposed no of Floors |  |  | A & B Wing = Stilt + 1st Floor ( Podium) + 2nd to 20th Floor
B Wing = Stilt+ 1st Floor ( Podium) + 2nd to 20th Floor
Expected Completion |  |  | As per RERA - 31/03/2024
Projected life of the structure |  |  | 57 Years
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | A & B Wing = Stilt + 1st Floor ( Podium) + 2nd to 20th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 15 Floor, Painting upto 11 Floor, Finishing upto 11 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 19 Slab, Brickwork upto 18 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 15 Floor, Painting upto 11 Floor, Finishing upto 11 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 81.82% |  | 90.64% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20 | s
RCC (Including podiums) |  | 19 | 90.48% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 18 | 90% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 15 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 11 | 55% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 11 | 55% |  |  |  |  | Plinth in process | 15
Possession |  | 11 | 55% |  |  |  |  | Plinth completed | 20
Construction details: |  | B Wing = Stilt+ 1st Floor ( Podium) + 2nd to 20th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 50% |  | 75% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 18000
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Infrastructure & Development Charges |  |  |  |  | 5,00,000/-
Share Money / Society Membership/Application/Entrance Fees |  |  |  |  | 20,260/-
Legal Services Charges |  |  |  |  | NA
Corpus Fund |  |  |  |  | 98000/-
Electric / Water Meter Charges |  |  |  |  | 25,000/-
Society Formation Charges |  |  |  |  | NA
Advance Maintenance for 12th Months |  |  |  |  | 1,50,000/-
Recommended rate of Parking |  |  |  |  | 10,00,000/-
Distressed valuation of the Property |  |  |  |  | 14400
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 61 |  | 32878.0998 |  | 52604.9597
Wing B |  | 56 |  | 31644.4378 |  | 50631.1004
Total |  | 117 |  | 64522.5376 |  | 103236.0601
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
A Wing
Ground Floor for Parking
1st Floor for Parking
2nd Floor for Residential & Fitness Centre
1 |  | Fitness Centre |  |  |  | 2nd Floor for Residential & Fitness Centre
2 |  | 2BHK | 543.6896 | 0 | 869.9034
3 |  | 2BHK | 569.9538 | 0 | 911.9261
4 |  | 1BHK | 389.3339 | 0 | 622.9342
3rd to 6th, 8th to 10th Floor
1 |  | 1BHK | 389.3339 | 0 | 622.9342 | 3rd to 6th, 8th to 10th Floor |  |  |  |  | 301 to 1001 | 301 | 1001
2 |  | 2BHK | 543.6896 | 0 | 869.9034 | [5 empty] | 302 to 1002 | 302 | 1002
3 |  | 2BHK | 569.9538 | 0 | 911.9261 | [5 empty] | 303 to 1003 | 303 | 1003
4 |  | 1BHK | 389.3339 | 0 | 622.9342 | [5 empty] | 304 to 1004 | 304 | 1004
7th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 |  | 2BHK | 543.6896 | 0 | 869.9034
3 |  | 2BHK | 569.9538 | 0 | 911.9261
4 |  | 1BHK | 389.3339 | 0 | 622.9342
11th Floor
1 |  | 1BHK | 414.3064 | 0 | 662.8902 | 11th Floor
2 |  | 2BHK | 543.6896 | 0 | 869.9034
3 |  | 2BHK | 669.9514 | 0 | 1071.9222
4 |  | 1BHK | 412.6918 | 0 | 660.3068
12th Floor
1 |  | 1BHK | 414.3064 | 0 | 662.8902 | 12th Floor
2 |  | 2BHK | 571.2455 | 0 | 913.9928
3 |  | 2BHK | 669.9514 | 0 | 1071.9222
4 |  | 1BHK | 412.6918 | 0 | 660.3068
13th Floor
1 |  | 1BHK | 414.3064 | 0 | 662.8902 | 13th Floor
2 |  | 2BHK | 571.2455 | 0 | 913.9928
3 |  | 2BHK | 669.9514 | 0 | 1071.9222
4 |  | 1BHK | 412.6918 | 0 | 660.3068
14th Floor (Part Refuge Area)
1 |  | 3BHK | 1099.5426 | 0 | 1759.2682 | 14th Floor (Part Refuge Area)
2 |  | Refuge Area
3 |  | 2BHK | 658.4339 | 0 | 1053.4942
15th Floor
1 |  | 3BHK | 935.3916 | 0 | 1496.6266 | 15th Floor
2 |  | 1BHK | 414.3064 | 0 | 662.8902
3 |  | 2BHK | 658.4339 | 0 | 1053.4942
16th to 18th Floor
1 |  | 3BHK | 935.3916 | 0 | 1496.6266 | 16th to 18th Floor
2 |  | 1BHK | 414.3064 | 0 | 662.8902
3 |  | 2BHK | 658.4339 | 0 | 1053.4942
19th Floor (Part Terrace Area)
1 |  | Terrace Area |  |  |  | 19th Floor (Part Terrace Area) |  | #DIV/0!
2 | [7 empty] | #DIV/0!
3 |  | 1BHK | 658.4339 | 0 | 1053.4942 |  |  | 11390.6654
B Wing
2nd Floor for Residential & Fitness Centre
5 |  | Fitness Centre |  |  |  | 2nd Floor for Residential & Fitness Centre
6 |  | 2BHK | 543.6896 | 0 | 869.9034
7 |  | 2BHK | 569.9538 | 0 | 911.9261
8 |  | 1BHK | 389.3339 | 0 | 622.9342
3rd to 6th, 8th to 10th Floor
5 |  | 1BHK | 389.3339 | 0 | 622.9342 | 3rd to 6th, 8th to 10th Floor |  |  |  |  | 305 to 1005 | 305 | 1005
6 |  | 2BHK | 543.6896 | 0 | 869.9034 | [5 empty] | 306 to 1006 | 306 | 1006
7 |  | 2BHK | 569.9538 | 0 | 911.9261 | [5 empty] | 307 to 1007 | 307 | 1007
8 |  | 1BHK | 389.3339 | 0 | 622.9342 | [5 empty] | 308 to 1008 | 308 | 1008
7th Floor (Part Refuge Area)
5 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
6 |  | 2BHK | 543.6896 | 0 | 869.9034
7 |  | 2BHK | 569.9538 | 0 | 911.9261
8 |  | 1BHK | 389.3339 | 0 | 622.9342 |  |  | 19263.6716
11th Floor
5 |  | 1BHK | 414.3064 | 0 | 662.8902 | 11th Floor
6 |  | 2BHK | 543.6896 | 0 | 869.9034
7 |  | 2BHK | 669.9514 | 0 | 1071.9222
8 |  | 1BHK | 412.6918 | 0 | 660.3068
12th Floor
5 |  | 1BHK | 414.3064 | 0 | 662.8902 | 12th Floor
6 |  | 2BHK | 571.2455 | 0 | 913.9928 |  |  | 18052.6593
7 |  | 2BHK | 669.9514 | 0 | 1071.9222
8 |  | 1BHK | 412.6918 | 0 | 660.3068
13th Floor
5 |  | 1BHK | 414.3064 | 0 | 662.8902 | 13th Floor
6 |  | 2BHK | 571.2455 | 0 | 913.9928
7 |  | 2BHK | 669.9514 | 0 | 1071.9222
8 |  | 1BHK | 412.6918 | 0 | 660.3068
14th Floor (Part Refuge Area)
4 |  | 3BHK | 1099.5426 | 0 | 1759.2682 | 14th Floor (Part Refuge Area)
5 |  | Refuge Area
6 |  | 2BHK | 583.4088 | 0 | 933.4541
15th Floor
4 |  | 3BHK | 935.3916 | 0 | 1496.6266 | 15th Floor
5 |  | 3BHK | 981.6768 | 0 | 1570.6829
16th to 18th Floor
4 |  | 3BHK | 935.3916 | 0 | 1496.6266 | 16th to 18th Floor |  | 16704.2338 |  |  | #REF! | #REF! | #REF!
5 |  | 3BHK | 936.3604 | 0 | 1498.1766 |  |  | 16686.9516 |  |  | #REF! | #REF! | #REF!
Remarks:
1 | Part OC received upto 11th floor only. Construction work is same as last visit dtd. 06/05/2024.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet.
5 | We have considered rate by verifying it from market inquire.
6 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
7 | Car parking is subjected to authentic documentation.
8 | As required by Bank, we have update Flat no.1702 - A wing from proposed Plans(Approved by S.E.B.P). Bank need to verify it before disbursement. Please provide revised approved Plans & CC.
8 | We have updated revised approved Plans & CC from MCGM site (on 22/08/2023)
9 | The validity of C.C. expried on 17/04/2022. Please provide latest C.C.
10 | As per RERA, completion period of project Silver Skyline is expired on 31/03/2024 but still project is under construction.
11 | As checked on RERA portal on date 18/08/2025, we have observed that above project "Silver Skyline" is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Pratik Niwate |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
2023-11-06
PHOTOGRAPHS OF PROPERTY : |  |  | Silver Skyline
Google Map :
Formulas:
Andheri = [Andheri, row above]

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted