## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-11
Name of the builder group |  |  |  |  | M/s. Savera Builders & Developers
Name of the builder company |  |  |  |  | M/s. Savera Builders & Developers
Name of the Project |  |  |  |  | Savera Complex
Contect Details ( Name & Contect No.) |  |  |  |  | 890546090/8600247466
Name / No of the Building |  |  |  |  | Building No.2 = Type A4 (Wing A) Building No.2 = Type A5 (Wing B) Building No.2 = Type A6 (Wing C) Building No.4 = Type A10 (Wing A)
Docouments Provided |  |  |  |  | Approved Plans & CC.
RERA No. |  |  |  |  | P99000016226
Project location details |  | Savera Complex, Gut No. 144, Kelve road, Zanzroli, Palghar, Palghar.
Gut No |  | 144 |  |  |  |  | Locality | Zanzroli
Road | Kelve road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401401
Near by Landmark |  | S. S Park |  |  | Distance from city centre: |  | 1.2 Km from Kelve Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Sambhav Apartment |  | Building |  | Internal Road |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.6229 |  | Longitude |  | 72.797
Location Link |  | https://goo.gl/maps/H2y56PwCVer8VWoAA?coh=178572&entry=tt
Approval details:
Approved usage of the Property: |  |  |  |  | Residential & Commercial.
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 10167.73
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0.18
Total FSI availaible for the project |  |  |  |  | 1.08
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 10981.15
Total number of Buildings |  |  |  |  | 4 Wings
Approval Detail : Plan approval
Layout Approval No |  |  | MHSL/K-1/B.S.P./S.R./C.R./241/18 |  |  |  | Dated | 16/02/2018.
Approved Floor plan No. Building No.2 Type A4 (Wing A) Building No.4 Type A10 (Wing A) |  |  | MHSL/K-1/B.S.P./S.R./C.R./241/18 |  |  |  | Dated | 16/02/2018.
Approved Floor plan No. Building No.2 Type A5 (Wing B) Building No.2 Type A6 (Wing C) |  |  | MHSL/K-1/MJ1/B.S.P/S.R/C.R/ 201/2019 |  |  |  | Dated | 2022-01-20
Commencement Certificate No. Building No.2 Type A4 (Wing A) Building No.2 Type A5 (Wing B) Building No.2 Type A6 (Wing C) Building No.4 Type A10 (Wing A) |  |  | MHSL/KS.1/T.1/NAP/SR.201/2019 Valid Up to: Gr. + 1st to 5th Floor |  |  |  | Dated | 2022-01-20
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2018-02-16 |  | Expected Completion |  | 2026-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 10981.15 |  | Approved no of units |  |  | Shop = 27 Flat = 86
Approved no of Floors |  | Building No.2 - Type A4 (Wing A) = G + 1st to 4th Floor Building No.2 - Type A5 (Wing B) = G + 1st to 5th Floor Building No.2 - Type A6 (Wing C) = G + 1st to 5th Floor Building No.4 - Type A10 (Wing A) = G + 1st to 4th Floor
Proposed no of Floors |  | Building No.2 - Type A4 (Wing A) = G + 1st to 5th Floor Building No.2 - Type A5 (Wing B) = G + 1st to 5th Floor Building No.2 - Type A6 (Wing C) = G + 1st to 5th Floor Building No.4 - Type A10 (Wing A) = G + 1st to 5th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building No.2 - Type A4 (Wing A)= G + 1st to 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 4 Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 4 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 4 Floor, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 4 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 83.5% |  | 92% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 4 | 80% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 80% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 80% | [5 empty] | Basement 3 | 0 |  | s
Painting & Wooden |  | 4 | 80% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.2 - Type A5 (Wing B)= G + 1st to 5th Floor Building No.2 - Type A6 (Wing C)= G + 1st to 5th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 93% |  | 95% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 60% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.2 - Type A6 (Wing C)= G + 1st to 5th Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 93% |  | 95% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 60% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.4 = G + 1st to 5th Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 2.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 5
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000/-
Society formation & Development charges | [5 empty] | 120000/-
Recommended rate of Parking | [5 empty] | 1,00,000/-
Distressed valuation of the Property | [5 empty] | 2800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Building No. 2 | Wing A | 7 |  | 601.277 |  |  | 901.9156
| Wing B | 13 |  | 1198.5714 |  |  | 1797.8571
| Wing C | 7 |  | 635.7218 |  |  | 953.5828
Total |  | 27 |  | 2435.5703 |  |  | 3653.3554
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Building No. 2 | Wing A | 16 |  | 5055.6355 |  |  | 8872
| Wing B | 31 |  | 11893.4127 |  |  | 17659.5888
| Wing C | 21 |  | 7917.7831 |  |  | 11993.2745
Building No. 4 Wing A |  | 18 |  | 5904.5922 |  |  | 8561.6587
Total |  | 86 |  | 30771.4235 |  |  | 47086.522 |  |  | 33206.9938
Building details Floor Wise
Details of Flats in Building
Flat No. (As per sales plan) | Flat No. (As per approved plan) | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No. 2
Type A4
Wing A
Ground floor is for Parking & Commercial
1 | 1 | Shop | 94.7232 |  | 0 | 142.0848 | N | Ground floor
2 | 2 | Shop | 98.9212 |  | 0 | 148.3817 | N
3 | 3 | Shop | 97.7371 |  | 0 | 146.6057 | N
4 | 4 | Shop | 42.6254 |  | 0 | 63.9382 | N
5 | 5 | Shop | 97.7371 |  | 0 | 146.6057 | N
6 | 6 | Shop | 96.9836 |  | 0 | 145.4755 | N
7 | 7 | Shop | 72.5494 |  | 0 | 108.824 | N
1st to 4th floor
1 | 1 | 1BHK | 315.9772 |  | 0 | 552 | N | 1st to 4th floor |  | 1.747
2 | 2 | 1BHK | 315.9772 |  | 0 | 557 | N
3 | 3 | 1BHK | 315.9772 |  | 0 | 557 | N
4 | 4 | 1BHK | 315.9772 |  | 0 | 552 | N
Building No. 2
Type A5
Wing B
Ground floor is for Parking, Commercial & Residential
8 |  | Shop | 99.1364 |  | 0 | 148.7047 | N | Ground floor
9 | 2 | Shop | 77.5008 |  | 0 | 116.2512 | N
10 | 3 | Shop | 99.1364 |  | 0 | 148.7047 | N
11 | 4 | Shop | 99.1364 |  | 0 | 148.7047 | N
12 | 5 | Shop | 98.9212 |  | 0 | 148.3817 | N
13 | 6 | Shop | 94.7232 |  | 0 | 142.0848 | N
14 | 7 | Shop | 63.6152 |  | 0 | 95.4229 | N
15 | 8 | Shop | 76.1015 |  | 0 | 114.1522 | N
16 | 9 | Shop | 96.9836 |  | 0 | 145.4755 | N
17 | 10 | Shop | 96.2302 |  | 0 | 144.3452 | N
18 | 11 | Shop | 96.2302 |  | 0 | 144.3452 | N
19 | 12 | Shop | 75.2404 |  | 0 | 112.8605 | N
20 | 13 | Shop | 125.6159 |  | 0 | 188.4238 | N
1 | 13 | 1BHK | 353.0592 |  | 0 | 529.5888 | N
1st to 4th floor
1 |  | 1BHK | 401.5779 |  | 0 | 571 | N | 1st to 4th floor |  |  | 1.4219
2 |  | 1BHK | 401.5779 |  | 0 | 571 | N |  |  |  | 1.4219
3 |  | 1BHK | 381.0187 |  | 0 | 572 | N |  |  |  | 1.5012
4 |  | 1BHK | 373.2686 |  | 0 | 572 | N |  |  |  | 1.5324
5 |  | 1BHK | 375.3138 |  | 0 | 570 | N |  |  | 29.0775 | 1.5187
6 |  | 1BHK | 375.3138 |  | 0 | 570 | N |  |  |  | 1.5187
5th floor | [10 empty] | #DIV/0!
1 |  | 1BHK | 401.5779 |  | 0 | 571 | N | 5th floor |  |  | 1.4219
2 |  | 1BHK | 401.5779 |  | 0 | 571 | N |  |  |  | 1.4219
3 |  | 1BHK | 381.0187 |  | 0 | 572 | N |  |  |  | 1.5012
4 |  | 1BHK | 373.2686 |  | 0 | 572 | N |  |  |  | 1.5324
5 |  | 1BHK | 375.3138 |  | 0 | 570 | N |  |  | 29.0775 | 1.5187
6 |  | 1BHK | 375.3138 |  | 0 | 570 | N |  |  |  | 1.5187
Building No. 2
Type A6
Wing C
Ground floor is for Parking, Commercial, & Residential
21 |  | Shop | 106.6712 |  | 0 | 160.0069 | N | Ground floor
22 |  | Shop | 75.2404 |  | 0 | 112.8605 | N
23 |  | Shop | 96.2302 |  | 0 | 144.3452 | N
24 |  | Shop | 96.2302 |  | 0 | 144.3452 | N
25 |  | Shop | 96.9836 |  | 0 | 145.4755 | N
26 |  | Shop | 93.7544 |  | 0 | 140.6317 | N
27 |  | Shop | 70.6118 |  | 0 | 105.9178 | N
1 |  | 1RK | 235.5163 |  | 0 | 353.2745 | N
1st to 4th floor
1 |  | 1BHK | 381.234 |  | 0 | 588 | N | 1st to 4th floor |  |  | 1.5424
2 |  | 1BHK | 381.0187 |  | 0 | 588 | N |  |  |  | 1.5432
3 |  | 1BHK | 387.1003 |  | 0 | 576 | N |  |  |  | 1.488
4 |  | 1BHK | 387.1003 |  | 0 | 576 | N |  |  |  | 1.488
5th floor
1 |  | 1BHK | 381.234 |  | 0 | 588 | N | 5th floor |  |  | 1.5424
2 |  | 1BHK | 381.0187 |  | 0 | 588 | N |  |  |  | 1.5432
3 |  | 1BHK | 387.1003 |  | 0 | 576 | N |  |  |  | 1.488
4 |  | 1BHK | 387.1003 |  | 0 | 576 | N |  |  |  | 1.488
Building No. 4
Type A10
Wing A
Ground floor is for Parking &Residential
1 | 1 | 1BHK | 328.0329 |  | 0 | 475.6477 | N | Ground floor
2 | 2 | 1BHK | 328.0329 |  | 0 | 475.6477 | N
1st to 4th floor
1 | 1 | 1BHK | 328.0329 |  | 0 | 475.6477 | N | 1st to 4th floor
2 | 2 | 1BHK | 328.0329 |  | 0 | 475.6477 | N
3 | 3 | 1BHK | 328.0329 |  | 0 | 475.6477 | N
4 | 4 | 1BHK | 328.0329 |  | 0 | 475.6477 | N
Remarks: 1. Building No.2 (A Wing) - Construction work is same as last visit dtd. 14/05/2025. Building No. 2 (B & C Wing) - Lift, Meter & Finishing work is pending. (Very Slow Speed) Building No. 4 - Work not yet started. 2. We considered building No.2 flat Saleable area as per builder area sheet. Shop & building no.4 saleable as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered rate as per Market Inquiry. 5. Car parking is subjected to authentic documentation. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. The Building No 2 consist of Type A4 (Wing A), Type A5 (Wing B), Type A6 (Wing C), Type A7 (Wing D) & Type A8 (Wing E) out of which we received approved plan of Type A4 (Wing A), Type A5 (Wing B) & Type A6 (Wing C). 8. The Building No 4 consist of Type A10 (Wing A), Type A10a (Wing B) & Type A10 (Wing C) out of which we received the approved plan of Type A10 (Wing A). 9. The Building No 4 is not registered on RERA & the builder's profile is not provided. 10. Please provide revised approved floor plan of Building No. 2 (Wing A) & Building No.4 (Wing A). 11. The construction stage is given as per the proposed structure of floor. 12. We have updated revised C.C & approved floor plan of Building No. 2 (Wing B & C). 13. The project has received first CC on 16/02/2018, But construction work is not yet completed. 14. On site we met Mr. Arvind Yadav 9890546090 . | [10 empty] | Construction work is in process at the time of Visit. (Slow Speed)
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Savera Complex
Google Map :
BLDG No. 2 Wing B
BLDG No. 2 Wing C
BLDG No. 2 Wing A
A
C
Wing A
Wing A
Wing B
Wing C

## 2A%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 50 | Recommended |  |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 2.5 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 5 | 5
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 70 | 80

## 2B%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 60 | Progress |  |  | 10 | 40 | 9 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 9 | 0 | 0 | 0 | 0
| 5 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 9 | 9
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 59 | 69

## 2C%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 4 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 40 | Recommended |  |  | 30 | 30 | 15 | 4 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 2 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 4 | 4
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 69 | 79

## 4A%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 0 | 20
| 5 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 0 | 20

## Note
2021-01-06 | Pratiksha

## Valuation
2021-01-06 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing |  |  |  |  | #DIV/0!
| Proptiger |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| 99 Acres |  |  |  |  | #DIV/0!
| 99 Acres |  |  |  |  | #DIV/0!
| Average |  |  |  |  | #DIV/0!
| Valuation Adopted |  |  |  |  | 32000

## Wing A
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.7 | 10.175 | CB |  |  | 0 |  |  | 0
|  | 1.4 | 1.2 | 1.68 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.15 | 2.1 | 4.515 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 1.6 | 1.92 | DB |  |  | 0 |  |  | 0
| toilet2 | 1 | 1.2 | 1.2 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 209.7904 | 19.49 |  |  | 0 | 0 |  | 0 | 0

## Sheet3
Axis Sanpada
Axis Goregaon
Axis Kalina
Middle Class
Upper Class
Developing
Developed
Residential
Commercial
Residential & Commercial