## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-09
Name of the builder group |  |  |  | M/s.Runwal Residency Private Limited
Name of the builder company |  |  |  | M/s.Runwal Residency Private Limited
Name of the Project |  |  |  | Runwal Gardens Phase III
Contect Details ( Name & Contect No.) |  |  |  | 2261162000
Name / No of the Building |  |  |  | Building No.24 to 30
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Building No. 24 to 26 = P51700026228 Building No. 27 & 28 = P51700026927 Building No. 29 & 30 = P51700028344
Project location details |  | Survey 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/9, 4/10, 4/11, 5/1, 5/2, 5/3, 5/4, 5/5, 5/6, 6/1, 6/2, 6/3, 7/1, 7/2A, 7/2B, 7/2C, 7/3A, 7/3B, 8/1, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7, 8/8, 8/9, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 10, 11, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10, 12/11, 12/12, 12/13, 12/14, 13, 14/1, 14/2A, 14/2B, 14/3, 14/4, 14/5, 15, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 17/10, 17/11, 18, 19, 22, 23/1, 23/2, 23/3, 23/10, 37/1, 37/2B, 37/2C, 37/2D, 37/3, 37/4, 37/21, 38/1, 38/2, 39/1, 39/2, 39/3, 40, 41/1A, 41/1B, 41/2, 41/3, 41/4, 44/1, 44/4,44/5A, 44/5B, 44/6A, 44/6B, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 44/13, 44/14, 44/15, 44/16, 44/17, 44/18, 44/19, 49, 50/1, 50/2, 50/3 at Village Gharivali and bearing S. Nos. 44/1, 44/2, 44/3, 44/4, 44/5, 44/6, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/4, 45/5A, 45/5B, 45/6, 46/1, 46/2A, 46/2B, 46/3, 47, 49, 50, 51(pt), 52/1, 52/2, 53/1A, 53/1B, 53/2A, 53/2B, 53/3A, 53/3B, 94(pt), at Village Usarghar Tal. Kalyan, District-Thane. 421201
Survey No |  | Survey 4/1, 4/2, 4/3, 4/4, 4/5, 4/6, 4/9, 4/10, 4/11, 5/1, 5/2, 5/3, 5/4, 5/5, 5/6, 6/1, 6/2, 6/3, 7/1, 7/2A, 7/2B, 7/2C, 7/3A, 7/3B, 8/1, 8/2, 8/3, 8/4, 8/5, 8/6, 8/7, 8/8, 8/9, 9/1, 9/2, 9/3, 9/4, 9/5, 9/6, 9/7, 9/8, 10, 11, 12/1, 12/2, 12/3, 12/4, 12/5, 12/6, 12/7, 12/8, 12/9, 12/10, 12/11, 12/12, 12/13, 12/14, 13, 14/1, 14/2A, 14/2B, 14/3, 14/4, 14/5, 15, 17/1, 17/2, 17/3, 17/4, 17/5, 17/6, 17/7, 17/8, 17/9, 17/10, 17/11, 18, 19, 22, 23/1, 23/2, 23/3, 23/10, 37/1, 37/2B, 37/2C, 37/2D, 37/3, 37/4, 37/21, 38/1, 38/2, 39/1, 39/2, 39/3, 40, 41/1A, 41/1B, 41/2, 41/3, 41/4, 44/1, 44/4,44/5A, 44/5B, 44/6A, 44/6B, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 44/13, 44/14, 44/15, 44/16, 44/17, 44/18, 44/19, 49, 50/1, 50/2, 50/3 at Village Gharivali and bearing S. Nos. 44/1, 44/2, 44/3, 44/4, 44/5, 44/6, 44/7, 44/8, 44/9, 44/10, 44/11, 44/12, 45/1, 45/2, 45/3, 45/4, 45/5A, 45/5B, 45/6, 46/1, 46/2A, 46/2B, 46/3, 47, 49, 50, 51(pt), 52/1, 52/2, 53/1A, 53/1B, 53/2A, 53/2B, 53/3A, 53/3B, 94(pt), at Village Usarghar Tal. Kalyan, District-Thane.
Road |  | Kalyan - Shilphata Road |  | Locality/Village |  | Sagoan
City |  | Nilaje |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421201
Near by Landmark |  | Premiere colony ground |  | Distance from city centre: |  | 4.1Km from Nilaje Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | Building U/C
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.1835418,73.0737084
Location Link |  | https://goo.gl/maps/R9ZfMLvFvpyJyZkL7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 533750
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 533750
Total number of Buildings |  |  |  | 07 Buildings
Approval Detail : Plan approval
Layout Approval No |  | SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.XV/178/2020 |  |  | Dated | 2020-10-14
Approved Floor plan No. (Building No.24 to 28) |  | SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.XV/178/2020 |  |  | Dated | 2020-10-14
Approved Floor plan No. (Building No.29 & 30) |  | SROT/Growth Center/2401/BP/ITP-Usarghar-Gharivali-Sagaon-01/Site-A/Vol.XXIII/171/2021 |  |  | Dated | 2021-02-11
Commencement Certificate No. |  | SROT/Growth Center/2401/BP/ ITPUsarghar-Gharivali-01/Amended CC Phase 8 B.No. 43,44 & 45/Vol46/527/2024 |  |  | Dated | 2024-05-14
Valid Up to: Building No.24 to 30 = Stilt + 1st to 32nd Floor
O. Certificate No.: |  | SROT/Growth Centre/2401/BP/ITP-Usarghar-Gharivali-01/566/2025 Approved upto : Phase 3 = Building No. 24, 25 & 26 = Gr/St + 1st to 32nd Floor |  | Date of approval: | Dated | 2025-05-27
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 79288.94
Approved no of units |  |  | Flats - 2285
Approved no of Floors |  |  | Building No.24 to 30 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor
Proposed no of Floors |  |  | Building No.24 to 30 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor
Expected Completion |  |  | As per RERA - Phase 3 Bldg no 24-26 = Completed Phase 3 Bldg No 27-28 = 30/12/2025 Phase 3 Bldg No 29-30 = 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Building No.24, 25 & 26 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 100% |  | 100% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 32 | 100% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 32 | 100% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 32 | 100% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 32 | 100% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 32 | 100% |  |  |  |  | Plinth completed | 32 | 30%
Progress % |  | 100% |  | Disbursement % |  | 100% |  | Plinth completed | 32 | 30%
Construction details: |  | Building No.25 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 89.84% |  | 94.69% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 32 | 100% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 30 | 93.75% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 30 | 93.75% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 5 | 15.62% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Construction details: |  | Building No.26 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 31 Slab, Brickwork upto 30 Floor, Internal Plaster upto 21 Floor, External Plaster upto 19.5 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 31 Slab, Brickwork upto 30 Floor, Internal Plaster upto 21 Floor, External Plaster upto 19.5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 65.62% |  | 84.2% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 31 | 93.94% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 30 | 93.75% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 21 | 65.62% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 19.5 | 60.94% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Construction details: |  | Building No.27 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 27 Floor, Painting upto 23 Floor, Finishing upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 27 Floor, Painting upto 23 Floor, Finishing upto 6 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 87.97% |  | 94.22% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 32 | 100% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 27 | 84.38% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 23 | 71.88% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 6 | 18.75% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Construction details: |  | Building No.28 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 27 Floor, External Plaster upto 25 Floor, Flooring upto 14 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 27 Floor, External Plaster upto 25 Floor, Flooring upto 14 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 76.02% |  | 90.31% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 27 | 84.38% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 78.12% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 14 | 43.75% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Construction details: |  | Part II - Flat No.6 to 8 Building No.28 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 13.64% |  | 47.73% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 3 | 9.091% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Average of Part I & Part II Building No.28 |  | Progress % |  | 44.83% | Disbursement % |  | 69.02% | All work Completed. OC Received.
Construction details: |  | Building No.29 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 30 Floor, Flooring upto 20 Floor, Painting upto 10 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 30 Floor, Flooring upto 20 Floor, Painting upto 10 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 82.19% |  | 92.81% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 30 | 93.75% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 20 | 62.5% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 10 | 31.25% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Construction details: |  | Building No. 30 = Stilt + 1st to 23rd Floors + Fire Check Floor + 24th to 32nd Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 26 Floor, Painting upto 23 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 32
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 26 Floor, Painting upto 23 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8
Excavation |  | 32 | 100% | 86.72% |  | 94.06% |  | Excavation in process | 16
Plinth |  | 32 | 100% |  |  |  |  | Excavation Completed | 32 | 2%
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 8 | 4%
Brickwork | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Footing Completed | 16 | 8%
Internal Plaster | Brickwork & Internal Plaster | 32 | 100% |  |  |  |  | Basement 1 | 0 | 15%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 32 | 100% |  |  |  |  | Basement 2 | 0 | 4%
Flooring & Fitting | Flooring & Fitting | 26 | 81.25% |  |  |  |  | Basement 3 | 0 | 8%
Painting & Wooden |  | 23 | 71.88% |  |  |  |  | Basement 4 | 0 | 15%
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 24 | 20%
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 32 | 30%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA | [7 empty] | rATE 8200 BHARGAV VERBAL 24/03/2025
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [7 empty] | rATE 7900 BHARGAV VERBAL 27/12/2024
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8200 |  |  | Rate has changed from 6700/- to 7400/- as per cosheeet(8flats have been matched)
Floor rise rate Per Sq. Ft. (Any Floor) |  |  |  |  | 1BHK = 200/- & 2BHK = 250/- 3 BHK = 300/-
Other Charges |  |  |  |  | 500000/- |  |  | Other Charges has also Changed From 40,000/- to 2 & 3BHK = 4,50,000/- & 1BHK = 100000 on 20/06/2022
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA |  |  | Other Charges has also Changed From 40,000/- to 4,50,000/- &
Advance Maintenance Charges |  |  |  |  | NA |  |  | Parking From 3,00,000/- to 3,50,000/-
Recommended rate of Parking |  |  |  |  | 4,00,000/- |  |  | Parking From 3,50,000/- to 4,00,000/-
Distressed valuation of the Property |  |  |  |  | 6560 |  |  | All these Above Changes are done by Ajinkya Sir (on 09/03/2022).
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  |  | 1BHK Other Charges 40K | Rushikesh | 2023-12-28
Building No.24 |  | 346 |  | 176387.7305 |  | 264581.5957
Building No.25 |  | 314 |  | 143347.0943 |  | 215020.6414
Building No.26 |  | 311 |  | 142198.4678 |  | 213297.7018
Building No.27 |  | 311 |  | 142198.4678 |  | 213297.7018
Building No.28 |  | 314 |  | 143347.0943 |  | 215020.6414
Building No.29 |  | 376 |  | 150857.6753 |  | 226286.5129
Building No.30 |  | 313 |  | 144271.1837 |  | 216406.7755
Total |  | 2285 |  | 1042607.7137 |  | 1563911.5705
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Building No.24
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 422.2717 | 0 | 633.4076 | 1st Floor
2 |  | 2BHK | 557.2523 | 0 | 835.8784
3 |  | 2BHK | 651.222 | 0 | 976.833
4 |  | Double Height Entrance Lobby Below
5 |  | 1BHK | 461.668 | 0 | 692.5019
6 |  | 1BHK | 420.0113 | 0 | 630.0169
7 |  | 2BHK | 526.5749 | 0 | 789.8623
8 |  | 2BHK | 526.5749 | 0 | 789.8623
9 |  | 2BHK | 495.6822 | 0 | 743.5233
10 |  | 3BHK | 689.0036 | 0 | 1033.5055
11 |  | 1BHK | 422.2717 | 0 | 633.4076
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 422.2717 | 0 | 633.4076 | 2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2 |  | 2BHK | 557.2523 | 0 | 835.8784
3 |  | 2BHK | 651.222 | 0 | 976.833
4 |  | 1BHK | 461.668 | 0 | 692.5019
5 |  | 1BHK | 461.668 | 0 | 692.5019
6 |  | 1BHK | 420.0113 | 0 | 630.0169 |  |  | 6277.6092 | 6077.6092
7 |  | 2BHK | 526.5749 | 0 | 789.8623
8 |  | 2BHK | 526.5749 | 0 | 789.8623
9 |  | 2BHK | 495.6822 | 0 | 743.5233
10 |  | 3BHK | 689.0036 | 0 | 1033.5055
11 |  | 1BHK | 422.2717 | 0 | 633.4076
8th Floor (Part Refuge Area)
1 |  | 1BHK | 422.2717 | 0 | 633.4076 | 8th Floor (Part Refuge Area)
2 |  | 2BHK | 557.2523 | 0 | 835.8784
3 |  | 2BHK | 651.222 | 0 | 976.833
4 |  | 1BHK | 461.668 | 0 | 692.5019
5 |  | 1BHK | 461.668 | 0 | 692.5019
6 |  | 1BHK | 420.0113 | 0 | 630.0169
7 |  | 2BHK | 526.5749 | 0 | 789.8623
8 |  | 2BHK | 526.5749 | 0 | 789.8623
9 |  | 2BHK | 495.6822 | 0 | 743.5233
10 |  | Refuge Area
11 |  | 1BHK | 422.2717 | 0 | 633.4076
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 422.2717 | 0 | 633.4076 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 2BHK | 557.2523 | 0 | 835.8784
3 |  | 2BHK | 651.222 | 0 | 976.833
4 |  | 1BHK | 461.668 | 0 | 692.5019
5 |  | 1BHK | 461.668 | 0 | 692.5019
6 |  | 1BHK | 420.0113 | 0 | 630.0169
7 |  | 2BHK | 526.5749 | 0 | 789.8623
8 |  | 2BHK | 526.5749 | 0 | 789.8623
9 |  | 2BHK | 495.6822 | 0 | 743.5233
10 |  | Refuge Area
11 |  | 1BHK | 422.2717 | 0 | 633.4076
29th Floor (Part Refuge Area)
1 |  | 1BHK | 422.2717 | 0 | 633.4076 | 29th Floor (Part Refuge Area)
2 |  | 2BHK | 557.2523 | 0 | 835.8784
3 |  | 2BHK | 651.222 | 0 | 976.833
4 |  | 1BHK | 461.668 | 0 | 692.5019
5 |  | 1BHK | 461.668 | 0 | 692.5019
6 |  | 1BHK | 420.0113 | 0 | 630.0169
7 |  | 2BHK | 526.5749 | 0 | 789.8623
8 |  | 2BHK | 526.5749 | 0 | 789.8623
9 |  | 2BHK | 495.6822 | 0 | 743.5233
10 |  | Refuge Area
11 |  | 1BHK | 422.2717 | 0 | 633.4076
Building No.25
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 1st Floor
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | Double Height Entrance Lobby Below
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor |  | 7022.9294 | 6822.9294
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
8th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
29th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 29th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Building No.26
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 1st Floor
2 |  | Double Height Entrance Lobby Below
3
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | Double Height Entrance Lobby Below
7
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
8th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
29th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 29th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Building No.27
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 1st Floor
2 |  | Double Height Entrance Lobby Below
3
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | Double Height Entrance Lobby Below
7
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2 |  | 1BHK | 333.4687 | 0 | 500.2031 |  |  | 6212.4767 | 6012.4767
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
8th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
29th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 29th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Building No.28
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 1st Floor
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | Double Height Entrance Lobby Below
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | 2BHK | 558.221 | 0 | 837.3316
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
8th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
29th Floor (Part Refuge Area)
1 |  | 1BHK | 450.904 | 0 | 676.3559 | 29th Floor (Part Refuge Area)
2 |  | 1BHK | 333.4687 | 0 | 500.2031
3 |  | 1BHK | 333.4687 | 0 | 500.2031
4 |  | 2BHK | 483.196 | 0 | 724.7939
5 |  | Refuge Area
6 |  | 1BHK | 461.668 | 0 | 692.5019
7 |  | 1BHK | 461.668 | 0 | 692.5019
8 |  | 2BHK | 528.1895 | 0 | 792.2842
9 |  | 2BHK | 528.1895 | 0 | 792.2842
10 |  | 1BHK | 441.6469 | 0 | 662.4704
Building No.29
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 333.0382 | 0 | 499.5572 | 1st Floor
2 |  | 1BHK | 333.0382 | 0 | 499.5572
3 |  | Double Height Entrance Lobby
4 |  | Double Height Entrance Lobby
5 |  | 1BHK | 333.0382 | 0 | 499.5572
6 |  | 1BHK | 439.7094 | 0 | 659.5641
7 |  | 2BHK | 558.0058 | 0 | 837.0086
8 |  | 1BHK | 336.0521 | 0 | 504.0781
9 |  | 1BHK | 336.0521 | 0 | 504.0781
10 |  | 2BHK | 528.943 | 0 | 793.4144
11 |  | 2BHK | 528.943 | 0 | 793.4144
12 |  | Double Height Entrance Lobby
2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 333.0382 | 0 | 499.5572 | 2nd to 7th, 9th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2 |  | 1BHK | 333.0382 | 0 | 499.5572
3 |  | 1BHK | 333.8993 | 0 | 500.8489
4 |  | 1BHK | 333.8993 | 0 | 500.8489
5 |  | 1BHK | 333.0382 | 0 | 499.5572
6 |  | 1BHK | 439.7094 | 0 | 659.5641
7 |  | 2BHK | 558.0058 | 0 | 837.0086
8 |  | 1BHK | 336.0521 | 0 | 504.0781
9 |  | 1BHK | 336.0521 | 0 | 504.0781
10 |  | 2BHK | 528.943 | 0 | 793.4144
11 |  | 2BHK | 528.943 | 0 | 793.4144
12 |  | 1BHK | 441.5393 | 0 | 662.3089
8th Floor (Part Refuge Area)
1 |  | 1BHK | 333.0382 | 0 | 499.5572 | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 333.0382 | 0 | 499.5572
3 |  | 1BHK | 333.8993 | 0 | 500.8489
4 |  | 1BHK | 333.8993 | 0 | 500.8489
5 |  | 1BHK | 333.0382 | 0 | 499.5572
6 |  | 1BHK | 439.7094 | 0 | 659.5641
7 |  | Refuge Area
8 |  | 1BHK | 336.0521 | 0 | 504.0781
9 |  | 1BHK | 336.0521 | 0 | 504.0781
10 |  | 2BHK | 528.943 | 0 | 793.4144
11 |  | 2BHK | 528.943 | 0 | 793.4144
12 |  | 1BHK | 441.5393 | 0 | 662.3089
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 333.0382 | 0 | 499.5572 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 1BHK | 333.0382 | 0 | 499.5572
3 |  | 1BHK | 333.8993 | 0 | 500.8489
4 |  | 1BHK | 333.8993 | 0 | 500.8489
5 |  | 1BHK | 333.0382 | 0 | 499.5572
6 |  | 1BHK | 439.7094 | 0 | 659.5641
7 |  | Refuge Area
8 |  | 1BHK | 336.0521 | 0 | 504.0781
9 |  | 1BHK | 336.0521 | 0 | 504.0781
10 |  | 2BHK | 528.943 | 0 | 793.4144
11 |  | 2BHK | 528.943 | 0 | 793.4144
12 |  | 1BHK | 441.5393 | 0 | 662.3089
29th Floor (Part Refuge Area)
1 |  | 1BHK | 333.0382 | 0 | 499.5572 | 29th Floor (Part Refuge Area)
2 |  | 1BHK | 333.0382 | 0 | 499.5572
3 |  | 1BHK | 333.8993 | 0 | 500.8489
4 |  | 1BHK | 333.8993 | 0 | 500.8489
5 |  | 1BHK | 333.0382 | 0 | 499.5572
6 |  | 1BHK | 439.7094 | 0 | 659.5641
7 |  | Refuge Area
8 |  | 1BHK | 336.0521 | 0 | 504.0781
9 |  | 1BHK | 336.0521 | 0 | 504.0781
10 |  | 2BHK | 528.943 | 0 | 793.4144
11 |  | 2BHK | 528.943 | 0 | 793.4144
12 |  | 1BHK | 441.5393 | 0 | 662.3089
Building No.30
Ground Floor for Parking
1st Floor
1 |  | 1BHK | 336.0521 | 0 | 504.0781 | 1st Floor
2 |  | 1BHK | 333.8993 | 0 | 500.8489
3 |  | 1BHK | 333.7916 | 0 | 500.6875
4 |  | Double Height Entrance Lobby
5 |  | Double Height Entrance Lobby
6 |  | 2BHK | 558.221 | 0 | 837.3316
7 |  | 1BHK | 333.0382 | 0 | 499.5572
8 |  | 3BHK | 790.4005 | 0 | 1185.6008
9 |  | 2BHK | 646.8088 | 0 | 970.2131
10 |  | 1BHK | 336.0521 | 0 | 504.0781
2nd to 7th, 9th to 13th, 15th to 17th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
1 |  | 1BHK | 336.0521 | 0 | 504.0781 | 2nd to 7th, 9th to 13th, 15th to 17th, 20th to 23rd, 25th to 28th, 30th to 32nd Floor
2 |  | 1BHK | 333.8993 | 0 | 500.8489
3 |  | 1BHK | 333.7916 | 0 | 500.6875
4 |  | 2BHK | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 462.852 | 0 | 694.278
6 |  | 2BHK | 558.221 | 0 | 837.3316 |  |  | 6420.8138 | 6170.8138
7 |  | 1BHK | 333.0382 | 0 | 499.5572
8 |  | 3BHK | 790.4005 | 0 | 1185.6008 |  |  | 7152.4919 | 6952.4919
9 |  | 2BHK | 646.8088 | 0 | 970.2131
10 |  | 1BHK | 336.0521 | 0 | 504.0781
18th Floor
1 |  | 1BHK | 336.0521 | 0 | 504.0781 | 18th Floor
2 |  | 1BHK | 333.8993 | 0 | 500.8489
3 |  | 1BHK | 333.7916 | 0 | 500.6875
4 |  | 2BHK | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 462.852 | 0 | 694.278
6 |  | 2BHK | 558.221 | 0 | 837.3316
7 |  | 1BHK | 333.0382 | 0 | 499.5572
8 |  | 3BHK | 790.4005 | 0 | 1244 |  |  | SA changes to 1244 by Smith for case 1808 Building No. 30 on 24/03/2025
9 |  | 2BHK | 646.8088 | 0 | 970.2131
10 |  | 1BHK | 336.0521 | 0 | 504.0781
8th Floor
1 |  | 1BHK | 336.0521 | 0 | 504.0781 | 8th Floor
2 |  | 1BHK | 333.8993 | 0 | 500.8489
3 |  | 1BHK | 333.7916 | 0 | 500.6875
4 |  | 2BHK | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 462.852 | 0 | 694.278
6 |  | Refuge Area
7 |  | 1BHK | 333.0382 | 0 | 499.5572
8 |  | 3BHK | 790.4005 | 0 | 1185.6008
9 |  | 2BHK | 646.8088 | 0 | 970.2131
10 |  | 1BHK | 336.0521 | 0 | 504.0781
Fire Check Floor Between 23rd & 24th Floor
14th, 19th & 24th Floor (Part Refuge Area)
1 |  | 1BHK | 336.0521 | 0 | 504.0781 | 14th, 19th & 24th Floor (Part Refuge Area)
2 |  | 1BHK | 333.8993 | 0 | 500.8489
3 |  | 1BHK | 333.7916 | 0 | 500.6875
4 |  | 2BHK | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 462.852 | 0 | 694.278
6 |  | Refuge Area
7 |  | 1BHK | 333.0382 | 0 | 499.5572
8 |  | 3BHK | 790.4005 | 0 | 1185.6008
9 |  | 2BHK | 646.8088 | 0 | 970.2131
10 |  | 1BHK | 336.0521 | 0 | 504.0781
29th Floor (Part Refuge Area)
1 |  | 1BHK | 336.0521 | 0 | 504.0781 | 29th Floor (Part Refuge Area)
2 |  | 1BHK | 333.8993 | 0 | 500.8489
3 |  | 1BHK | 333.7916 | 0 | 500.6875
4 |  | 2BHK | 494.4982 | 0 | 741.7472
5 |  | 1BHK | 462.852 | 0 | 694.278
6 |  | Refuge Area
7 |  | 1BHK | 333.0382 | 0 | 499.5572
8 |  | 3BHK | 790.4005 | 0 | 1185.6008
9 |  | 2BHK | 646.8088 | 0 | 970.2131
10 |  | 1BHK | 336.0521 | 0 | 504.0781
Remarks:
1. Building No. 24, 25 & 26 = All work Completed. OC Received. Building No. 27, 28, 29 & 30 = Construction work was in process at the time of visit. Internal Visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Constrution details are collected from Miss. Anuja. 8. We update all towers revised Plans (30/04/2021) 9. We update revised approved plans of Tower 29 & 30 (on 29/06/2021). 10.We update revised CC of Tower 24 & 30 taken from RERA site. (on 07/10/2024). 11. Recommended Rates of the Property have been revised on 27/12/2024 and 24/03/2025. 12. We have updated OC for Building No. 24, 25 & 26 (On 31/05/2025)
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Gangaram Lambore |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Runwal Gardens Phase III
Google Map :
Formulas:
Sagoan = [Sagoan, row above]
Building No.30
24
25
26
27
28
29
30

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Runwal Gardens Phase 3 | 1BHK | 344 | 550.4 | 5813.9535 | 3200000
housing. | Runwal Gardens Phase 3 | 1BHK | 443 | 708.8 | 5925.5079 | 4200000
housing. | Runwal Gardens Phase 3 | 1.5BHK | 492 | 787.2 | 6478.6585 | 5100000
housing. | Runwal Gardens Phase 3 | 1.5BHK | 528 | 844.8 | 6273.6742 | 5300000
housing. | Runwal Gardens Phase 3 | 2BHK | 540 | 864 | 6597.2222 | 5700000
housing. | Runwal Gardens Phase 3 | 2BHK | 628 | 1004.8 | 6170.3822 | 6200000
99 Acres | Runwal Gardens Phase 3 | 3BHK | 676 | 1081.6 | 6286.9822 | 6800000
Average |  |  |  |  | 6220.9115
Valuation Adopted |  |  |  |  | 6200

## Note
15/12/2020. | Pratiksha
27/07/2021. | Asmita | abhishek | demand rate for 6400

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.2 | 3.05 | 12.81 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB | 1.325 | 2.4 | 3.18 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.775 | 2.15 | 5.9662 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.9 | 3.1 | 8.99 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.1 | 3.18 | 9.858 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 2.62 | 3.38 | 8.8556 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.35 | 2.1 | 2.835 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.35 | 2.1 | 2.835 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.43 | 1.05 | 1.5015 |  |  |  | 0 |  |  | 0
| passage2 | 1 | 1.35 | 1.35 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 592.0345 | 55.0014 |  |  | 34.2295 | 3.18 |  | 0 | 0
|  |  | 626.2641 | 58.1814