## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 10/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 09/08/2025.
Name of the builder group |  |  |  | M/s. Chalama Infraproperties Private Limited
Name of the builder company |  |  |  | M/s. Chalama Infraproperties Private Limited
Name of the Project |  |  |  | Dosti Planet North ­ Sector 3
Contact Details ( Name & Contact No.) |  |  |  | Mr. Sandeep Jha 8097547099
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | Mr. Pritam 7208854822
Name / No of the Building |  |  |  | Tower 2 - Amber & Tower 3 - Sapphire
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P51700034985
Project location details |  | Dosti Planet North ­ Sector 3, Survey No.181/2G, 181/2H, 181/2D, 156/3, near Dosti Planet North Emerald, Mumbai - Pune Highway, , Shil, Mumbra, Thane, Thane - 400612.
Survey No |  | 181/2G, 181/2H, 181/2D, 156/3
Locality |  | NA
Road |  | Mumbai - Pune Highway |  | Village |  | Shil
City |  | Mumbra |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400612
Nearby Landmark |  | Dosti Planet North Emerald |  | Distance from city centre: |  | 5KM from Mumbra Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Under Construction
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Mmrda Apartment 2
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.153776,73.03756
Location Link |  | https://goo.gl/maps/DL1wfuMoWv9RHK3T8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 20770
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.3766
Total FSI availaible for the project |  |  |  | 3.4766
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 72208.61
Total number of Buildings |  |  |  | 2 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation
Layout Approval No |  | S11/0226/20/TMC/TD-DP/TPS/3860/22 |  |  | Dated | 11/01/2022.
Approved Floor plan No. |  | S11/0226/20/TMC/TD-DP/TPS/3860/22 |  |  | Dated | 11/01/2022.
Commencement-CC No Valid Up to: |  | S11/0226/20/TMC/TDD/3983/22 |  |  | Dated | 23/02/2022.
Tower 2 = G + 1st to 29th Floor Tower 3 = B + G + 1st to 34th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 72208.61
Approved no of units |  |  | Sale Flats - 631, Mhada Flats -106
Approved no of Floors |  |  | Tower 2 = B + G + 1st to 29th Floor Tower 3 = B + G + 1st to 34th Floor
Proposed no of Floors |  |  | Tower 2 (Amber) = 2B + G + 1st to 34th Floor
Tower 3 (Sapphire) = 2B + G + 1st to 34th Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Tower 2 (Amber) = 2B + G + 1st to 34th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 25.5 Floor, External Plaster upto 23.8 Floor, Flooring upto 12 Floor Completed | , Internal Plaster upto 25.5 Floor, External Plaster upto 23.8 Floor, Flooring upto 12 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 34 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 25.5 Floor, External Plaster upto 23.8 Floor, Flooring upto 12 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.5
Excavation |  | 34 | 100% | 73.65% |  | 89.01% |  | Excavation in process | 17
Plinth |  | 34 | 100% |  |  |  |  | Excavation Completed | 34
RCC (Including podiums) |  | 35 | 100% |  |  |  |  | Footing in Process | 8.5
Brickwork | Brickwork & Internal Plaster | 34 | 100% |  |  |  |  | Footing Completed | 17
Internal Plaster | Brickwork & Internal Plaster | 25.5 | 75% |  |  |  |  | Basement 1 | 25.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23.8 | 70% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 35.29% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 34
Construction details: |  | Tower 3 (Sapphire) = 2B + G + 1st to 34th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 25.5 Floor, External Plaster upto 23.8 Floor, Flooring upto 5 Floor Completed | , Internal Plaster upto 25.5 Floor, External Plaster upto 23.8 Floor, Flooring upto 5 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 34 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 25.5 Floor, External Plaster upto 23.8 Floor, Flooring upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 8.5
Excavation |  | 34 | 100% | 71.6% |  | 87.99% |  | Excavation in process | 17
Plinth |  | 34 | 100% |  |  |  |  | Excavation Completed | 34
RCC (Including podiums) |  | 35 | 100% |  |  |  |  | Footing in Process | 8.5
Brickwork | Brickwork & Internal Plaster | 34 | 100% |  |  |  |  | Footing Completed | 17
Internal Plaster | Brickwork & Internal Plaster | 25.5 | 75% |  |  |  |  | Basement 1 | 25.5
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23.8 | 70% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 14.71% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 34
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 8300 |  |  | 7500 to 8300 & OC by sanket on 28/09/2023 on very higher side
Floor Rise Rate
Development Charges |  |  |  |  | 250000 |  |  | don’t increase the rate again
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 6640
Residential Area Details : Sale Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 2 - Amber |  | 402 |  | 255754.0049 |  | 383631.0073
Tower 3 - Sapphire |  | 229 |  | 115591.3668 |  | 173387.0502 |  | 228
Total |  | 631 |  | 371345.3717 |  | 557018.0575
Residential Area Details : Mhada Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower 3 - Sapphire |  | 106 |  | 45068.868 |  | 67603.302 |  | 335
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat (Mhada/ Sale ) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Tower 2 - Amber
Basement Floor For Parking
Ground Floor For Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th Floor
1 | Sale | 3BHK | 819.1458 | 0 | 1228.7187 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th Floor
2 | Sale | 2BHK | 682.7713 | 0 | 1024.1569
3 | Sale | 2BHK | 682.7713 | 0 | 1024.1569
4 | Sale | 3BHK | 819.1458 | 0 | 1228.7187 |  |  | 7337.7456
5 | Sale | 2BHK | 590.0857 | 0 | 885.1286
6 | Sale | 2BHK | 585.4249 | 0 | 878.1373
7 | Sale | 2BHK | 611.5567 | 0 | 917.335
8 | Sale | 2BHK | 517.7915 | 0 | 776.6872
9 | Sale | 2BHK | 517.7915 | 0 | 776.6872
10 | Sale | 2BHK | 611.5567 | 0 | 917.335
11 | Sale | 2BHK | 585.4249 | 0 | 878.1373
12 | Sale | 2BHK | 590.0857 | 0 | 885.1286
8th, 13th, 18th, 23rd, 28th, 33rd Floor (Part Refuge Area)
1 | Sale | 3BHK | 819.1458 | 0 | 1228.7187 | 8th, 13th, 18th, 23rd, 28th, 33rd Floor (Part Refuge Area)
2 | Sale | 2BHK | 682.7713 | 0 | 1024.1569 |  |  | 8201.8681
3 | Sale | 2BHK | 682.7713 | 0 | 1024.1569
4 | Sale | 3BHK | 819.1458 | 0 | 1228.7187
5 | Sale | 2BHK | 590.0857 | 0 | 885.1286
6 | Sale | 2BHK | 585.4249 | 0 | 878.1373 | 8th, 13th, 18th, 23rd, 28th, 33rd Floor (Part Refuge Area)
7 | Sale | 2BHK | 611.5567 | 0 | 917.335
8 | Sale | 2BHK | 517.7915 | 0 | 776.6872
9 | - | Refuge Area
10 | Sale | 2BHK | 611.5567 | 0 | 917.335
11 | Sale | 2BHK | 585.4249 | 0 | 878.1373
12 | Sale | 2BHK | 590.0857 | 0 | 885.1286
Tower 3 - Sapphire
Basement Floor For Parking
Ground Floor For Parking
1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th Floor
1 | Mhada | 1BHK | 425.178 | 0 | 637.767 | 1st to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th Floor |  | 8623.8391
2 | Mhada | 1BHK | 425.178 | 0 | 637.767
3 | Mhada | 1BHK | 425.178 | 0 | 637.767
4 | Mhada | 1BHK | 425.178 | 0 | 637.767
5 | Sale | 2BHK | 553.162 | 0 | 829.7429
6 | Sale | 2BHK | 553.162 | 0 | 829.7429
7 | Sale | 1BHK | 437.2337 | 0 | 655.8505
8 | Sale | 1BHK | 437.2337 | 0 | 655.8505
9 | Sale | 2BHK | 553.162 | 0 | 829.7429
10 | Sale | 2BHK | 553.162 | 0 | 829.7429
8th, 13th, 18th, 23rd Floor (Part Refuge Area)
1 | Mhada | 1BHK | 425.178 | 0 | 637.767 | 8th, 13th, 18th, 23rd Floor (Part Refuge Area)
2 | Mhada | 1BHK | 425.178 | 0 | 637.767
3 | Mhada | 1BHK | 425.178 | 0 | 637.767
4 | - | Refuge Area
5 | Sale | 2BHK | 553.162 | 0 | 829.7429
6 | Sale | 2BHK | 553.162 | 0 | 829.7429
7 | Sale | 1BHK | 437.2337 | 0 | 655.8505
8 | Sale | 1BHK | 437.2337 | 0 | 655.8505
9 | Sale | 2BHK | 553.162 | 0 | 829.7429
10 | Sale | 2BHK | 553.162 | 0 | 829.7429
28th Floor
1 | Sale | 1BHK | 425.178 | 0 | 637.767 | 28th Floor |  | 7130.3046 | 7049.4773
2 | Mhada | 1BHK | 425.178 | 0 | 637.767
3 | Mhada | 1BHK | 425.178 | 0 | 637.767
4 | Sale | 1BHK | 425.178 | 0 | 637.767
5 | Sale | 2BHK | 553.162 | 0 | 829.7429
6 | Sale | 2BHK | 553.162 | 0 | 829.7429
7 | Sale | 1BHK | 437.2337 | 0 | 655.8505
8 | Sale | 1BHK | 437.2337 | 0 | 655.8505
9 | Sale | 2BHK | 553.162 | 0 | 829.7429
10 | Sale | 2BHK | 553.162 | 0 | 829.7429
29th to 32nd & 34th Floor
1 | Sale | 1BHK | 425.178 | 0 | 637.767 | 29th to 32nd & 34th Floor
2 | Sale | 1BHK | 425.178 | 0 | 637.767
3 | Sale | 1BHK | 425.178 | 0 | 637.767
4 | Sale | 1BHK | 425.178 | 0 | 637.767
5 | Sale | 2BHK | 553.162 | 0 | 829.7429
6 | Sale | 2BHK | 553.162 | 0 | 829.7429
7 | Sale | 1BHK | 437.2337 | 0 | 655.8505
8 | Sale | 1BHK | 437.2337 | 0 | 655.8505
9 | Sale | 2BHK | 553.162 | 0 | 829.7429
10 | Sale | 2BHK | 553.162 | 0 | 829.7429
33rd Floor (Part Refuge Area)
1 | Sale | 1BHK | 425.178 | 0 | 637.767 | 33rd Floor (Part Refuge Area)
2 | Sale | 1BHK | 425.178 | 0 | 637.767
3 | Sale | 1BHK | 425.178 | 0 | 637.767
4 | - | Refuge Area
5 | Sale | 2BHK | 553.162 | 0 | 829.7429
6 | Sale | 2BHK | 553.162 | 0 | 829.7429
7 | Sale | 1BHK | 437.2337 | 0 | 655.8505
8 | Sale | 1BHK | 437.2337 | 0 | 655.8505
9 | Sale | 2BHK | 553.162 | 0 | 829.7429
10 | Sale | 2BHK | 553.162 | 0 | 829.7429
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Mayuresh Kadam - 7208854815.
* | We have done APF For Tower 2 - Amber and Tower 3 - Sapphire because provided CC is only Approved for Tower 2 and Tower 3.
* | Construction work goes beyond approved no of floors and CC permission of Tower 2, Please provide revised approved plan and CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Gangaram Lambore |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Dosti Planet North ­ Sector 3
Google Map :
Tower 2
Amber
Tower 3
Sapphire

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted