## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | Sai Aastha Developers
Name of the builder company |  |  |  | Sai Aastha Developers
Name of the Project |  |  |  | Enso Sanza
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Shashank 7208864085
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Darshan 8097436793
Name / No of the Building |  |  |  | A, B, C & D Wing
Name / No of the Existing Building |  |  |  | Sai Nath SRA CHS.(LTD.) | [5 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans. | [5 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800013955 |  |  |  | #N/A |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Enso Sanza, Survey No.163 A/2 (Part) & Redevelopment of "Sai Nath SRA CHS.(LTD.)", near Uk Lukecity, Internal Road, Hanuman Nagar, Akurli, Kandivali East, Borivali, Mumbai - 400101. | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 163 A/2 (Part) & Redevelopment of "Sai Nath SRA CHS.(LTD.)" | [7 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Hanuman Nagar | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Akurli |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kandivali East |  | District |  | Mumbai |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Borivali |  | Pin Code |  | 400101 | [6 empty] | Mahad | Daund
Nearby Landmark |  | Uk Lukecity |  | Distance from city centre: |  | 3.80 Km from Kandivali Railway Station | [6 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [8 empty] | Mangaon | Ambegaon
[13 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [8 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [8 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [8 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 18.30 M Wide Road |  |  | Uk Lukecity
West | NA | Other plot |  |  | Slums
North | NA | Other plot |  |  | Building
South | NA | Other plot |  |  | u/c Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.200154,72.865708
Location Link |  | https://goo.gl/maps/UQQ8eUFSZLWZreKP9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3543.72
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 1.5868
Total FSI availaible for the project |  |  |  | 5.5868
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 19798.18
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority
Layout Approval No |  | SRA/ENG/RS/STGOVT/0019/ 20061020/AP/S |  |  | Dated | 2023-02-21
Approved Floor plan No. |  | SRA/ENG/RS/STGOVT/0019/ 20061020/AP/S |  |  | Dated | 2023-02-21
Commencement-CC No |  | SRA/ENG/3167/RS/STGL/AP |  |  | Dated | 2021-05-06
Valid Up to: |  | This C.C is re-endorsed & further extended for part portion marked A to H upto 22nd (pt.) upper floor with O.H.T. & L.M.R as per approved amended plans dated 29/04/2021
Commencement-CC No |  | RS/STGOVT/0019/20061020/AP/S |  |  | Dated | 2024-11-19
Valid Up to: |  | This C.C is further extended upto 18th upper floor for wing A & B in the form of RCC frame only & Brickwork & finishing work for entire wing C & D of sale bldg. as per amended plan dtd. 22/03/2024.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4529.64
Approved no of units |  |  | Flats - 118, Shops - 05
Approved no of Floors |  |  | A Wing = B + G + 1st to 23rd Floor B Wing = B + G + 1st to 20th Floor C Wing = B + G + 1st to 23rd Floor D Wing = B + G + 1st to 23rd Floor
Proposed no of Floors |  |  | A Wing = B + G + 1st to 23rd Floor
B Wing = B + G + 1st to 20th Floor
C Wing = B + G + 1st to 23rd Floor
D Wing = B + G + 1st to 23rd Floor
Expected Completion |  |  | As per RERA - 30/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Club House, Cycling & Jogging Track, Children's Play Area, Indoor Games, Gymnasium, Terrace Garden, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = B + G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 15 Floor Completed | , RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 15 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 21 Slab, Brickwork upto 20 Floor, Internal Plaster upto 16 Floor, External Plaster upto 15 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 63.26% |  | 82.34% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 21 | 87.5% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 20 | 86.96% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 16 | 69.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 65.22% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | B Wing = B + G + 1st to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 17 Floor, External Plaster upto 16 Floor Completed | , Internal Plaster upto 17 Floor, External Plaster upto 16 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 17 Floor, External Plaster upto 16 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 71.88% |  | 88.25% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 17 | 85% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 80% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | C Wing = B + G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 21 Floor, Finishing upto 7 Floor Completed | , Flooring upto 22 Floor, Painting upto 21 Floor, Finishing upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 21 Floor, Finishing upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 90.65% |  | 94.78% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 95.65% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 21 | 91.3% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 30.43% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | D Wing = B + G + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 21 Floor, Painting upto 21 Floor, Finishing upto 5 Floor Completed | , Flooring upto 21 Floor, Painting upto 21 Floor, Finishing upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 21 Floor, Painting upto 21 Floor, Finishing upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 89.78% |  | 94.57% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 21 | 91.3% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 21 | 91.3% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 21.74% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 22500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 35000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 947685
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 900000
Distressed valuation of the Property |  |  |  |  | 18000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing B |  | 5 |  | 1116.9803 |  | 1787.1684
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing B |  | 118 |  | 41699.1978 |  | 64633.7566
Grand Total |  | 123 |  | 42816.1781 |  | 66420.925
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing B
Basement For Puzzle Parking
Ground Floor for Commercial, Meter Room & Parking
1 |  | Shop | 294.9336 | 0 | 471.8938 | Ground Floor for Commercial, Meter Room & Parking
2 |  | Shop | 242.8358 | 0 | 388.5373 | Ground Floor for Commercial, Meter Room & Parking
3 |  | Shop | 197.3041 | 0 | 315.6866 | Ground Floor for Commercial, Meter Room & Parking
4 |  | Shop | 143.1612 | 0 | 229.0579 | Ground Floor for Commercial, Meter Room & Parking
5 |  | Shop | 238.7455 | 0 | 381.9928 | Ground Floor for Commercial, Meter Room & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing B
1st Floor For Residential
1 |  | 2BHK | 489.4391 | 0 | 758.6306 | 1st Floor For Residential
2 |  | Car Parking
3 |  | Car Parking
4 |  | 1BHK | 379.3234 | 0 | 587.9512
5 |  | 1BHK | 379.3234 | 0 | 587.9512
6 |  | MP Room | 243.2664 | 0 | 377.0629
2nd to 20th Floor (Refuge area on 8th & 15th Floor of Wing A) | [7 empty] | 8th, 15th Floor Refuge area at A WING
1 |  | 2BHK | 489.4391 | 0 | 758.6306 | 2nd to 20th Floor |  | 45.305
2 |  | 1BHK | 337.7743 | 0 | 523.5502
3 |  | 1RK | 287.0759 | 0 | 444.9676
4 |  | 1BHK | 379.3234 | 0 | 587.9512
5 |  | 1BHK | 379.3234 | 0 | 587.9512
6 |  | MP Room | 243.2664 | 0 | 377.0629
Remarks:
* | Construction work is in process at the time of Visit. Internal visit not allowed.(Slow Speed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved floor plan & C.C for Wing B. (on 31/08/2023).
* | Provide revised CC For C & D Wings.
* | We have updated revised CC from Rera site (on 20/03/2024 & 14/08/2025).
* | Construction work goes beyond CC permission. Please provide revised approved CC.
* | Please provide revised approved plans dtd. 22/03/2024.
* | As per RERA, completion period of project Enso Sanza is expired on 29/12/2024 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sanket Salvi |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Enso Sanza
Layout :
Google Map :
Formulas:
Akurli = [Akurli, row above]
WING B
Wing C
Wing C
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC