## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-18
Name of the builder |  |  |  | M/s. Madhusudan Leisure Homes
Name of the builder company |  |  |  | M/s. Madhusudan Leisure Homes
Name of the Project |  |  |  | Madhusudan Retreat
Contact Details ( Name & Contact No.) |  |  |  | Sagar Vora- 9702782222
Name / No of the Building |  |  |  | Type A (3, 40, 75 to 78, 102, 103, 106 to 109) Type A1 (74, 104, 105, 110) Type A2 (30, 62 to 71) Type B (5, 31 to 39, 41, 43, 72, 73, 80 to 84, 101, 132, 133) Type B1 (79) Type C (4, 6, 7, 42)
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet.
RERA No. |  |  |  | P51700030973
Project location details |  | Madhusudan Retreat, Survey No.50, near Hotel S R Dhaba, Chauk - Karjat - Murbad Rd, Patgaon, Pathgaon, Murbad, Karjat, Thane - 410201.
Survey No |  | 50
Locality |  | Patgaon
Road |  | Chauk - Karjat - Murbad Rd |  | Village |  | Pathgaon
City |  | Murbad |  | District |  | Thane
Taluka |  | Karjat |  | Pin Code |  | 410201
Nearby Landmark |  | Hotel S R Dhaba |  | Distance from city centre: |  | 16.8 KM from Vangani Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Banglow
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open plot
West | NA | NA |  |  | Open plot
North | NA | NA |  |  | Open plot
South | NA | NA |  |  | Chauk - Karjat - Murbad Rd
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.1303 |  | Longitude |  | 73.4179
Location Link |  | https://maps.app.goo.gl/JXDkHeHuouEaUnAt6
Area Statement Details :
Total Land Area under plots (1 - 125) |  |  |  | 29279.53
Net Area of plots |  |  |  | 43962.64
FSI |  |  |  | 1.5
Total number of Buildings |  |  |  | 53 Bunglows
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | District Collector, Raigad
Layout Approval No |  | BS/RKAN/BP/M.Pathgaon/T.Murbad/Z.Thane/2840 |  |  | Dated | 2021-12-31
Approved Floor plan No. |  | BS/RKAN/BP/M.Pathgaon/T.Murbad/Z.Thane/2840 |  |  | Dated | 2021-12-31
Commencement-CC No Valid Up to: |  | MS/K-1/T-11/ARBP/Pathgaon /T.Murbad/SR-10/2021 |  |  | Dated | 2022-06-09
Type (A, A1, A2, B, B1, C) = Ground + 1st Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 43962.64
Approved no of units |  |  | Bunglows - 53
Approved no of Floors |  |  | Type (A, A1, A2, B, B1, C) = Ground + 1st Floor
Proposed no of Floors |  |  | Type (A, A1, A2, B, B1, C) = Ground + 1st Floor
Expected Completion |  |  | As per RERA - 29/06/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details:
Plot/ Banglow No | Progress % | Disburse-ment % | Stage of construction:
1 | 100% | 100% | All work Completed. Possession granted to the Building.
2 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
3 | 5% | 32.5% | Excavation Completed, Footing work Completed
4 | 30% | 60% | Excavation, Plinth Completed, RCC upto 1 Slab Completed
5 | 72% | 88.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.7 Floor Completed
6 | 31.5% | 61% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.2 Floor Completed
7 | 31.5% | 61% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.2 Floor Completed
8 | 0% | 0% | Work not yet Started.
9 | 100% | 100% | All work Completed. Possession granted to the Building.
10 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
11 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
12 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
13 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
14 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
15 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
16 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
17 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
18 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
19 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
20 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
21 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
22 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed
23 | 70% | 87.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.5 Floor Completed
24 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
25 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
26 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
27 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
28 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
29 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
30 | 55.25% | 78.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.7 Floor Completed
31 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
32 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
33 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
34 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
35 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
36 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
37 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
38 | 63.25% | 83.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.2 Floor Completed
39 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
40 | 61.75% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.3 Floor, External Plaster upto 0.2 Floor Completed
41 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
42 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed
43 | 71.5% | 88% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.8 Floor, External Plaster upto 0.8 Floor Completed
44 | 10% | 45% | Excavation, Plinth Completed
45 | 5% | 32.5% | Excavation Completed, Footing work Completed
46 | 5% | 32.5% | Excavation Completed, Footing work Completed
47 | 2.5% | 26.25% | Excavation Completed, Footing work is process
48 | 2.5% | 26.25% | Excavation Completed, Footing work is process
49 | 0% | 0% | Work not yet Started.
50 | 0% | 0% | Work not yet Started.
51 | 0% | 0% | Work not yet Started.
52 | 0% | 0% | Work not yet Started.
53 | 0% | 0% | Work not yet Started.
54 | 0% | 0% | Work not yet Started.
55 | 0% | 0% | Work not yet Started.
56 | 0% | 0% | Work not yet Started.
57 | 0% | 0% | Work not yet Started.
58 | 2.5% | 26.25% | Excavation Completed, Footing work is process
59 | 2.5% | 26.25% | Excavation Completed, Footing work is process
60 | 5% | 32.5% | Excavation Completed, Footing work Completed
61 | 5% | 32.5% | Excavation Completed, Footing work Completed
62 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed
63 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed
64 | 55.25% | 78.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.7 Floor Completed
65 | 50% | 75% | Excavation, Plinth, RCC Slab Completed
66 | 31.5% | 61% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.2 Floor Completed
67 | 50% | 75% | Excavation, Plinth, RCC Slab Completed
68 | 50.75% | 75.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.1 Floor Completed
69 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed
70 | 50% | 75% | Excavation, Plinth, RCC Slab Completed
71 | 50.75% | 75.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.1 Floor Completed
72 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
73 | 73% | 89% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.8 Floor Completed
74 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
75 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
76 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed
77 | 70% | 87.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.5 Floor Completed
78 | 61.25% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor Completed
79 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.25 Floor, External Plaster upto 0.25 Floor Completed
80 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
81 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
82 | 59.5% | 81% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.8 Floor, Internal Plaster upto 0.2 Floor, External Plaster upto 0.2 Floor Completed
83 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
84 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
85 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
86 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
87 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
88 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
89 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
90 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
91 | 50% | 75% | Excavation, Plinth, RCC Slab Completed
92 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
93 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
94 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
95 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
96 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed
97 | 0% | 0% | Work not yet Started.
98 | 0% | 0% | Work not yet Started.
99 | 0% | 0% | Work not yet Started.
100 | 0% | 0% | Work not yet Started.
101 | 30.75% | 60.5% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.1 Floor Completed
102 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed
103 | 50% | 75% | Excavation, Plinth, RCC Slab Completed
104 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed
105 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed
106 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
107 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed
108 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
109 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
110 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed
132 | 63.25% | 83.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.2 Floor Completed
133 | 58.25% | 80.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.1 Floor Completed
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Plot + Bunglow Per Sq. Ft. (on Saleable area) |  |  |  |  | 2700
Development Charges |  |  |  |  | 50000
Retreat Club membership Charges |  |  |  |  | 50000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges (2 years) |  |  |  |  | 15000
Recommended rate of Parking
Distressed valuation of the Property |  |  |  |  | 2160
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Type A |  | 12 |  | 7729.4131 |  | 13304.304
Type A1 |  | 4 |  | 2576.471 |  | 4434.768
Type A2 |  | 11 |  | 7085.2954 |  | 12195.612
Type B |  | 21 |  | 19258.9488 |  | 29982.4762
Type B1 |  | 1 |  | 917.0928 |  | 1427.737
Type C |  | 4 |  | 5231.304 |  | 7095.1982
Total |  | 53 |  | 42798.5251 |  | 68440.0954
Building details Floor Wise
Details of Flats in Building | [7 empty] | 10.764
Bunglow / Plot No | Type | Description | Plot Area | Carpet Area | Attached Terrace area | Built - Up Area | Saleable area
50%
Type A
3 | Type A | 1BHK | 2455.699 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  | 2846991.888
40 | Type A | 1BHK | 1937.52 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  | 2846991.888
75 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
76 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  | 2846991.888
77 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
78 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
102 | Type A | 1BHK | 1767.0182 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
103 | Type A | 1BHK | 1668.2047 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
106 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
107 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694 |  | 2846991.888
108 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  | 2846991.888
109 | Type A | 1BHK | 1743.768 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  | 2846991.888
Type A1
74 | Type A1 | 1BHK | 1722.24 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  |  | 47.25
104 | Type A2 | 1BHK | 1641.7253 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799 |  |  | 48.555
105 | Type A3 | 1BHK | 1722.24 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
110 | Type A4 | 1BHK | 1735.695 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799
Type A2
30 | Type A2 | 1BHK | 1614.6 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799
62 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799
63 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
64 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799
65 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
66 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
67 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
68 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
69 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
70 | Type A2 | 1BHK | 1695.33 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 9483.694
71 | Type A2 | 1BHK | 2107.9141 | 644.1178 | 264.7944 | 1108.692 | 1054.4414 | 16122.2799
Type B
5 | Type B | 2BHK | 2504.7828 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
31 | Type B | 2BHK | 1999.1977 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
32 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585
33 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
34 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585
35 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585
36 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585
37 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585
38 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585
39 | Type B | 2BHK | 1937.52 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 6824.3585 |  | 10.764
41 | Type B | 2BHK | 3169.2445 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
43 | Type B | 2BHK | 2152.8 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
72 | Type B | 2BHK | 2375.8301 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
73 | Type B | 2BHK | 2152.8 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
80 | Type B | 2BHK | 2152.8 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
81 | Type B | 2BHK | 2152.8 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
83 | Type B | 2BHK | 2152.8 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
84 | Type B | 2BHK | 2562.6931 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
101 | Type B | 2BHK | 2181.0017 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
132 | Type B | 2BHK | 2562.6931 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
133 | Type B | 2BHK | 2181.0017 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094
Type B1
79 | Type B1 | 2BHK | 1950.975 | 917.0928 | 269.1 | 1427.737 | 1465.3392 | 11601.4094 |  | 3809881.92
Type C | [9 empty] | 0
4 | Type C | 3BHK | 2719.417 | 1307.826 | 192.6756 | 1773.7996 | 2058.0768 | 8260.1388 |  | 5350999.68
6 | Type C | 3BHK | 2732.872 | 1307.826 | 192.6756 | 1773.7996 | 2058.0768 | 8260.1388 |  | 5350999.68
7 | Type C | 3BHK | 2960.6382 | 1307.826 | 192.6756 | 1773.7996 | 2058.0768 | 4858.9052 |  | 5350999.68
42 | Type C | 3BHK | 2582.7142 | 1307.826 | 192.6756 | 1773.7996 | 2058.0768 | 8260.1388 |  | 5350999.68
Remarks:
* | Bunglow No.3, 5, 6 |  |  | Work is same as last visit (22/05/2024). |  |  |  |  | Type A (3, 40), Type A2 (30), Type B (5, 31 to 34, 41, 132, 133), Type C (4, 6, 7, 42) =
* | Bunglow No.7, 79, 82, 133 |  |  | Work is same as last visit (17/01/2025).
* | Bunglow No. 43 |  |  | Work is same as last visit (19/09/2024).
* | Bunglow No. 32, 34 to 38, 40, 42, 62, 63, 65 to 72, 74 to 78, 80, 81, 101 to 110, 132 |  |  | Work is same as last visit (13/05/2025).
* | Bunglow No. 4, 30, 31, 33, 39, 41, 73, 83, 84 |  |  | Construction work is in process at the time of visit.
* | Bunglow No. 64 |  |  | Construction work has incresed as compare to last visited date 13/05/2025 but at the time of visit no labour or no active work found on site.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Project is connected by Chauk - Karjat - Murbad Rd.
* | The project is 2.2 km from Madhusudan Heritage.
* | The Project is 19.1 Km from Neral Railway station.
* | The Project is 27.9 Km from Badlapur Railway station.
* | The Project is 33.9 Km from Karjat Railway statiom.
* | There is No School, No Market Place, Hospital in range of 2 to 4km.
* | There is industry in the north direction.
* | On Site, we meet Mr. Prashant : 7030240399
* | As per RERA, completion period of project Madhusudan Retreat is expired on 29/06/2025 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge. | [9 empty] | Extra construction work given to 30, 42 & 102
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Madhusudan Retreat |  |  |  |  | Marking As per Red 18/01/2025
PHOTOGRAPHS OF PROPERTY : |  |  | Madhusudan Retreat
PHOTOGRAPHS OF PROPERTY : |  |  | Madhusudan Retreat
Sale Plan:
Google Map :
Formulas:
Pathgaon = [Pathgaon, row above]
76 75 74
42 72 132
41 40 39
38 37 36
65 66 67 63
68 69 70 71
84 83 80 81
79 78 77
108 109 110
105 106 107
103 104
101 102
30
30

## %
Plot/ Banglow no | Floor |  | Excavation | Plinth | RCC | Brick work | Internal Plaster | Ext. Plaster | Flooring | Painting | Finishing | Possession | Progress % | Disbursement % | Stage of construction: | Excavation | Plinth | RCC (Including podiums) | Brickwork | Internal Plaster | Ext. Plaster & Plumbing | Flooring & Fitting | Painting & Wooden | Building Common Amenities | Possession | Piling Work in process | Excavation in process | Excavation Completed | Footing in Process | Footing Completed | Basement 1 | Basement 2 | Basement 3 | Basement 4 | Plinth in process | Plinth completed
1 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work Completed. Possession granted to the Building. | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities | Completed
2 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
3 | G + 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 32.5% | Excavation Completed, Footing work Completed | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work Completed |  | Excavation | Completed
4 | G + 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 60% | Excavation, Plinth Completed, RCC upto 1 Slab Completed | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , RCC upto 1 Slab | Excavation, Plinth | Completed | Completed
5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.7 | 0 | 0 | 0 | 0 | 72% | 88.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.7 Floor Completed | 100% | 100% | 100% | 100% | 100% | 70% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.7 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
6 | G + 1 | 1 | 1 | 1 | 1 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5% | 61% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.2 Floor Completed | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , RCC upto 1 Slab, Brickwork upto 0.2 Floor | Excavation, Plinth | Completed | Completed
7 | G + 1 | 1 | 1 | 1 | 1 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5% | 61% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.2 Floor Completed | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , RCC upto 1 Slab, Brickwork upto 0.2 Floor | Excavation, Plinth | Completed | Completed
8 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
9 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work Completed. Possession granted to the Building. | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities | Completed
10 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
11 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
12 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
13 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
14 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
15 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
16 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
17 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
18 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
19 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
20 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
21 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
22 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 85% | 95% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring | Completed
23 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 70% | 87.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
24 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
25 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
26 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
27 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
28 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
29 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
30 | G + 1 | 1 | 1 | 1 | 2 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 55.25% | 78.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.7 Floor Completed | 100% | 100% | 100% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.7 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
31 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
32 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
33 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
34 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
35 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
36 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
37 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
38 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.5 | 0.2 | 0 | 0 | 0 | 0 | 63.25% | 83.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.2 Floor Completed | 100% | 100% | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.5 Floor, External Plaster upto 0.2 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
39 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
40 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.3 | 0.2 | 0 | 0 | 0 | 0 | 61.75% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.3 Floor, External Plaster upto 0.2 Floor Completed | 100% | 100% | 100% | 100% | 30% | 20% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.3 Floor, External Plaster upto 0.2 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
41 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
42 | G + 1 | 1 | 1 | 1 | 2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed | 100% | 100% | 100% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.2 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
43 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 71.5% | 88% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.8 Floor, External Plaster upto 0.8 Floor Completed | 100% | 100% | 100% | 100% | 80% | 80% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.8 Floor, External Plaster upto 0.8 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
44 | G + 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 45% | Excavation, Plinth Completed | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth | Completed
45 | G + 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 32.5% | Excavation Completed, Footing work Completed | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work Completed |  | Excavation | Completed
46 | G + 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 32.5% | Excavation Completed, Footing work Completed | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work Completed |  | Excavation | Completed
47 | G + 1 | 1 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5% | 26.25% | Excavation Completed, Footing work is process | 100% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work is process |  | Excavation | Completed
48 | G + 1 | 1 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5% | 26.25% | Excavation Completed, Footing work is process | 100% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work is process |  | Excavation | Completed
49 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
50 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
51 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
52 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
53 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
54 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
55 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
56 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
57 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
58 | G + 1 | 1 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5% | 26.25% | Excavation Completed, Footing work is process | 100% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work is process |  | Excavation | Completed
59 | G + 1 | 1 | 1 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5% | 26.25% | Excavation Completed, Footing work is process | 100% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work is process |  | Excavation | Completed
60 | G + 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 32.5% | Excavation Completed, Footing work Completed | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work Completed |  | Excavation | Completed
61 | G + 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 32.5% | Excavation Completed, Footing work Completed | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | , Footing work Completed |  | Excavation | Completed
62 | G + 1 | 1 | 1 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
63 | G + 1 | 1 | 1 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
64 | G + 1 | 1 | 1 | 1 | 2 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 55.25% | 78.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.7 Floor Completed | 100% | 100% | 100% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.7 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
65 | G + 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 75% | Excavation, Plinth, RCC Slab Completed | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab | Completed
66 | G + 1 | 1 | 1 | 1 | 1 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 31.5% | 61% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.2 Floor Completed | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , RCC upto 1 Slab, Brickwork upto 0.2 Floor | Excavation, Plinth | Completed | Completed
67 | G + 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 75% | Excavation, Plinth, RCC Slab Completed | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab | Completed
68 | G + 1 | 1 | 1 | 1 | 2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 50.75% | 75.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.1 Floor Completed | 100% | 100% | 100% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.1 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
69 | G + 1 | 1 | 1 | 1 | 2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed | 100% | 100% | 100% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.2 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
70 | G + 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 75% | Excavation, Plinth, RCC Slab Completed | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab | Completed
71 | G + 1 | 1 | 1 | 1 | 2 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 50.75% | 75.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.1 Floor Completed | 100% | 100% | 100% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.1 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
72 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
73 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.8 | 0 | 0 | 0 | 0 | 73% | 89% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.8 Floor Completed | 100% | 100% | 100% | 100% | 100% | 80% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.8 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
74 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
75 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
76 | G + 1 | 1 | 1 | 1 | 2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed | 100% | 100% | 100% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.2 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
77 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 70% | 87.5% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
78 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 61.25% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor Completed | 100% | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.5 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
79 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 61.88% | 82.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.25 Floor, External Plaster upto 0.25 Floor Completed | 100% | 100% | 100% | 100% | 25% | 25% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.25 Floor, External Plaster upto 0.25 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
80 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
81 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
82 | G + 1 | 1 | 1 | 1 | 2 | 0.8 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 59.5% | 81% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.8 Floor, Internal Plaster upto 0.2 Floor, External Plaster upto 0.2 Floor Completed | 100% | 100% | 100% | 80% | 20% | 20% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.8 Floor, Internal Plaster upto 0.2 Floor, External Plaster upto 0.2 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
83 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
84 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
85 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
86 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
87 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
88 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
89 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
90 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
91 | G + 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 75% | Excavation, Plinth, RCC Slab Completed | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab | Completed
92 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
93 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
94 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
95 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
96 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 75% | 90% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster | Completed
97 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
98 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
99 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
100 | G + 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | Work not yet Started. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 | Work not yet Started.
101 | G + 1 | 1 | 1 | 1 | 1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 30.75% | 60.5% | Excavation, Plinth Completed, RCC upto 1 Slab, Brickwork upto 0.1 Floor Completed | 100% | 100% | 50% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , RCC upto 1 Slab, Brickwork upto 0.1 Floor | Excavation, Plinth | Completed | Completed
102 | G + 1 | 1 | 1 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
103 | G + 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 75% | Excavation, Plinth, RCC Slab Completed | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab | Completed
104 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 57.5% | 80% | Excavation, Plinth, RCC Slab, Brickwork Completed | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  |  | Excavation, Plinth, RCC Slab, Brickwork | Completed
105 | G + 1 | 1 | 1 | 1 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 53.75% | 77.5% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.5 Floor Completed | 100% | 100% | 100% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.5 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
106 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
107 | G + 1 | 1 | 1 | 1 | 2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 51.5% | 76% | Excavation, Plinth, RCC Slab Completed, Brickwork upto 0.2 Floor Completed | 100% | 100% | 100% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Brickwork upto 0.2 Floor | Excavation, Plinth, RCC Slab | Completed | Completed
108 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
109 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
110 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 0.4 | 0 | 0 | 0 | 0 | 69% | 87% | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 0.4 Floor Completed | 100% | 100% | 100% | 100% | 100% | 40% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , External Plaster upto 0.4 Floor | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster | Completed | Completed
132 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.5 | 0.2 | 0 | 0 | 0 | 0 | 63.25% | 83.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.5 Floor, External Plaster upto 0.2 Floor Completed | 100% | 100% | 100% | 100% | 50% | 20% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.5 Floor, External Plaster upto 0.2 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
133 | G + 1 | 1 | 1 | 1 | 2 | 1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 58.25% | 80.5% | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 0.1 Floor Completed | 100% | 100% | 100% | 100% | 10% | 0% | 0% | 0% | 0% | 0% | 0.25 | 0.5 | 1 | 0.25 | 0.5 | 0 | 0 | 0 | 0 | 0.75 | 1 |  | , Internal Plaster upto 0.1 Floor | Excavation, Plinth, RCC Slab, Brickwork | Completed | Completed
Construction details: |  | G + 1 | [5 empty] | Excavation, Plinth, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth, RCC Slab
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 50% |  | 75% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 2 | 100% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted