## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 22/08/2025
CPC Name: |  |  |  |  | Axis Kalina
Date Of Property Visit |  |  |  |  | 2025-08-19
Name of the builder group |  |  |  |  | M/s. Nirvana Lifestyle Ventures
Name of the builder company |  |  |  |  | M/s. Nirvana Lifestyle Ventures
Name of the Project |  |  |  |  | Wollywood Phase III
Contect Details ( Name & Contect No.) |  |  |  |  | 2262296229/8975034788-Shitej
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Shitej 8975034788
Name / no of the Building |  |  |  |  | Wollywood Phase III/3 Buildings
Docouments Provided |  |  |  |  | Approved Layout, NA Order
RERA No. |  |  |  |  | P99000016446
Project location details |  | Wollywood Phase III, Gut No. 73 2/1,61/1,61/5,73 1/2,61 7/2 & Plot No. 108,109,110,111,112,117,118, Gates Budruk, Wada, Palghar
Plot No | 108, 109, 110, 111, 112, 117, 118 |  | Gut. No |  | 73 2/1, 61/1, 61/5, 73 1/2, 61 7/2 |  | Locality | Gates Budruk
Road | Bhiwandi Wada Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 421303
Near by Landmark |  | Ganpati Temple, Gates |  |  | Distance from city centre: |  | About 30.6 Km from Atgaon Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Open Plot |  | Open Plot |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.6305 |  | Longitude |  | 73.1246
Location Link |  | https://goo.gl/maps/xyKgjExtSVHmnbPr8
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 4441.5
Permissible FSI |  |  |  |  | 0.98375
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.98375
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 4369.31
Total number of Buildings |  |  |  |  | 3 Buildings
Approval Detail : Plan approval
Layout Approval No |  | BS/RKKN/BP/GATES/WADA/SN.61-1 & OTHER/SSNR/267 |  |  |  | Dated | 03/03/2017.
Building plan approval No |  | BS/RKKN/BP/GATES/WADA/SN.61-1 & OTHER/SSNR/267 |  |  |  | Dated | 03/03/2017. | Expiry date:NA
NA order cum Commencement of Construction No. |  | MHSL/KS.1/T.2/NP/SR-32/2016 Valid Upto : Type A = G + 1st to 3rd Floor Type B = G + 1st to 3rd Floor |  |  |  | Dated | 02/05/2018. | Expiry date: One year from date of issue
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 02/05/2018. |  | Expected Completion |  | 2026-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 4369.31 |  | Approved no of units |  | Shop = 8 & Stores = 4 Flats = 82
Approved no of Floors |  | Building Type - A1, A2 & B = Gr. + 1st to 3rd Floor
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Type - A1 - Simran = G + 3rd Floor | [6 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Work not yet Started. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 0 | 0% |  | 0% |  | 0% |  | Excavation in process | 1.5
Plinth |  | 0 | 0% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Construction details: |  | Type - A2 - Queen = G + 3rd Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3 |  |  |  | Ajinkya sir has told this changes…He had visit the project in may and got to knw that simran work has not started yet.
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 10% |  | 45% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Construction details: |  | Type - B - Chandani = G + 1st to 3rd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 1.5 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 1.5 Floor, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 81.67% |  | 92.5% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 1.5 | 50% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 33.33% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 7000
Society Formation Charges | [5 empty] | 50,000/-
Recommended rate of Parking | [5 empty] | 50,000/-
Development charges & Resort Membership | [5 empty] | 3,00,000/-
Distressed valuation of the Property | [5 empty] | 4000
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Type A1 - Simran |  | 4 | 1590.719 |  |  | 2386.0785
Type A2 - Queen |  | 4 | 1590.719 |  |  | 2386.0785
Type B - Chandani |  | 4 | 1619.3986 |  |  | 2429.0979
Total |  | 12 | 4800.8366 |  |  | 7201.2549
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Type A1 - Simran |  | 23 | 9035.8398 |  |  | 13558
Type A2 - Queen |  | 23 | 9035.8398 |  |  | 13558
Type B - Chandani |  | 36 | 15015.4571 |  |  | 22866
Total |  | 82 | 33087.1367 |  |  | 49982
Grand Total |  | 94 | 37887.9733 |  |  | 57183.2549
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building Type A1 - Simran
Ground Floor is for Shops & Parking
1 |  | Shop-1 | 506.4806 |  | 0 | 759.721 | N | Ground Floor |  | 47.0532 |  | 10.764
2 |  | Shop-2 | 506.4806 |  | 0 | 759.721 | N |  |  | 47.0532 |  | 10.764
3 |  | Store-1 | 288.8788 |  | 0 | 433.3183 | N |  |  | 26.8375 |  | 10.764
4 |  | Store-2 | 288.8788 |  | 0 | 433.3183 | N |  | 4 | 26.8375 |  | 10.764
1st & 2nd Floor
101, 201 |  | 1BHK | 503.8628 |  | 0 | 770 | N | 1st & 2nd Floor |  | 40.82 | 5.99 | 10.764
102, 202 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
103, 203 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
104, 204 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
105, 205 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
106, 206 |  | 1RK | 294.9336 |  | 0 | 416 | N |  |  | 24.16 | 3.24 | 10.764
107, 207 |  | 1RK | 294.9336 |  | 0 | 416 | N |  |  | 24.16 | 3.24 | 10.764
108, 208 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  | 16 | 40.82 | 5.99 | 10.764
3rd Floor
301 |  | 1BHK | 503.8628 |  | 0 | 770 | N | 3rd Floor |  | 40.82 | 5.99 | 10.764
302 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
303 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
304 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
305 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
306 |  | 1RK | 294.9336 |  | 0 | 416 | N |  |  | 24.16 | 3.24 | 10.764
307 |  | 1RK | 294.9336 |  | 0 | 416 | N |  | 7 | 24.16 | 3.24 | 10.764
308 |  | Terrace | [6 empty] | 7 | 24.16 | 3.24 | 10.764
Building Type A2 - Queen
Ground Floor is for Shops & Parking
1 |  | Shop-1 | 506.4806 |  | 0 | 759.721 | N | Ground Floor |  | 47.0532 |  | 10.764
2 |  | Shop-2 | 506.4806 |  | 0 | 759.721 | N |  |  | 47.0532 |  | 10.764
3 |  | Store-1 | 288.8788 |  | 0 | 433.3183 | N |  |  | 26.8375 |  | 10.764
4 |  | Store-2 | 288.8788 |  | 0 | 433.3183 | N |  | 4 | 26.8375 |  | 10.764
1st & 2nd Floor
101, 201 |  | 1BHK | 503.8628 |  | 0 | 770 | N | 1st & 2nd Floor |  | 40.82 | 5.99 | 10.764
102, 202 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
103, 203 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
104, 204 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
105, 205 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
106, 206 |  | 1RK | 294.9336 |  | 0 | 416 | N |  |  | 24.16 | 3.24 | 10.764
107, 207 |  | 1RK | 294.9336 |  | 0 | 416 | N |  |  | 24.16 | 3.24 | 10.764
108, 208 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  | 16 | 40.82 | 5.99 | 10.764
3rd Floor
301 |  | 1BHK | 503.8628 |  | 0 | 770 | N | 3rd Floor |  | 40.82 | 5.99 | 10.764
302 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
303 |  | 1RK | 287.2912 |  | 0 | 432 | N |  |  | 23.45 | 3.24 | 10.764
304 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
305 |  | 1BHK | 503.8628 |  | 0 | 770 | N |  |  | 40.82 | 5.99 | 10.764
306 |  | 1RK | 294.9336 |  | 0 | 416 | N |  |  | 24.16 | 3.24 | 10.764
307 |  | 1RK | 294.9336 |  | 0 | 416 | N |  | 7 | 24.16 | 3.24 | 10.764
308 |  | Terrace | [6 empty] | 7 | 24.16 | 3.24 | 10.764
Building Type B - Chandani
Ground Floor is for Shops & Parking
1 |  | Shop | 510.9725 |  | 0 | 766.4587 | N | Ground Floor |  | 47.4705 |  | 10.764
2 |  | Shop | 298.7268 |  | 0 | 448.0903 | N |  |  | 27.7524 |  | 10.764
3 |  | Shop | 298.7268 |  | 0 | 448.0903 | N |  |  | 27.7524 |  | 10.764
4 |  | Shop | 510.9725 |  | 0 | 766.4587 | N |  | 4 | 47.4705 |  | 10.764
1st, 2nd & 3rd Floor
1 |  | 1BHK | 344.5556 |  | 0 | 507 | N | 1st, 2nd & 3rd |  | 3.25 | 28.76 |  | 10.764
2 |  | 1RK | 489.5467 |  | 0 | 752 | N |  |  | 3.08 | 42.4 |  | 10.764
3 |  | 1BHK | 494.2829 |  | 0 | 786 | N |  |  | 2.98 | 42.94 |  | 10.764
4 |  | 1RK | 340.7882 |  | 0 | 507 | N |  |  | 3.15 | 28.51 |  | 10.764
5 |  | 1BHK | 488.4703 |  | 0 | 752 | N |  |  | 2.98 | 42.4 |  | 10.764
6 |  | 1RK | 344.5556 |  | 0 | 507 | N |  |  | 3.25 | 28.76 |  | 10.764
7 |  | 1RK | 344.5556 |  | 0 | 507 | N |  |  | 3.25 | 28.76 |  | 10.764
8 |  | 1BHK | 489.5467 |  | 0 | 752 | N |  |  | 3.08 | 42.4 |  | 10.764
9 |  | 1RK | 340.7882 |  | 0 | 507 | N |  |  | 3.15 | 28.51 |  | 10.764
10 |  | 1BHK | 496.1128 |  | 0 | 786 | N |  |  | 3.15 | 42.94 |  | 10.764
11 |  | 1BHK | 488.4703 |  | 0 | 752 | N |  |  | 2.98 | 42.4 |  | 10.764
12 |  | 1RK | 343.4792 |  | 0 | 507 | N |  | 36 | 3.15 | 28.76 |  | 10.764
Remarks: 1. Type - B - Chandani = Construction work is same as last visit dtd. 20/08/2024. Type - A2 - Queen = Construction work was stopped from visit 7/02/2020. Type - A1 - Simran = Work not yet started. 2. We considered Shop Saleable area as per our calculation. 3. We considered Flat Saleable area as per builder area sheet. 4. We considered Carpet area as per Approved Plan. 5. We considered recommended rate as per Market Inquire. 6. Car parking is subjected to authentic documentation. 7. As per the builder salesperson, Mr. Rupesh Bandre, Queen & Simran Buildings are cancelled from the project. 8. The project has received first NA order on 02/05/2018, But construction work is not yet completed. | [8 empty] | 108
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Wollywood Phase III
Google Map :
Queen
Queen
Chandani

## A1
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 0 | 20
| 4 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 0 | 20

## B
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 10 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0.5 | 0 | Progress |  |  | 10 | 4 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 3 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 4 | 3
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 14 | 33

## Note
2021-02-23 | Pratiksha | direct visit external visit complete side off madhe koni bhetla nahi direct visit

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 5.88 | 2.98 | 17.5224 | CB | 1 | 2.75 | 2.75 |  |  | 0
|  |  |  | 0 | FB | 1 | 3.24 | 3.24 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.03 | 2.4 | 4.872 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.65 | 3.85 | 14.0525 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.43 | 1.35 | 3.2805 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 427.6257 | 39.7274 |  |  | 64.4764 | 5.99 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0