## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-11
Name of the builder |  |  |  | Mr. Mohd Sajid Ashfaqueahd Khan
Name of the builder Company |  |  |  | M/s. S. K. Construction
Name of Project |  |  |  | Signature Galaxy Apartment
Contact Details ( Name & Contect No.) |  |  |  | 9022442667
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P99000025417
Project location details |  | Signature Galaxy Apartment, Survey No.22, Hissa No.6(P), Plot No.10, Vithhal Mandir Road, Waliv, Vasai, Vasai, Palghar.
Survey No |  | 22, Hissa No.6(P), Plot No.10
Road |  | Vithhal Mandir Road |  | Locality/Village |  | Waliv
City |  | Vasai |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401208
Near by Landmark |  | Hayat Residency |  | Distance from city centre: |  | 7.1Km from Vasai Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Suryoday CHS
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Hayat Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.4202 |  | Longitude |  | 72.8623
Location Link |  | https://goo.gl/maps/Qtue797UnvkpA8Gn8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 487.66
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 487.66
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | VVCMC/TP/REV/VP-5796/2756/2016-2017 |  |  | Dated | 26/10/2016.
Approved Floor plan No. |  | VVCMC/TP/REV/VP-5796/2756/2016-2017 |  |  | Dated | 26/10/2016.
Plinth Completion Certificate No. |  | VVCMC/TP/PCC/VP-5796/119/2018-19 |  |  | Dated | 24/01/2019.
Commencement Certificate No. |  | VVCMC/TP/REV/VP-5796/118/2018-19 |  |  | Dated | 24/01/2019.
Valid Up to: Gr + 1st to 3rd Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 487.66
Approved no of units |  |  | Flats - 11, Shops - 5
Approved no of Floors |  |  | Gr + 1st to 3rd Floor
Proposed no of Floors |  |  | Gr + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Gr + 1st to 4th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 95% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5200
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7000/-
Development Charges |  |  |  |  | 1,45,000/-
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water & Supply |  |  |  |  | 65000/-
Society Formation Charges |  |  |  |  | 150000/-
Advance Maintenance Charges |  |  |  |  | 85000/-
Recommended rate of Parking |  |  |  |  | 100000/-
Distressed valuation of the Property |  |  |  |  | 4160
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shop |  | 5 | 706.6566 |  | 1059.9849
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Flat |  | 11 | 4712.6137 |  | 6833.2899
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
Ground Floor for Commercial
1 |  | Shop | 74.0563 | 0 | 111.0845 | Ground Floor
2 |  | Shop | 123.8129 | 0 | 185.7194
3 |  | Shop | 176.1259 | 0 | 264.1889
4 |  | Shop | 103.6035 | 0 | 155.4052
5 |  | Shop | 229.0579 | 0 | 343.5869
1st to 2nd Floor for Residential
1 |  | 1BHK | 446.9482 | 0 | 648.0749 | 1st to 2nd Floor |  | 5036.4551
2 |  | 1RK | 266.705 | 0 | 386.7223 |  |  | 5430.2537
3 |  | 2BHK | 570.0883 | 0 | 826.6281 |  |  | 5201.8555
4 |  | 1BHK | 430.6945 | 0 | 624.5071 |  |  | 5226.5219
3rd Floor (Part Terrace)
1 |  | 1BHK | 446.9482 | 0 | 648.0749 | 3rd Floor (Part Terrace) |  | 5036.4551
2 |  | 1RK | 266.705 | 0 | 386.7223 |  |  | 5430.2537
3 |  | 2BHK | 570.0883 | 0 | 826.6281 |  |  | 5201.8555
4 |  | Terrace
Remarks:
1. Finishing work is pending. Some flats are occupied by tenants. 2. We considered Saleable area as per our calculation. 3. We have considered construction percentage as per proposed no. of floors (Gr + 4th Floor) because construction work goes beyond approved no. of floors (Gr + 3rd Floor). 4. We considered Carpet area as per Approved Plan. 5. We considered Gross carpet area = Net carpet + Enclose balcony + A.P Area 6. We have considered rate by verifying it from market inquire. 7. Car parking is subjected to authentic documentation. 8. Please provide the latest approved CC & Floor plans. construction percentage given as per proposed no of floors. 9. As checked on RERA portal on date 19/08/2025, we have observed that above project "Signature Galaxy Apartment" is kept under abeyance. Please check from your end. 9. As per RERA, completion period of project Signature Galaxy Apartment is expired on 30/09/2022 but still project is under construction. 10. On site we met Mr.Suraj Singh : 9022442667. 8. On Site, we meet Mr.Ganesh Kautkar - 9923214522/7021844589.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Shruti
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Signature Galaxy Apartment
Google Map :

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted