## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis sanpada
Date Of Property Visit |  |  |  |  | 2025-08-18
Name of the builder group |  |  |  |  | M/s.Sudarshan Nirman Co.
Name of the builder company |  |  |  |  | M/s.Sudarshan Nirman Co.
Name of the Project |  |  |  |  | Sudarshan Garden Phase II
Contact Details ( Name & Contact No.) |  |  |  |  | 2241319977
Name / no of the Building |  |  |  |  | Building no.3 (A & B Wings) = Madhusudan Building no.4 (A, B & C Wings) = Ananta
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC, Cost Sheet
RERA No. |  |  |  |  | P51700018847
Project location details |  | Sudarshan Garden Phase II, Next to Millitary school, Village-Pitambare, Khadavali East, Kalyan, Dist.- Thane.
Plot No | NA |  |  | Survey No |  | 34 /1/A/1 | Locality | Pitambare
Road | Ghodbunder Road |  |  |  | District | Thane
City | Kalyan |  |  |  | Pin Code | 421605
Near by Landmark |  | Millitary school. |  |  | Distance from city centre: |  | About 1.5 Km from Khadivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Slum |  | Building |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.3494 |  | Longitude |  | 73.2114
Location Link |  | https://goo.gl/maps/tstyEvWwXuLvGYpw8
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 3292.21
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 3292.21
Total number of Buildings |  |  |  |  | 02 Buildings (5 Wings)
Approval Detail : Plan approval
Layout Approval No |  | BS/RKN/BP./Pitambare/Kalyan/459 |  |  |  | Dated | 14/03/2018.
Building plan approval No |  | BS/RKN/BP./Pitambare/Kalyan/459 |  |  |  | Dated | 14/03/2018. | Expiry date:NA
Date of Commencement of Construction |  | BS/RKN/BP./Pitambare/Kalyan/1354 Valid Up to:Gr. + 1st to 3rd floor. |  |  |  | Dated | 11/07/2018. | Expiry date: One year from date of issue
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 11/07/2018. |  | Expected Completion |  | 2026-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 3292.21 |  | Approved no of units |  |  | Flats = 60
Approved no of Floors |  | Gr. + 1st to 3rd floor. |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building no. 3 (A & B) = Gr. + 1st to 3rd floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 50% |  | 75% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Construction details: |  | Building no. 4 (A, B & C Wing) = Gr. + 1st to 3rd floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 50% |  | 75% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3200
Advance maintenance | [5 empty] | 35,000/-
Grill Charges | [5 empty] | 55000/-
Recommended rate of Parking | [5 empty] | 100000/-
Development charges | [5 empty] | 200000/-
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2560
Building details Floor Wise
Details of Flats in Building
Flat No. | Description | Carpet area | Attached Terrace area |  | Saleable area |  | PLC Y/N | Floor
Building No. 1
Ground Floor For Parking & Commercial.
1 | Shop | 136.7136 | 0 |  | 205.0703 |  | N | Ground Floor
2 | Shop | 92.4649 | 0 |  | 138.6974 |  | N
3 | Shop | 118.0014 | 0 |  | 177.0021 |  | N
4 | Shop | 118.0014 | 0 |  | 177.0021 |  | N
5 | Shop | 94.1043 | 0 |  | 141.1564 |  | N
6 | Shop | 138.7049 | 0 |  | 208.0574 |  | N
1st To 3rd Floor.
1 | 2 BHK | 473 | 0 |  | 685.85 |  | N | 1st To 3rd Floor.
2 | 2 BHK | 473 | 0 |  | 685.85 |  | N
3 | 2 BHK | 473 | 0 |  | 685.85 |  | N
4 | 2 BHK | 473 | 0 |  | 685.85 |  | N
Building No. 2.
Ground Floor For Parking.
1st & 3rd Floor.
1 | 1 BHK | 271 | 39.7999 |  | 432.7499 |  | N | 1st & 3rd Floor.
2 | 1 BHK | 271 | 39.7999 |  | 432.7499 |  | N
3 | 1 BHK | 293 | 0 |  | 424.85 |  | N
4 | 1 BHK | 293 | 0 |  | 424.85 |  | N
2nd Floor.
1 | 1 BHK | 271 | 0 |  | 392.95 |  | N | 2nd Floor.
2 | 1 BHK | 271 | 0 |  | 392.95 |  | N
3 | 1 BHK | 293 | 0 |  | 424.85 |  | N
4 | 1 BHK | 293 | 0 |  | 424.85 |  | N
Building No. 3 = Madhusudan
A Wing.
Ground Floor For Parking.
1st & 3rd Floor.
1 | 1 BHK | 392 | 43.2454 |  | 605 |  | N | 1st & 3rd Floor. |  | 36300
2 | 1 BHK | 351 | 0 |  | 540 |  | N |  | 1.5385 | 32400
3 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
4 | 2 BHK | 432 | 0 |  | 670 |  | N |  |  | 40200
2nd Floor. | [9 empty] | 0
1 | 1 BHK | 358 | 0 |  | 550 |  | N | 2nd Floor. |  | 33000
2 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
3 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
4 | 2 BHK | 432 | 0 |  | 670 |  | N |  |  | 40200
B Wing. | [9 empty] | 0
Ground Floor For Parking. | [9 empty] | 0
1st & 3rd Floor. | [9 empty] | 0
1 | 2 BHK | 392 | 0 |  | 670 |  | N | 1st & 3rd Floor. |  | 40200
2 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
3 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
4 | 1 BHK | 432 | 43 |  | 605 |  | N |  |  | 36300
2nd Floor. | [9 empty] | 0
1 | 2 BHK | 358 | 0 |  | 670 |  | N | 2nd Floor. |  | 40200
2 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
3 | 1 BHK | 351 | 0 |  | 540 |  | N |  |  | 32400
4 | 1 BHK | 432 | 0 |  | 550 |  | N |  |  | 33000
Building No. 4 = Ananta | [9 empty] | 0
A Wing. | [9 empty] | 0
Ground Floor For Parking. | [9 empty] | 0
1st & 3rd Floor. | [9 empty] | 0 | 1.5849
1 | 1 BHK | 265 | 27.0951 |  | 420 |  | N | 1st & 3rd Floor. |  | 25200 | 1.587
2 | 1 BHK | 293 | 0 |  | 465 |  | N |  |  | 27900
3 | 1 BHK | 300 | 0 |  | 455 |  | N |  |  | 27300
4 | 1 BHK | 273 | 27 |  | 410 |  | N |  |  | 24600
2nd Floor. | [9 empty] | 0
1 | 1 BHK | 265 | 0 |  | 420 |  | N | 2nd Floor. |  | 25200
2 | 1 BHK | 265 | 0 |  | 420 |  | N |  |  | 25200
3 | 1 BHK | 273 | 0 |  | 410 |  | N |  |  | 24600
4 | 1 BHK | 273 | 0 |  | 410 |  | N |  |  | 24600
B Wing. | [9 empty] | 0
Ground Floor For Parking. | [9 empty] | 0
1st & 3rd Floor. | [9 empty] | 0
1 | 1 BHK | 265 | 27 |  | 410 |  | N | 1st & 3rd Floor. |  | 24600
2 | 1 BHK | 293 | 0 |  | 455 |  | N |  |  | 27300
3 | 1 BHK | 293 | 0 |  | 455 |  | N |  |  | 27300
4 | 1 BHK | 265 | 27 |  | 410 |  | N |  |  | 24600
2nd Floor. | [9 empty] | 0
1 | 1 BHK | 265 | 0 |  | 410 |  | N | 2nd Floor. |  | 24600
2 | 1 BHK | 265 | 0 |  | 410 |  | N |  |  | 24600
3 | 1 BHK | 265 | 0 |  | 410 |  | N |  |  | 24600
4 | 1 BHK | 265 | 0 |  | 410 |  | N |  |  | 24600
C Wing. | [9 empty] | 0
Ground Floor For Parking. | [9 empty] | 0
1st & 3rd Floor. | [9 empty] | 0
1 | 1 BHK | 273 | 0 |  | 410 |  | N | 1st & 3rd Floor. |  | 24600
2 | 1 BHK | 300 | 0 |  | 455 |  | N |  |  | 27300
3 | 1 BHK | 293 | 27 |  | 465 |  | N |  |  | 27900
4 | 1 BHK | 265 | 27 |  | 420 |  | N |  |  | 25200
2nd Floor. | [9 empty] | 0
1 | 1 BHK | 273 | 0 |  | 410 |  | N | 2nd Floor. |  | 24600
2 | 1 BHK | 273 | 0 |  | 410 |  | N |  |  | 24600
3 | 1 BHK | 265 | 0 |  | 420 |  | N |  |  | 25200
4 | 1 BHK | 265 | 0 |  | 420 |  | N |  |  | 25200
Remarks: 1. Building no.3 (A & B Wings) & Building no.4 (A, B & C Wings) = Construction work is same as last visit dtd. 08/02/2025. 2. We considered Saleable area as per builder area statement sheet. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. Since the project has received first CC on 11/07/2018., But construction work of Building No. 3 & 4 is under construction. 8. On site, we meet Miss. Archita : 9892747917.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Sudarshan Garden Phase II
Google Map :
3 (A & B Wing)
4 (A, B & C Wing)

## Construction % Blg 3
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 5 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 0.2 | 0 | Progress |  |  | 10 | 2 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 1.5 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 2 | 1.5
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 12 | 31.5

## Construction %Blg 4
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## Note
2021-01-06 | Pratiksha | OLD APF

## Valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Housing | Sudarshan Garden Phase II | 1BHK | 265 | 418.7 | 2393.1216 | 1002000
Housing | Sudarshan Garden Phase II | 1BHK | 273 | 431.34 | 2392.5442 | 1032000
Housing | Sudarshan Garden Phase II | 1BHK | 293 | 462.94 | 2393.3987 | 1108000
Housing | Sudarshan Garden Phase II | 2BHK | 432 | 682.56 | 2392.4637 | 1633000
Average |  |  |  |  | 2392.882
Valuation Adopted |  |  |  |  | 2400

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0