## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-11
Name of the builder group |  |  |  | Vihang Enterprises
Name of the builder company |  |  |  | Vihang Enterprises
Name of the Project |  |  |  | Vihang Woods
Provided Contact Details (Name & Contact No.) |  |  |  | 8424964646
Site Person - Contact Details (Name & Contact No.) |  |  |  | Security
Name / No of the Building |  |  |  | Building B, C & D
Name / No of the Existing Building |  |  |  | NA
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700005038
Project location details |  | Vihang Woods, Survey No.91/1/1A, 91/1/2B, 91/1/3C, 91/2A, 91/2B, 91/2C, 102/1, 102/2A, 102/2B, 102/2C, 102/3A, 102/3B, 103/1, 103/2, 103/3A, 103/3B, 103/4103/5B/1, 103/5B/2, 104/7A, 104/7B, 104/7C, 104/8A, 104/8B, 104/8C, 104/11A, 104/11B, 104/11C,109/29A, 109/29B, 109/29C, 109/29D, 109/30/1A, 109/30/1B, 109/30/4A, 109/30/4B, 109/33, 109/34, 104/8D, 91/2D, 99/1, 99/2A, 99/2B, 100/30B, 100/30B & 100/30C, near Godrej Emerald, Bhatti Road, Gaimukh Gaon, Bhayandarpada, Thane West, Thane, Thane - 400615.
Survey No |  | 91/1/1A, 91/1/2B, 91/1/3C, 91/2A, 91/2B, 91/2C, 102/1, 102/2A, 102/2B, 102/2C, 102/3A, 102/3B, 103/1, 103/2, 103/3A, 103/3B, 103/4103/5B/1, 103/5B/2, 104/7A, 104/7B, 104/7C, 104/8A, 104/8B, 104/8C, 104/11A, 104/11B, 104/11C,109/29A, 109/29B, 109/29C, 109/29D, 109/30/1A, 109/30/1B, 109/30/4A, 109/30/4B, 109/33, 109/34, 104/8D, 91/2D, 99/1, 99/2A, 99/2B, 100/30B, 100/30B & 100/30C
Locality |  | Gaimukh Gaon
Road |  | Bhatti Road |  | Locality/Village |  | Bhayandarpada
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400615
Nearby Landmark |  | Godrej Emerald |  | Distance from city centre: |  | 13.3 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Building
West | NA | 40.00 M Wide D.P Road |  |  | Bhatti Road
North | NA | Wing E |  |  | Open Plot
South | NA | S.No. 103/3/A/2 /Amenity Plot |  |  | Godrej Emerald
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.282965,72.950859
Location Link |  | https://goo.gl/maps/fq6jACa9SZR4Vnbu6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 41431.52
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.9923
Total FSI availaible for the project |  |  |  | 3.0923
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 128119.91
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation
Layout Approval No |  | S06/0084/10/TMC/TD-DP/TPS 4447/23 |  |  | Dated | 21/07/2023.
Approved Floor plan No. (Wing C & D) |  | S06/0084/10/TMC/TD-DP/TPS 4447/23 |  |  | Dated | 21/07/2023.
Commencement-CC No (Wing C & D) Valid Up to: |  | S06/0084/10/TMC/TDD 4447/23 |  |  | Dated | 21/07/2023.
Building C & D = LG + UG + 1st to 31st Floor
Approved Floor plan No. (Wing B) |  | S06/0084/10/TMC/TD-DP/TPS/ 4114/22 |  |  | Dated | 01/07/2022.
Commencement-CC No (Wing B) Valid Up to: |  | S06/0084/10/TMC/TDD/TPS/4114/ 22 |  |  | Dated | 01/07/2022.
Building Type B = LG + UG + 1st to 30th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Builtup Area of Building (Sq.Mt) |  |  | 22868.97 |  |  |  |  | 9556.08+5735.31+7577.58
Approved no of units |  |  | Sale Flats = 456, Mhada Flat = 249, Shop = 14
Approved no of Floors |  |  | Building B = Lower Gr + Upper Gr + 1st to 30th Floor Building C & D = Lower Gr + Upper Gr + 1st to 31st Floor
Proposed no of Floor |  |  | Building B = Lower Gr + Upper Gr + 1st to 30th Floor
Building C = Lower Gr + Upper Gr + 1st to 31st Floor
Building D = Lower Gr + Upper Gr + 1st to 31st Floor
Expected Completion |  |  | As per RERA - 30/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Center, Creche, Lift of reputed Brand, CCTV surveillance, Fire Rated Main Road, Fire Fighting system, Power backup in common araes, Rain water Harvesting, Parking etc. |  |  |  |  | http://vihangwoods.a2zproperty.in/
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building B = Lower Gr + Upper Gr + 1st to 30th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 25 Floor, Flooring upto 18 Floor, Painting upto 8 Floor Completed | , External Plaster upto 25 Floor, Flooring upto 18 Floor, Painting upto 8 Floor
Basement | 0 | Ground | 2 | Podium | 0 | Floors | 30 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 25 Floor, Flooring upto 18 Floor, Painting upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.5
Excavation |  | 30 | 100% | 80.67% |  | 92.17% |  | Excavation in process | 15
Plinth |  | 30 | 100% |  |  |  |  | Excavation Completed | 30
RCC (Including podiums) |  | 32 | 100% |  |  |  |  | Footing in Process | 7.5
Brickwork | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Footing Completed | 15
Internal Plaster | Brickwork & Internal Plaster | 30 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 25 | 83.33% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 60% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 26.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 22.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 30
Construction details: |  | Building C = Lower Gr + Upper Gr + 1st to 31st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 28 Slab, Brickwork upto 21 Floor Completed | , RCC upto 28 Slab, Brickwork upto 21 Floor
Basement | 0 | Ground | 2 | Podium | 0 | Floors | 31 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 28 Slab, Brickwork upto 21 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.75
Excavation |  | 31 | 100% | 49.02% |  | 73.84% |  | Excavation in process | 15.5
Plinth |  | 31 | 100% |  |  |  |  | Excavation Completed | 31
RCC (Including podiums) |  | 28 | 84.85% |  |  |  |  | Footing in Process | 7.75
Brickwork | Brickwork & Internal Plaster | 21 | 67.74% |  |  |  |  | Footing Completed | 15.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0 |  | Note- We considered C Wing as Part II of D wing which was changed on Date 19/05/2025
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 23.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 31
Construction details: |  | Building D = Lower Gr + Upper Gr + 1st to 31st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 28 Slab, Brickwork upto 21 Floor Completed | , RCC upto 28 Slab, Brickwork upto 21 Floor
Basement | 0 | Ground | 2 | Podium | 0 | Floors | 31 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 28 Slab, Brickwork upto 21 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.75
Excavation |  | 31 | 100% | 49.02% |  | 73.84% |  | Excavation in process | 15.5
Plinth |  | 31 | 100% |  |  |  |  | Excavation Completed | 31
RCC (Including podiums) |  | 28 | 84.85% |  |  |  |  | Footing in Process | 7.75
Brickwork | Brickwork & Internal Plaster | 21 | 67.74% |  |  |  |  | Footing Completed | 15.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 23.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 31
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 8500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 16000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 6800
Commercial Area Details (Sale) : Shops
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building D |  | 14 |  | 4505.7028 |  | 6983.8393
Total |  | 14 |  | 4505.7028 |  | 6983.8393
Residential Area Details (Sale) : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building B |  | 7 |  | 2395.061 |  | 3592.5916
Building C |  | 214 |  | 96463.7388 |  | 144695.6082
Building D |  | 235 |  | 127466.104 |  | 191199.1559
Total |  | 456 |  | 226324.9038 |  | 339487.3557
Residential Area Details (Mhada) : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building B |  | 231 |  | 79238.1742 |  | 118857.2613
Building C |  | 18 |  | 6653.4437 |  | 9980.1655
Total |  | 249 |  | 85891.6179 |  | 128837.4268
Grand Total |  | 719 |  | 316722.2244 |  | 475308.6218
Details of Residential & Commercials in Building | [7 empty] | 10.764
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building D
Lower Ground Floor For Commercial, Entrance Lobby, Meter Room, Panel Room & Parking Area
1 |  | Shop | 136.1646 | 0 | 211.0551 | Lower Ground Floor For Commercial, Entrance Lobby, Meter Room, Panel Room & Parking Area
2 |  | Shop | 193.6444 | 0 | 300.1488
3 |  | Shop | 171.9011 | 0 | 266.4467
4 |  | Shop | 224.9676 | 0 | 348.6998
5 |  | Shop | 224.7523 | 0 | 348.3661
6 |  | Shop | 164.151 | 0 | 254.434
7 |  | Shop | 202.5785 | 0 | 313.9966 | [8 empty] | 10067.3636
8 |  | Shop | 224.9676 | 0 | 348.6998 | [6 empty] | 56.4757
9 |  | Shop | 171.9011 | 0 | 266.4467 | [6 empty] | 5.0935 | 61.5692
10 |  | Shop | 193.6444 | 0 | 300.1488 | [6 empty] | 2.1 |  | 10472.519
11 |  | Shop | 128.0916 | 0 | 198.542
12 |  | Shop | 206.3459 | 0 | 319.8361
13 |  | Shop | 1373.917 | 0 | 2129.5713
14 |  | Shop | 888.6758 | 0 | 1377.4476
15661.0227
Flat No. (Approved Plan) | Mhada/ Sale | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor | [7 empty] | 10023.1853
[5 empty] | 50% | [6 empty] | 56.4757
Building Type B | [11 empty] | 5.0935 | 61.5692
Lower Ground Floor For Meter Room, LV Panel Room, Entrance Lobby & Parking Area | [11 empty] | 2.1 |  | 10260.6701
Upper Ground Floor For Residential, Entrance Lobby & Parking Area
1 | Sale | 1BHK | 362.8544 | 0 | 544.2817 | Upper Ground Floor For Residential, Entrance Lobby & Parking Area
2 | Sale | 1BHK | 314.5478 | 0 | 471.8216
3 | Entrance Lobby / Parking Area
4 | Sale | 1BHK | 362.8544 | 0 | 544.2817
5 | Sale | 1BHK | 362.8544 | 0 | 544.2817
6 | Sale | 1BHK | 314.5478 | 0 | 471.8216
7 | Sale | 1BHK | 314.5478 | 0 | 471.8216
8 | Sale | 1BHK | 362.8544 | 0 | 544.2817
1st to 6th, 8th to 10th, 12th to 15th, 17th to 20th, 22nd to 23rd & 24th Floor For Residential
1 | Mhada | 1BHK | 370.3462 | 0 | 555.5193 | 1st to 6th, 8th to 10th, 12th to 15th, 17th to 20th, 22nd to 23rd & 24th Floor For Residential
2 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
3 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
4 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
5 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
6 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
7 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
8 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
7th, 11th, 16th & 21st Floor (Part Refuge Area)
1 | Refuge Area |  |  |  |  | 7th, 11th, 16th & 21st Floor (Part Refuge Area)
2
3 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
4 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
5 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
6 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
7 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
8 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
25th, 27th to 30th Floor
1 | Mhada | 1BHK | 370.3462 | 0 | 555.5193 | 25th, 27th to 30th Floor
2 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
3 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
4 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
5 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
6 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
7 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
8 | Mhada | 1BHK | 370.3462 | 0 | 555.5193 | [5 empty] | 8760.0902
26th Floor (Part Refuge Area) | [10 empty] | 9222.2731
1 | Refuge Area |  |  |  |  | 26th Floor (Part Refuge Area)
2 | Mhada | 1BHK | 315.9342 | 0 | 473.9012 |  |  |  |  | 61.5692
3 | Mhada | 1BHK | 315.9342 | 0 | 473.9012 | [5 empty] | 8987.4902
4 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
5 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
6 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
7 | Mhada | 1BHK | 315.9342 | 0 | 473.9012
8 | Mhada | 1BHK | 370.3462 | 0 | 555.5193
Building Type C
Lower Ground Floor For Meter Room, LV Panel Room, Entrance Lobby & Parking Area
Upper Ground Floor For Entrance Lobby, Society Office, Fitness Center, Creche, Drivers Room & Parking Area
1st to 6th, 8th to 10th, 12th to 15th & 17th Floor For Residential
1 | Sale | 2BHK | 662.0936 | 0 | 993.1405 | 1st to 6th, 8th to 10th, 12th to 15th & 17th Floor For Residential
2 | Sale | 1BHK | 343.3716 | 0 | 515.0574
3 | Sale | 1BHK | 343.0487 | 0 | 514.573 |  |  |  | 56.4757
4 | Sale | 2BHK | 662.0936 | 0 | 993.1405 |  |  |  | 5.0935
5 | Sale | 1BHK | 422.8099 | 0 | 634.2149 |  |  |  | 2.1
6 | Sale | 1BHK | 342.941 | 0 | 514.4116
7 | Sale | 1BHK | 342.6181 | 0 | 513.9272
8 | Sale | 1BHK | 423.0252 | 0 | 634.5378
7th, 11th & 16th Part Refuge Area
1 | Sale | 2BHK | 662.0936 | 0 | 993.1405 | 7th, 11th & 16th Part Refuge Area
2 | Sale | 1BHK | 343.3716 | 0 | 515.0574
3 | Sale | 1BHK | 343.0487 | 0 | 514.573
4 | Sale | 2BHK | 662.0936 | 0 | 993.1405
5 | Refuge Area
6
7 | Sale | 1BHK | 342.6181 | 0 | 513.9272
8 | Sale | 1BHK | 423.0252 | 0 | 634.5378
18th to 20th Floor
1 | Sale | 2BHK | 662.0936 | 0 | 993.1405 | 18th to 20th Floor
2 | Mhada | 1BHK | 343.3716 | 0 | 515.0574
3 | Mhada | 1BHK | 343.0487 | 0 | 514.573
4 | Sale | 2BHK | 662.0936 | 0 | 993.1405
5 | Mhada | 1BHK | 422.8099 | 0 | 634.2149
6 | Mhada | 1BHK | 342.941 | 0 | 514.4116
7 | Mhada | 1BHK | 342.6181 | 0 | 513.9272
8 | Mhada | 1BHK | 423.0252 | 0 | 634.5378
22nd to 25th, 27th to 30th Floor
1 | Sale | 2BHK | 662.0936 | 0 | 993.1405 | 22nd to 25th, 27th to 30th Floor
2 | Sale | 1BHK | 343.3716 | 0 | 515.0574
3 | Sale | 1BHK | 343.0487 | 0 | 514.573
4 | Sale | 2BHK | 662.0936 | 0 | 993.1405
5 | Sale | 1BHK | 422.8099 | 0 | 634.2149
6 | Sale | 1BHK | 342.941 | 0 | 514.4116
7 | Sale | 1BHK | 342.6181 | 0 | 513.9272
8 | Sale | 1BHK | 423.0252 | 0 | 634.5378
21st & 26th Floor ( Part Refuge Area )
1 | Sale | 2BHK | 662.0936 | 0 | 993.1405 | 21st & 26th Floor ( Part Refuge Area )
2 | Sale | 1BHK | 343.3716 | 0 | 515.0574
3 | Sale | 1BHK | 343.0487 | 0 | 514.573
4 | Sale | 2BHK | 662.0936 | 0 | 993.1405
5 | Refuge Area
6 | Sale | 1BHK | 342.941 | 0 | 514.4116
7 | Sale | 1BHK | 342.6181 | 0 | 513.9272
8 | Sale | 1BHK | 423.0252 | 0 | 634.5378
31st Floor (Part Recreational & Refuge Area )
Building D
Upper Ground Floor For Residential ( Part Entrance Lobby, Creche & Parking Area )
1 | Parking Area |  |  |  |  | Upper Ground Floor For Residential ( Part Entrance Lobby, Creche & Parking Area )
2 | Entrance Lobby & Creche
3 | Entrance Lobby
4 | Sale | 2BHK | 659.7256 | 0 | 989.5883
5 | Sale | 1BHK | 420.8724 | 0 | 631.3086
6 | Sale | 1BHK | 657.4651 | 0 | 986.1977
7 | Parking Area
8
1st to 6th, 8th to 10th, 12th to 15th Floor
1 | Sale | 2BHK | 661.1249 | 0 | 991.6873 | 1st to 6th, 8th to 10th, 12th to 15th Floor
2 | Sale | 1BHK | 422.8099 | 0 | 634.2149
3 | Sale | 1BHK | 423.0252 | 0 | 634.5378
4 | Sale | 2BHK | 659.7256 | 0 | 989.5883
5 | Sale | 1BHK | 420.8724 | 0 | 631.3086
6 | Sale | 2BHK | 659.7256 | 0 | 989.5883
7 | Sale | 2BHK | 659.7256 | 0 | 989.5883
8 | Sale | 1BHK | 420.8724 | 0 | 631.3086
7th, 11th & 16th Floor ( Part Refuge Area )
1 | Refuge Area |  |  |  |  | 7th, 11th & 16th Floor ( Part Refuge Area )
2
3 | Sale | 1BHK | 423.0252 | 0 | 634.5378
4 | Sale | 2BHK | 659.7256 | 0 | 989.5883
5 | Sale | 1BHK | 420.8724 | 0 | 631.3086
6 | Sale | 2BHK | 659.4026 | 0 | 989.104
7 | Sale | 2BHK | 659.4026 | 0 | 989.104
8 | Sale | 1BHK | 420.8724 | 0 | 631.3086
17th Floor
1 | Sale | 2BHK | 661.1249 | 0 | 991.6873 | 17th Floor
2 | Sale | 1BHK | 422.8099 | 0 | 634.2149
3 | Sale | 1BHK | 423.0252 | 0 | 634.5378
4 | Sale | 2BHK | 659.7256 | 0 | 989.5883
5 | Sale | 1BHK | 420.8724 | 0 | 631.3086
6 | Sale | 2BHK | 659.4026 | 0 | 989.104
7 | Sale | 2BHK | 659.4026 | 0 | 989.104
8 | Sale | 1BHK | 420.8724 | 0 | 631.3086
18th to 20th, 22nd to 25th, 27th to 30th Floor
1 | Sale | 2BHK | 661.1249 | 0 | 991.6873 | 18th to 20th, 22nd to 25th, 27th to 30th Floor
2 | Sale | 1BHK | 422.8099 | 0 | 634.2149
3 | Sale | 1BHK | 423.0252 | 0 | 634.5378
4 | Sale | 2BHK | 659.7256 | 0 | 989.5883
5 | Sale | 1BHK | 420.8724 | 0 | 631.3086
6 | Sale | 2BHK | 659.4026 | 0 | 989.104
7 | Sale | 2BHK | 659.4026 | 0 | 989.104
8 | Sale | 1BHK | 420.8724 | 0 | 631.3086
21st & 26th Floor ( Part Refuge Area )
1 | Sale | 2BHK | 661.1249 | 0 | 991.6873 | 21st & 26th Floor ( Part Refuge Area )
2 | Sale | Refuge Area
3 | Sale | 1BHK | 423.0252 | 0 | 634.5378
4 | Sale | 2BHK | 659.7256 | 0 | 989.5883
5 | Sale | 1BHK | 420.8724 | 0 | 631.3086
6 | Sale | 2BHK | 659.4026 | 0 | 989.104
7 | Sale | 2BHK | 659.4026 | 0 | 989.104
8 | Sale | 1BHK | 420.8724 | 0 | 631.3086
31st Floor (Part Recreational & Refuge Area )
Remarks:
* | Construction work is in process at the time of Visit.(Internal Photo was not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area + Enclosed Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have considered flat numbering as per Sale Plan in type B building.
* | We have updated approved plans for Building Type B (On 08/08/2024).
* | Only Upper ground Floor flats are for Sale in Building Type B.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vihang Woods
w
Layout :
Google Map :
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Building C
Building D
Building C
Building D
Building B
Building B
Building C
Building D
Part I
Part II
Building D
Building B
Building C
Part I
Part II
Building B
Building C
Building D

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted