## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 25/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-08-11 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Prestige Mulund Realty Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Prestige Mulund Realty Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Siesta | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Miss. Sayali 9359530990
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Sayali (CRM) : 9359530990
Name / No of the Building |  |  |  | Sector V - Building No.4 (Wing A & B)
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800005285 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Siesta, CTS No.19/1 to 19/13, near Yogi Hills CHS, Agrawal Road, Veena Nagar, Mulund, Mulund West, Andheri, Mumbai - 400080. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 19/1 to 19/13 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Veena Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Agrawal Road |  | Locality/Village |  | Mulund | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Mulund West |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Andheri |  | Pin Code |  | 400080 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Yogi Hills CHS |  | Distance from city centre: |  | 2.7 KM from Mulund Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | 27.45 M Wide D.P Road |  |  | Agarwal Road
West | NA | Bellenza |  |  | Bellenza
North | NA | Open Plot |  |  | Gobind Udyog Bhawan Industrial Estate / Internal Road
South | NA | Agarwal Holding |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.184000,72.942556
Location Link |  | https://maps.app.goo.gl/8nDPh7LfE4y59DJv9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | Not Provided | [5 empty] | 0
Permissible FSI |  |  |  | NA | [5 empty] | 0
Permissible TDR/Paid FSI |  |  |  | NA | [5 empty] | #DIV/0!
Total FSI availaible for the project |  |  |  | NA | [5 empty] | #DIV/0!
Total Approved Builtup area of the Building No.4 (Sq.Mt) |  |  |  | 42290.75 | [5 empty] | 0
Total number of Buildings |  |  |  | 02 Wings | [5 empty] | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Not Provided |  |  | Dated | NA | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | SRA/DDTP/0524/T/PL/AP |  |  | Dated | 2022-11-21 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | SRA/DDTP/0524/T/PL/AP |  |  | Dated | 2022-11-21 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This further CC is re -endorsed as per approved approved amended plans dated 21/11/2022. | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | This further CC is re -endorsed as per approved approved amended plans dated 21/11/2022. |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | SRA/DDTP/0524/T/PL/AP Approved upto : Building No.4 (Wing A & B) = Gr/St + 1st to 54th Floor |  |  | Dated | 2025-04-30 | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 42290.75
Approved no of units |  |  | Flats - 462
Approved no of Floors |  |  | Wing A & B = B + Gr + P1 to P9 + 10th & 11th Eco-Deck + 12th Service Floor + 13th to 54th Floor
Proposed no of Floors |  |  | Wing A & B = B + Gr + P1 to P9 + 10th & 11th Eco-Deck + 12th Service Floor + 13th to 54th Floor
Expected Completion |  |  | Completed
Projected life of the structure |  |  | 60 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Jogging Track, Cafeteria, Entrance Lobby, Card Room, Party Lawn, Cigar Lounge, Chess Board, Billiards/Snooker Table, Amphitheater, Sewage Treatment Plant, 24X7 Water Supply, Fire Fighting System, Water Conservation, Rain water Harvesting, Car Parking, Club House, Indoor Games, Children's Play Area, Spa/Sauna/Steam, Storm Water Drains, Solid Waste Management And Disposal, Landscaping & Tree Planting Energy management, Meter Room, Staff Quarter, Maintenance Staff, Squash Court, 24x7 Security, Gymnasium, Power Backup, Lift(s), Swimming Pool etc. |  |  |  |  | https://housing.com/in/buy/projects/page/5626-prestige-siesta-by-prestige-groups-in-mulund-west
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Wing A & B = B + Gr + P1 to P9 + 10th & 11th Eco-Deck + 12th Service Floor + 13th to 54th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 54 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 13.5
Excavation |  | 54 | 100% | 100% |  | 100% |  | Excavation in process | 27
Plinth |  | 54 | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 55 | 100% |  |  |  |  | Footing in Process | 13.5
Brickwork | Brickwork & Internal Plaster | 54 | 100% |  |  |  |  | Footing Completed | 27
Internal Plaster | Brickwork & Internal Plaster | 54 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 54 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 54 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 54 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 54 | 100% |  |  |  |  | Plinth in process | 40.5
Possession |  | 54 | 100% |  |  |  |  | Plinth completed | 54
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 17000 |  |  |  |  | 13500 08/02/2024 sanjay sir | [6 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. | [16 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from 12th Floor |  |  |  |  | 100 | [11 empty] | 1100000 | 500000 | 250000 | 250000
LUC Charges |  |  |  |  | 512000 | [11 empty] | 1200000 | 600000 | 300000 | 300000
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 75000 | [11 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 800000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 13600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 4 | Wing A | 231 |  | 287469.7143 |  | 431204.5715
| Wing B | 231 |  | 287277.7491 |  | 430916.6237
Total |  | 462 |  | 574747.4634 |  | 862121.1952
Grand Total |  | 462 |  | 574747.4634 |  | 862121.1952
Building details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area + Enclosed Balcony | ELEV. Proj. | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Sector V- Building No. 4
Wing A
Basement Floor For Parking
Ground Floor For Parking & Meter Room
1st Podium Floor For Parking
2nd to 9th Podium Floor For Parking
10th E-Level Lower Level Floor For Indoor Swimming Pool, Jaccuzi, Library, Clubhouse, Kids Play Area & Wellness Facility
11th E-Level Upper Level Floor For Activity Area, Gymnasium, Multipurpose Hall, Lounge, Garden
Tranfer Girder Floor Inbetween 11th E-Level Floor & 12th Service Floor
12th Floor For Service Floor
13th, 15th, 17th, 19th, 23rd, 25th, 27th, 29th, 31st, 33rd, 36th, 38th, 40th, 44th, 46th, 48th, 50th Floor For Residential
1 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224 |  |  | 13489.1852
2 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
3 |  | 2.5BHK | 866.7496 | 385.1897 | 1251.9393 | 0 | 1877.909
4 |  | 2.5BHK | 866.7496 | 456.1998 | 1322.9494 | 0 | 1984.4241
5 |  | 2.5BHK | 971.6286 | 377.9025 | 1349.5311 | 0 | 2024.2967
6 |  | 2.5BHK | 971.6286 | 494.0138 | 1465.6424 | 0 | 2198.4636
16th, 18th, 20th, 22nd, 24th, 26th, 30th, 32nd, 34th, 37th, 39th, 41st, 43rd, 45th, 47th & 51st Floor
1 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
2 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
3 |  | 2.5BHK | 865.8293 | 447.0182 | 1312.8474 | 0 | 1969.2711
4 |  | 2.5BHK | 865.8293 | 379.3449 | 1245.1741 | 0 | 1867.7612
5 |  | 2.5BHK | 971.6286 | 497.0492 | 1468.6778 | 0 | 2203.0168
6 |  | 2.5BHK | 971.6286 | 424.6936 | 1396.3222 | 0 | 2094.4833
Fire Check Floor Inbetween 18th & 19th Floor & 37th & 38th
35th Floor For Part Refuge Area & Service Area
14th, 28th & 49th Floor (Part Refuge Area)
1 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
2 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
3 |  | 2.5BHK | 866.7496 | 447.0182 | 1313.7677 | 0 | 1970.6516
4 |  | 2.5BHK | 866.7496 | 379.3449 | 1246.0945 | 0 | 1869.1417
5 |  | 2.5BHK | 971.6286 | 497.0492 | 1468.6778 | 0 | 2203.0168
6 |  | Refuge Area
21st & 42th Floor (Part Refuge Area)
1 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
2 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
3 |  | 2.5BHK | 866.7496 | 385.1897 | 1251.9393 | 0 | 1877.909
4 |  | 2.5BHK | 866.7496 | 456.1998 | 1322.9494 | 0 | 1984.4241
5 |  | 2.5BHK | 971.6286 | 377.9025 | 1349.5311 | 0 | 2024.2967
6 |  | Refuge Area
52nd Floor
1 |  | 2BHK | 719.1891 | 218.0786 | 937.2678 | 0 | 1405.9016
2 |  | 2BHK | 719.1891 | 218.0786 | 937.2678 | 0 | 1405.9016
3 |  | 8BHK + MP Room Triplex With 53rd & 54th Floor | 4190.9634 | 1589.197 | 5780.1604 | 0 | 8670.2405 | 386.1122 | 34.204 | 351.9082 | 354.93
4 |  | 8BHK + MP Room Triplex With 53rd & 54th Floor | 4586.1744 | 1734.8339 | 6321.0083 | 0 | 9481.5125 | 425.908 | 32.196 | 393.712
53rd Floor
1 |  | 2BHK | 719.1891 | 229.1117 | 948.3009 | 0 | 1422.4513
2 |  | 2BHK | 719.1891 | 229.1117 | 948.3009 | 0 | 1422.4513
3 |  | Triplex With 52nd & 54th Floor
4 |  | Triplex With 52nd & 54th Floor
54th Floor
1 |  | 2BHK | 719.1891 | 218.0786 | 937.2678 | 0 | 1405.9016
2 |  | 2BHK | 719.1891 | 218.0786 | 937.2678 | 0 | 1405.9016
3 |  | Triplex With 52nd & 53rd Floor
4 |  | Triplex With 52nd & 53rd Floor
Wing B
Basement Floor For Parking
Ground Floor For Parking & Meter Room
1st Podium Floor For Parking
2nd to 9th Podium Floor For Parking
10th E-Level Lower Level Floor For Indoor Swimming Pool, Jaccuzi, Library, Clubhouse, Kids Play Area & Wellness Facility
11th E-Level Upper Level Floor For Activity Area, Gymnasium, Multipurpose Hall, Lounge, Garden
Tranfer Girder Floor Inbetween 11th E- Level Floor & 12th Service Floor
12th Floor For Service Floor
13th, 15th, 17th, 19th, 23rd, 25th, 27th, 29th, 31st, 33rd, 36th, 38th, 40th, 44th, 46th, 48th, 50th Floor For Residential
1 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
2 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
3 |  | 2.5BHK | 866.7496 | 379.3449 | 1246.0945 | 0 | 1869.1417
4 |  | 2.5BHK | 866.7496 | 447.0182 | 1313.7677 | 0 | 1970.6516
5 |  | 2.5BHK | 971.6286 | 424.6936 | 1396.3222 | 0 | 2094.4833
6 |  | 2.5BHK | 971.6286 | 497.0492 | 1468.6778 | 0 | 2203.0168
16th, 18th, 20th, 22nd, 24th, 26th, 30th, 32nd, 34th, 37th, 39th, 41st, 43rd, 45th, 47th & 51st Floor
1 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
2 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
3 |  | 2.5BHK | 865.8293 | 456.1998 | 1322.0291 | 0 | 1983.0436
4 |  | 2.5BHK | 865.8293 | 385.1897 | 1251.019 | 0 | 1876.5285
5 |  | 2.5BHK | 971.6286 | 494.0138 | 1465.6424 | 0 | 2198.4636
6 |  | 2.5BHK | 971.6286 | 377.9025 | 1349.5311 | 0 | 2024.2967
Fire Check Floor Inbetween 18th & 19th Floor & 37th & 38th
35th Floor For Part Refuge Area & Service Area
14th, 28th & 49th Floor (Part Refuge Area)
1 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
2 |  | 2BHK | 716.8641 | 217.2175 | 934.0816 | 0 | 1401.1224
3 |  | 2.5BHK | 866.7496 | 385.1897 | 1251.9393 | 0 | 1877.909
4 |  | 2.5BHK | 866.7496 | 456.1998 | 1322.9494 | 0 | 1984.4241
5 |  | 2.5BHK | 971.6286 | 377.9025 | 1349.5311 | 0 | 2024.2967
6 |  | Refuge Area
21st & 42th Floor (Part Refuge Area)
1 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
2 |  | 2BHK | 716.8641 | 227.7124 | 944.5765 | 0 | 1416.8648
3 |  | 2.5BHK | 866.7496 | 379.3449 | 1246.0945 | 0 | 1869.1417
4 |  | 2.5BHK | 866.7496 | 447.0182 | 1313.7677 | 0 | 1970.6516
5 |  | 2.5BHK | 971.6286 | 424.6936 | 1396.3222 | 0 | 2094.4833
6 |  | Refuge Area
52nd Floor
1 |  | 2BHK | 719.1891 | 229.1117 | 948.3009 | 0 | 1422.4513
2 |  | 2BHK | 719.1891 | 229.1117 | 948.3009 | 0 | 1422.4513
3 |  | 8BHK + MP Room Triplex With 53rd & 54th Floor | 4190.9634 | 1589.197 | 5780.1604 | 0 | 8670.2405
4 |  | 8BHK + MP Room Triplex With 53rd & 54th Floor | 4586.1744 | 1734.8339 | 6321.0083 | 0 | 9481.5125
53rd Floor
1 |  | 2BHK | 719.1891 | 218.0786 | 937.2678 | 0 | 1405.9016
2 |  | 2BHK | 719.1891 | 218.0786 | 937.2678 | 0 | 1405.9016
3 |  | Triplex With 52nd & 54th Floor
4 |  | Triplex With 52nd & 54th Floor
54th Floor
1 |  | 2BHK | 719.1891 | 229.1117 | 948.3009 | 0 | 1422.4513
2 |  | 2BHK | 719.1891 | 229.1117 | 948.3009 | 0 | 1422.4513
3 |  | Triplex With 52nd & 53rd Floor
4 |  | Triplex With 52nd & 53rd Floor
Remarks:
* | All work Completed. OC Received. OC for Basement floor is pending.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose Balcony + ELEV. Proj.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Since Project's Builtup Area is above 20000 Sq.M. Please check for Environment Clearance Certificate.
* | Please provide Area statement sheet.
* | We have updated OC (On 25/09/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nainesh Tambe |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Siesta
Layout :
Google Map :
Formulas:
Mulund = [Mulund, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F106: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H136: SACHIN: Give loading of 50% for A Category
Wing A
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate