## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 20/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-19
Name of the builder group |  |  |  |  | M/s. Nirvana Leisure Realty
Name of the builder company |  |  |  |  | M/s. Nirvana Leisure Realty
Name of the Project |  |  |  |  | City of Music
Contect Details ( Name & Contect No.) |  |  |  |  | 8208930283 & Anita- 8591302669
Name / no of the Building |  |  |  |  | Villa/Plot no. 01, 10, 16, 17, 19A, 23A, 24A, 24B, 25, 27A, 27B 30A, 30B, 31, 32B, 36, 38B, 44, 45, 47, 48, 49 52, 58, 61, 62, 63, 64, 66, 72, 75, 76 81, 84, 86, 87, 89, 91, 92, 93, 94, 96 101, 102, 108, 109, 110, 111,112, 114, 118, 119, 120 121A, 122 (A & B), 125B, 126B, 127, 128
Docouments Provided |  |  |  |  | Approved Layout & NA order (By District Collector of Raigad) Building/Villa Floor Plan & CC Approved by Grampanchayat, Chive, Tal. Sudhagad, Dist. Raigad.
RERA No. |  |  |  |  | City of Music Phase II = P52000016821 - Plot No. 01, 58, 61, 62, 63, 64, 66, 81, 84, 86, 87, 89, 91, 92, 93, 94, 96, 101, 102 City of Music Phase III = P52000027911- Plot No. 01, 10, 16, 17, 19A, 23A, 24A, 24B, 25, 27A, 27B, 30A, 30B, 31, 32B, 36, 38B, 44, 45, 47, 48, 49, 52, 76, 108, 109, 110, 111,112, 114, 118, 119, 120, 121A, 122 (A & B), 125B, 128 Not registered on RERA = Plot No.126B | [7 empty] | City of Music Phase IV = P52000050052
Project location details |  | City of Music Phase II & Phase III, On Gat No. 70/1A, 70/1B, 73/1A, 73/4, 73/5A, 75/1B, 75/1A/1, 75/1A/2, 78/1A, 78/1B, 76/1, 76/2 of Village - Bhilpada, Bhilpada Khopoli Road, Khopoli-Pali National Highway, Opp Lake City, Pali, Tal -Sudhagad, Dist -Raigad- 410205.
Gut. No |  | 70/1A, 70/1B, 73/1A, 73/1B, 73/4, 73/5A, 75/1A/1, 75/1A/2, 75/1B, 78/1A, 78/1B, 76/1, 76/2 |  |  | Locality |  | Bhilpada (khuravale)
Road |  | Khopoli Pali Road |  |  | District |  | Raigad
Taluka |  | Sudhagad |  |  | Pin Code |  | 410205
Near by Landmark |  | Lake City Apratim Group |  |  | Distance from city centre: |  | About 7 Km from Pali Bus Stand
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 5 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Khopoli to Pali Road |  | River |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 18.5858931,73.2532133
Location Link |  | https://goo.gl/maps/oVmqb6v4ryeNTcUi9
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Approval details:
Total Land Area under Layout as Per 7/12 = 80950 Sq.Mt.
Land Area under Plots (1 to 130) = 39692 Sq.Mt.
Building/Villa Floor Plan-Approved by Grampanchayat of Chive, Tal. Sudhagad, Dist. Raigad.
Plot No. | Total land area of the plot in Sq. Mt |  | Permissible FAR |  | Permissible TDR/Paid FAR | Total FAR availaible | Total Approved Builtup area of the Villa in Sq. Mt.
1 | 191.9361 |  | 0.4 |  | 0 | 0.4 | 76.99 |  | 191.9361 | 2066
2 | 191.9361 | [8 empty] | 2066
3 | 191.9361 | [8 empty] | 2066
4 | 191.9361 | [8 empty] | 2066
5 | 191.9361 | [8 empty] | 2066
6 | 191.9361 | [8 empty] | 2066
7 | 191.9361 | [8 empty] | 2066
8 | 224.9164 | [8 empty] | 2066
9 | 183.9465 | [8 empty] | 2066
10 | 183.9465 |  | 0.36 |  | 0 | 0.36 | 78.56 |  |  | 2066
11 | 184.9684 | [8 empty] | 2066
12 | 192.958 | [8 empty] | 2066
13 | 192.958 | [8 empty] | 2066
14 | 193.887 | [8 empty] | 2066
15 | 193.887 | [8 empty] | 2066
16 | 193.887 |  | 0.527 |  | 0 | 0.527 | 101.19
17 | 194.909 |  | 0.6 |  | 0 | 0.6 | 120
18 | 338.9075
19A | 100.4738 |  | 0.35 |  | 0 | 0.35 | 89.23
19B | 100.4738
20A | 100.4738
20B | 100.4738
21A | 113.4801
21B | 113.4801
22 | 222.7796
23A | 106.466 |  | 0.17 |  | 0 | 0.17 | 36.76
23B | 106.466
24A | 101.4493 |  | 0.3 |  | 0 | 0.3 | 61.66
24B | 101.4493 |  | 0.29 |  | 0 | 0.29 | 59.3
25 | 193.7941 |  | 0.47 |  | 0 | 0.47 | 91.26
26A | 96.9435
26B | 96.9435
27A | 96.479 |  | 0.2 |  | 0 | 0.2 | 193
27B | 96.479 |  | 0.35 |  | 0 | 0.35 | 193
28 | 192.958
29 | 192.958
30A | 96.479 |  | 0.47 |  | 0 | 0.47 | 91.84
30B | 96.479
31A | 96.479 |  | 0.64 |  | 0 | 0.64 | 120
31B | 96.479
32A | 96.479
32B | 96.479 |  | 0.34 |  | 0 | 0.34 | 67.3
33A | 96.479
33B | 96.479
34 | 175.9569
35 | 258.9186
36 | 351.9138 |  | 0.41 |  | 0 | 0.41 | 144.6
37 | 173.913
38A | 154.4036
38B | 154.4036 |  | 0.26 |  | 0 | 0.26 | 81.13
39A | 110.9253
39B | 110.9253
40 | 503.809
41 | 154.961
42 | 99.9628
43 | 99.9628
44 | 99.9628 |  | 0.78 |  | 0 | 0.78 | 100
45 | 99.9628 |  | 0.87 |  | 0 | 0.87 | 87
46 | 99.9628
47 | 195.9309 |  | 0.26 |  | 0 | 0.26 | 104.28
48 | 150.9662 |  | 0.43 |  | 0 | 0.43 | 65.59
49 | 99.9628 |  | 0.66 |  | 0 | 0.66 | 65.72
50 | 99.9628
51 | 99.9628
52 | 99.9628 |  | 0.61 |  | 0 | 0.61 | 61.24
53 | 99.9628
54 | 99.9628
55 | 99.9628
56 | 99.9628
57 | 149.9443
58 | 175.9569 |  | 0.49 |  | 0 | 0.49 | 86.35
59 | 99.9628
60 | 99.9628
61 | 99.9628 |  | 0.74 |  | 0 | 0.74 | 74.25
62 | 99.9628 |  | 0.96 |  | 0 | 0.96 | 96.39
63 | 99.9628 |  | 0.79 |  | 0 | 0.79 | 79.67
64 | 99.9628 |  | 0.62 |  | 0 | 0.62 | 62.32
65 | 99.9628
66 | 99.9628 |  | 0.71 |  | 0 | 0.71 | 71
67 | 99.9628
68 | 99.9628
69 | 184.9684
70 | 184.9684
71 | 99.9628
72 | 99.9628 |  | 0.48 |  | 0 | 0.48 | 48.58
73 | 99.9628
74 | 99.9628
75 | 99.9628 |  | 0.69 |  | 0 | 0.69 | 69.43
76 | 99.9628 |  | 0.77 |  | 0 | 0.77 | 77.1
77 | 99.9628
78 | 99.9628
79 | 99.9628
80 | 99.9628
81 | 99.9628 |  | 0.79 |  | 0 | 0.79 | 79.22
82 | 149.9443
83 | 149.9443
84 | 99.9628
85 | 99.9628
86 | 99.9628 |  | 0.68 |  | 0 | 0.68 | 100
87 | 99.9628 |  | 0.39 |  | 0 | 0.39 | 62.51
88 | 99.9628
89 | 99.9628 |  | 0.69 |  | 0 | 0.69 | 69.25
90 | 99.9628
91 | 99.9628 |  | 0.58 |  | 0 | 0.58 | 58.66
92 | 99.9628 |  | 0.4 |  | 0 | 0.4 | 62.56
93 | 99.9628
94 | 99.9628 |  | 0.63 |  | 0 | 0.63 | 63.45
95 | 149.9443
96 | 175 |  | 0.53 |  | 0 | 0.53 | 92.81
97 | 149.9443
98 | 149.9443
99 | 149.9443
100 | 149.9443
101 | 149.9443 |  | 0.49 |  | 0 | 0.49 | 74.92
102 | 149.9443 |  | 0.56 |  | 0 | 0.56 | 80.52
103 | 149.9443
104 | 149.9443
105 | 149.9443
106 | 149.9443
107 | 149.9443
108 | 149.9443 |  | 0.59 |  | 0 | 0.59 | 88.54
109 | 149.9443 |  | 0.66 |  | 0 | 0.66 | 100.12
110 | 149.9443
111 | 149.9443 |  | 0.75 |  | 0 | 0.75 | 150
112 | 149.9443 |  | 0.91 |  | 0 | 0.91 | 91.45
113 | 149.9443
114 | 149.9443 |  | 0.47 |  | 0 | 0.47 | 71.53
115 | 149.9443
116 | 149.9443
117 | 149.9443
118 | 149.9443 |  | 0.29 |  | 0 | 0.29 | 92.31
119 | 149.9443
120 | 171.9621
121A | 127.4619 |  | 0.3 |  | 0 | 0.3 | 78.68
121B | 127.4619
122A | 127.4619 |  | 0.68 |  | 0 | 0.68 | 143.36
122B | 127.4619 |  | 0.68 |  | 0 | 0.68 | 143.36
123A | 127.4619
123B | 127.4619
124A | 127.4619
124B | 127.4619
125A | 127.4619 |  | 0.28 |  | 0 | 0.28 | 72.37
125B | 127.4619
126A | 127.4619
126B | 127.4619 |  | 0.33 |  | 0 | 0.33 | 84.15
127 | 254.9238 |  | 0.6 |  | 0 | 0.6 | 154
128 | 262.9134 |  | 0.4 |  | 0 | 0.4 | 106
110 | 150 |  |  |  | 0 | 0 |  |  | 0
119 | 150 |  |  |  | 0 | 0 |  |  | 0
120 | 172 |  |  |  | 0 | 0 |  |  | 0
Total number of Buildings |  |  |  |  | 60 Villas
Approval Detail : Plan approval
Layout Approval No |  | MHSL/L.N.A.1(B)/S.R.560/2014 |  |  |  | Dated | 09/12/2015.
Floor Approved Plan No. |  | Approved by Grampanchayat of Chive, Tal. Sudhagad, Dist. Raigad. |  |  |  | Dated | Not Mentioned in Plan
Date of CC Approved by Grampanchayat of Chive, Tal. Sudhagad, Dist. Raigad. |  | G.No.17/8 = Plot No.16 G.No.142 = Plot No.01, 24 (A&B), 30, 36, 38B, 58, 61, 86, 87, 89, 109, 112, 114, 122 (A&B), 125B G.No.22 = Plot No. 47, 48, 49, 27B, 91, 101, 10, 45, 111, 72, 27A, 94, 92, 32B, 126B G.No.48 = Plot No. 75 G.No.97/8 = Plot No. 81, 31, 17, 118 G.No. 86 = Plot No.25, 52, 127, 44, 62, 63, 64, 23A, 121A, 76, 102 G.No.128 = Plot No.128 G.No.97/8 = Plot No.10 |  |  |  | Dated | 21/10/2020 25/01/2021 25/05/2021 25/01/2021 28/10/2020 27/09/2021 27/09/2021 29/10/2020
NA Order No.: |  | MHSL/L.N.A.1(B)/S.R.560/2014 |  |  | Date of approval: 31/07/2014 | Dated | 09/12/2015.
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA
Commencement date of construction |  |  | 09/12/2015. |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 2266.3 |  | Approved no of units |  |  | 60 Villas
Approved no of Floors |  | Villa/Plot no.1, 10, 16, 17, 19A, 23A, 24A, 24B, 25, 27A, 27B, 30B, 31, 32 B, 36, 38B, 44, 45, 47, 48, 49, 52, 58, 61, 62, 63, 64, 75, 76, 81, 84, 86, 87, 89, 91, 92, 93, 94, 96, 101, 108, 109, 110, 111,112, 114, 118, 119, 120, 125B, 122 (A & B), 127, 128 = G + 1st Floor Villa/Plot no.23A, 30A & 72 = Ground Floor Villa/Plot no.102, 66
Construction details :
Plot No. |  |  | Stage of construction |  |  | Progress |  | Disbursement
1, 10, 16, 17, 19A, 23A, 24A, 24B, 25, 27A, 27B, 30A, 30B, 32B, 36, 44, 45, 47 to 49, 52, 58, 61 to 64, 66,72, 75, 76, 81, 84, 86, 87, 89, 91, 92, 93, 94, 96, 101, 108 to 112, 114, 118 to 120, 121A, 122A, 122B, 125B, 126B, 127 |  |  | All work completed. Please provide OC. |  |  | 100% |  | 100%
Plot No. | Stage of construction |  |  |  |  | Progress % |  | Disbursement %
1 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
2 | 0 |  |  |  |  | 0% |  | 0%
3 | 0 |  |  |  |  | 0% |  | 0%
4 | 0 |  |  |  |  | 0% |  | 0%
5 | 0 |  |  |  |  | 0% |  | 0%
6 | 0 |  |  |  |  | 0% |  | 0%
7 | 0 |  |  |  |  | 0% |  | 0%
8 | 0 |  |  |  |  | 0% |  | 0%
9 | 0 |  |  |  |  | 0% |  | 0%
10 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
11 | 0 |  |  |  |  | 0% |  | 0%
12 | 0 |  |  |  |  | 0% |  | 0%
13 | 0 |  |  |  |  | 0% |  | 0%
14 | 0 |  |  |  |  | 0% |  | 0%
15 | 0 |  |  |  |  | 0% |  | 0%
16 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
17 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
18 | 0 |  |  |  |  | 0% |  | 0%
19A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
19B | 0 |  |  |  |  | 0% |  | 0%
20A | 0 |  |  |  |  | 0% |  | 0%
20B | 0 |  |  |  |  | 0% |  | 0%
21A | 0 |  |  |  |  | 0% |  | 0%
21B | 0 |  |  |  |  | 0% |  | 0%
22 | 0 |  |  |  |  | 0% |  | 0%
23A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
23B | 0 |  |  |  |  | 0% |  | 0%
24A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
24B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
25 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
26A | 0 |  |  |  |  | 0% |  | 0%
26B | 0 |  |  |  |  | 0% |  | 0%
27A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
27B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
28 | 0 |  |  |  |  | 0% |  | 0%
29 | 0 |  |  |  |  | 0% |  | 0%
30A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
30B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
31A & B | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. |  |  |  |  | 92.5% |  | 95% | 1
31B | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. |  |  |  |  | 92.5% |  | 95%
32A | 0 |  |  |  |  | 0% |  | 0%
32B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
33A | 0 |  |  |  |  | 0% |  | 0%
33B | 0 |  |  |  |  | #DIV/0! |  | 0%
34 | 0 |  |  |  |  | 0% |  | 0%
35 | 0 |  |  |  |  | 0% |  | 0%
36 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
37 | 0 |  |  |  |  | 0% |  | 0%
38A | 0 |  |  |  |  | 0% |  | 0%
38B | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 0.5 Floor, Painting upto 0.5 Floor Completed |  |  |  |  | 82.5% |  | 92.5% |  |  | Already given extra stage for 38A. Work is same as last visit (18/12/2023)
39A | 0 |  |  |  |  | 0% |  | 0%
39B | 0 |  |  |  |  | 0% |  | 0%
40 | 0 |  |  |  |  | 0% |  | 0%
41 | 0 |  |  |  |  | 0% |  | 0%
42 | 0 |  |  |  |  | 0% |  | 0%
43 | 0 |  |  |  |  | 0% |  | 0%
44 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
45 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
46 | 0 |  |  |  |  | 0% |  | 0%
47 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
48 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
49 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
50 | 0 |  |  |  |  | 0% |  | 0%
51 | 0 |  |  |  |  | 0% |  | 0%
52 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
53 | 0 |  |  |  |  | 0% |  | 0%
54 | 0 |  |  |  |  | 0% |  | 0%
55 | 0 |  |  |  |  | 0% |  | 0%
56 | 0 |  |  |  |  | 0% |  | 0%
57 | 0 |  |  |  |  | 0% |  | 0%
58 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
59 | 0 |  |  |  |  | 0% |  | 0%
60 | 0 |  |  |  |  | 0% |  | 0%
61 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
62 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
63 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
64 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
65 | 0 |  |  |  |  | 0% |  | 0%
66 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
67 | 0 |  |  |  |  | 0% |  | 0%
68 | 0 |  |  |  |  | 0% |  | 0%
69 | 0 |  |  |  |  | 0% |  | 0%
70 | 0 |  |  |  |  | 0% |  | 0%
71 | 0 |  |  |  |  | 0% |  | 0%
72 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
73 | 0 |  |  |  |  | 0% |  | 0%
74 | 0 |  |  |  |  | 0% |  | 0%
75 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
76 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
77 | 0 |  |  |  |  | 0% |  | 0%
78 | 0 |  |  |  |  | 0% |  | 0%
79 | 0 |  |  |  |  | 0% |  | 0%
80 | 0 |  |  |  |  | 0% |  | 0%
81 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
82 | 0 |  |  |  |  | 0% |  | 0%
83 | 0 |  |  |  |  | 0% |  | 0%
84 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
85 | 0 |  |  |  |  | 0% |  | 0%
86 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
87 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
88 | 0 |  |  |  |  | 0% |  | 0%
89 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
90 | 0 |  |  |  |  | 0% |  | 0%
91 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
92 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
93 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
94 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
95 | 0 |  |  |  |  | 0% |  | 0%
96 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
97 | 0 |  |  |  |  | 0% |  | 0%
98 | 0 |  |  |  |  | 0% |  | 0%
99 | 0 |  |  |  |  | 0% |  | 0%
100 | 0 |  |  |  |  | 0% |  | 0%
101 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
102 | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. |  |  |  |  | 90% |  | 95%
103 | 0 |  |  |  |  | 0% |  | 0%
104 | 0 |  |  |  |  | 0% |  | 0%
105 | 0 |  |  |  |  | 0% |  | 0%
106 | 0 |  |  |  |  | 0% |  | 0%
107 | 0 |  |  |  |  | 0% |  | 0%
108 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
109 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
110 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
111 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
112 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
113 | 0 |  |  |  |  | 0% |  | 0%
114 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
115 | 0 |  |  |  |  | 0% |  | 0%
116 | 0 |  |  |  |  | 0% |  | 0%
117 | 0 |  |  |  |  | 0% |  | 0%
118 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
119 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
120 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
121A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
121B | 0 |  |  |  |  | 0% |  | 0%
122A | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
122B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100% | 1
123A | 0 |  |  |  |  | 0% |  | 0%
123B | 0 |  |  |  |  | 0% |  | 0%
124A | 0 |  |  |  |  | 0% |  | 0%
124B | 0 |  |  |  |  | 0% |  | 0%
125A | 0 |  |  |  |  | 0% |  | 0%
125B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
126A | 0 |  |  |  |  | 0% |  | 0%
126B | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
127 | All work completed. Please provide OC. |  |  |  |  | 100% |  | 100%
128 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab, Brickwork upto 0.5 Floor, Internal Plaster upto 0.5 Floor Completed |  |  |  |  | 37.5% |  | 65%
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Value of the Property :
Recommended rate of the Plot + Villa Per Sq. Ft. (on Saleable area) | [5 empty] | 5400 |  |  | As per market inqury(Index II) rate has changed from 5000/- to 5400/- (By rakesh Sir)
Development Charges | [5 empty] | 2,00,000/-
Resort Membership | [5 empty] | 1,50,000/-
Legal Charges | [5 empty] | 15,000/-
Distressed valuation of the Property | [5 empty] | 4320
Building details Floor Wise | [8 empty] | Note - Deck Area & Pool Area is not Considered in any villa
Details of Flats in Building
Description | Plot Area (Sq.Ft) | RERA Carpet area (Sq.Ft) | Attached Terrace area (Sq.Ft) |  | Built-Up Area (Sq.Ft) | Saleable area (Sq.Ft) | PLC Y/N | Floor
Bungalow/Villa on Plot no.01 = Villa No.01
2BHK + Terrace | 2066.688 | 668.1376 | 315.6295 |  | 828.7204 | 1226.835 | N | G + 1st Floor |  | 5888807.8704
Bungalow/Villa on Plot no.10 = Villa No.10
2BHK + Terrace | 1980.576 | 813.048 | 223.3315 |  | 845.6198 | 1412.5425 | N | G + 1st Floor |  | 6780203.9885
Bungalow/Villa on Plot no.16 = Villa No.16
3BHK + Terrace | 2185.092 | 971.6996 | 96.3378 |  | 1089.2092 | 1602.8883 | N | G + 1st Floor
Bungalow/Villa on Plot no.17 = Villa No.17
3BHK + Terrace | 2131.272 | 1055.8128 | 242.8358 |  | 1291.68 | 1770.2457 | N | G + 1st Floor + Terrace
Bungalow/Villa on Plot no.19A = Villa No.19A
2BHK | 1081.782 | 578.3056 | 0 |  | 615.3779 | 925.2889 | N | G + 1st Floor |  | 4441386.9128
Bungalow/Villa on Plot no.19B = Villa No.19B
1BHK | 1081.782 | 299.0422 | 0 |  | 615.3779 | 478.4676 | N | G + Terrace Floor |  | 2296644.2404
Bungalow/Villa on Plot no.23A = Villa No.23A
1BHK | 1146.366 | 359.3443 | 0 |  | 615.3779 | 574.9509 | N | Ground Floor |  | 2759764.2209
Bungalow/Villa on Plot no.24A = Villa No.24A
2BHK + Terrace | 1087.164 | 535.0515 | 137.0731 |  | 663.7082 | 924.619 | N | G + 1st Floor
Bungalow/Villa on Plot no.24B = Villa No.24B
2BHK + Terrace | 1092.546 | 538.9804 | 106.5044 |  | 638.3052 | 915.6208 | N | G + 1st Floor
Bungalow/Villa on Plot no.25 = Villa No.25
3BHK + Terrace | 2088.216 | 786.1218 | 182.8265 |  | 982.3226 | 1349.2082 | N | G + 1st Floor | 5024.0578
Bungalow/Villa on Plot no.27A = Villa No.27A
3BHK + Terrace | 2077.452 | 699.7784 | 332.4677 |  | 928.2874 | 1285.8793 | N | G + 1st Floor + Terrace
Bungalow/Villa on Plot no.27B = Villa No.27B
2BHK+ Terrace | 2077.452 | 575.0828 | 169.533 | 0 | 743.7924 | 1004.8991 | N | G + 1st Floor + Terrace
Bungalow/Villa on Plot no.30 = Villa No.30A | [11 empty] | 10.764
1BHK | 1038.726 | 306.5361 | 0 |  | 367.8433 | 490.4578 | N | Ground Floor
Bungalow/Villa on Plot no.30 = Villa No.30B | [13 empty] | 176
2BHK + Terrace | 1038.726 | 384.7064 | 46.931 |  | 461.6477 | 638.9958 | N | G + 1st Floor
Bungalow/Villa on Plot no.31 (A & B) = Villa No.31
3BHK + Terrace | 2007.486 | 1204.0309 | 258.1961 |  | 1291.68 | 2055.5475 | N | G + 1st Floor
Bungalow/Villa on Plot no.32B = Villa No.32B
2BHK+ Terrace | 2077.452 | 423.6409 | 165.7807 | 0 | 743.7924 | 760.7158 | N | G + 1st Floor + Terrace
Bungalow/Villa on Plot no.36 = Villa No.36
4BHK | 3788.928 | 1236.2454 | 0 |  | 1556.4744 | 1977.9926 | N | G + 1st Floor | 150.664
Bungalow/Villa on Plot no.38B = Villa No.38B
3BHK | 1663.038 | 860.4892 | 167.546 |  | 1556.4744 | 1460.5558 | N | G + 1st Floor | 150.664
Bungalow/Villa on Plot no.44 = Villa No.44 | [8 empty] | 0 |  | 1236.2454 | 1556.4744
2BHK | 1076.4 | 658.055 | 0 |  | 846.481 | 1052.888 | N | G + 1st Floor | 0.33333 | 5105.5241 |  |  | 4314.9415
Bungalow/Villa on Plot no.45 = Villa No.45 | [8 empty] | 1621.7473 |  | 1236.2454 | 1556.4744
2BHK | 1076.4 | 761.235 | 0 |  | 936.468 | 1217.9761 | N | G + 1st Floor | 0.33333 | 4413.5063
Bungalow/Villa on Plot no.47 = Villa No.47
3BHK + Terrace | 2109.744 | 952.3557 | 265.4618 |  | 1122.4699 | 1656.4999 | N | G + 1st Floor |  | 7951199.7427
Bungalow/Villa on Plot no.48 = Villa No.48
2BHK + Terrace | 1625.364 | 548.401 | 157.4127 |  | 706.1184 | 956.148 | N | G + 1st Floor |  | 4589510.5751
Bungalow/Villa on Plot no.49 = Villa No.49
2BHK + Terrace | 1076.4 | 548.2471 | 174.3058 |  | 659.1874 | 964.3483 | N | G + 1st Floor |  | 4628871.6814
Bungalow/Villa on Plot no.52 = Villa No52
2BHK + Terrace | 1076.4 | 551.5506 | 116.305 |  | 707.4101 | 940.6335 | N | G + 1st Floor | 4656.5429 | 4515040.5731
Bungalow/Villa on Plot no.58 = Villa No.58
3BHK + Terrace | 1894.464 | 763.5336 | 103.6035 |  | 929.4714 | 1273.4555 | N | G + 1st Floor |  | 6112586.2637
Bungalow/Villa on Plot no.61= Villa No.61
2BHK + Terrace | 1076.4 | 577.2561 | 236.4786 |  | 799.227 | 1041.8491 | N | G + 2nd Floor |  | 5000875.5214
Bungalow/Villa on Plot no.62= Villa No.62
2BHK + Terrace | 1076.4 | 683.2288 | 177.1668 |  | 1037.542 | 1181.7494 | N | G + 1st Floor |  | 5672397.2198
Bungalow/Villa on Plot no.63= Villa No.63
3BHK + Terrace | 1076.4 | 712.6608 | 106.8865 |  | 857.5679 | 1193.7005 | N | G + 1st Floor |  | 5729762.2787
Bungalow/Villa on Plot no.64= Villa No.64
2BHK + Terrace | 1076.4 | 569.0378 | 167.2338 |  | 670.8125 | 994.0774 | N | G + 1st Floor |  | 4771571.3211
Bungalow/Villa on Plot no.66 = Villa No.66
2BHK + Terrace | 1076.4 | 671.3722 | 129.0388 |  | 764.244 | 1138.7149 | N | G + 1st Floor |  | 5465831.7542
Bungalow/Villa on Plot no.72 = Villa No.72
1BHK | 1076.4 | 481.1357 | 0 |  | 522.9151 | 769.8172 | N | Ground Floor |  | 5429.697
Bungalow/Villa on Plot no.75 = Villa No.75
2BHK + Terrace | 1076.4 | 611.0873 | 111.3536 |  | 747.3445 | 1033.4165 | N | G + 1st Floor
Bungalow/Villa on Plot no.76 = Villa No.76
2BHK + Terrace | 1076.4 | 733.5074 | 230.9954 |  | 829.9044 | 1250.6103 | N | G + 1st Floor + Terrace
Bungalow/Villa on Plot no.81 = Villa No.81
2BHK + Terrace | 1076.4 | 706.2702 | 142.7952 |  | 852.7241 | 1201.4299 | N | G + 1st Floor |  |  | 6487721.3943
Bungalow/Villa on Plot no.86 = Villa No.86
2BHK + Terrace | 1076.4 | 585.1569 | 173.2918 |  | 731.952 | 1022.8969 | N | G + 1st Floor | 4304.3439
Bungalow/Villa on Plot no.87 = Villa No.87
2BHK + Terrace | 1076.4 | 525.2993 | 167.1811 |  | 672.8576 | 924.0695 | N | G + 1st Floor | 4764.685
Bungalow/Villa on Plot no.89 = Villa No.89
2BHK + Terrace | 1076.4 | 726.2471 | 94.9385 |  | 745.407 | 1256.9338 | N | G + 1st Floor |  | 6033282.2784
Bungalow/Villa on Plot no.91 = Villa No.91
2BHK + Terrace | 1076.4 | 515.4449 | 99.8899 |  | 631.4162 | 874.6568 | N | G + 1st Floor |  | 4198352.6707
Bungalow/Villa on Plot no.92 = Villa No.92
2BHK + Terrace | 1076.4 | 551.063 | 151.2719 |  | 673.3958 | 957.3367 | N | G + 1st Floor | 4905.787 | 4595216.184
Bungalow/Villa on Plot no.94 = Villa No.94
2BHK + Terrace | 1076.4 | 566.4943 | 230.3496 |  | 682.9758 | 983.174 | N | G + 1st Floor |  | 4719235.2031
Bungalow/Villa on Plot no.96 = Villa No.96
3BHK + Terrace | 1883.7 | 830.7182 | 137.5101 |  | 999.0068 | 1397.9041 | N | G + 1st Floor |  | 6709939.6965
Bungalow/Villa on Plot no.101 = Villa No.101
2BHK + Terrace | 1614.6 | 698.251 | 174.6459 |  | 806.4389 | 1204.5245 | N | G + 1st Floor |  | 5781717.7816
Bungalow/Villa on Plot no.102 = Villa No.102
2BHK | 1614.6 | 858.4085 | 0 |  | 866.7173 | 1373.4537 | N | G + 1st Floor |  | 6592577.6517
Bungalow/Villa on Plot no.108 = Villa No.108
3BHK + Terrace | 1614.6 | 810.0685 | 94.2313 |  | 953.0446 | 1390.3409 | N | G + 1st Floor + Terrace |  | 4948.6425
Bungalow/Villa on Plot no.109 = Villa No.109
3BHK + Terrace | 1614.6 | 895.8554 | 120.5568 |  | 1077.6917 | 1493.6471 | N | G + 1st Floor
Bungalow/Villa on Plot no.111 = Villa No.111
3BHK + Terrace | 1614.6 | 931.9213 | 461.9909 |  | 1211.8111 | 1722.0695 | N | G + 1st Floor + Terrace |  | 4196.9125
Bungalow/Villa on Plot no.112 = Villa No.112
3BHK + Terrace | 1614.6 | 800.5919 | 107.2482 |  | 984.3678 | 1334.5711 | N | G + 1st Floor |  | 5415.5039
Bungalow/Villa on Plot no.114 = Villa No.114
2BHK + Terrace | 1614.6 | 621.7997 | 174.3553 |  | 769.9489 | 1082.0571 | N | G + 1st Floor |  | 6679.2915
Bungalow/Villa on Plot no.118 = Villa No.118
3BHK + Terrace | 1614.6 | 732.7055 | 264.7944 |  | 993.6248 | 1260.5936 | N | G + 1st Floor + Terrace |  | 5733.311
Bungalow/Villa on Plot no.121A = Villa No.121A
2BHK + Terrace | 1372.41 | 709.9977 | 212.4362 |  | 846.9115 | 1206.8084 | N | G + 1st Floor |  | 5792680.5281
Bungalow/Villa on Plot no.122A = Villa No.122A | [10 empty] | 10.764
3BHK | 1372.41 | 717.4669 | 0 |  | 1543.127 | 1147.947 | N | G + 1st Floor |  | 5510145.6783
Bungalow/Villa on Plot no.122B = Villa No.122B
2BHK + Terrace | 1372.41 | 490.4078 | 129.5447 |  | 1543.127 | 914.1973 | N | G + 1st Floor |  | 4388146.9632
Bungalow/Villa on Plot no.125B = Villa No.125B
2BHK + Terrace | 1372.41 | 585.313 | 272.8911 |  | 778.9907 | 1027.4644 | N | G + 1st Floor |  | 5840.4319
Bungalow/Villa on Plot no.126B = Villa No.126B
3BHK | 1372.41 | 874.603 | 0 |  | 905.7906 | 1399.3648 | N | G + 1st Floor |  | 4288.2571
Bungalow/Villa on Plot no.127 = Villa No.127
3BHK + Terrace | 2744.82 | 1431.612 | 136.8104 |  | 1657.656 | 2358.9844 | N | G + 1st Floor |  | 2543.8218
Bungalow/Villa on Plot no.128 = Villa No.128
3BHK + Terrace | 2830.932 | 956.3846 | 370.9888 |  | 1140.984 | 1653.8783 | N | G + 1st Floor |  | 3628.3419
Remarks :
Plot No.1, 10, 16, 24A, 24B, 27A, 27B, 30A, 30B, 44, 45, 47 to 49, 58, 61 to 64, 66, 75, 84, 89, 93, 96, 101, 108 to 112, 114, 118 to 120, 121A, 122A, 122B, 125B, 127 |  |  |  |  | All work Completed. Please provide OC.
Plot No. 128 |  |  |  |  | Work is same as last visit (02/09/2023).
Plot No. 38B |  |  |  |  | Work is same as last visit (18/12/2023).
Plot No. 31, 102 |  |  |  |  | Construction work is in process at the time of visit.
2. We considered Saleable area as per our calculation. 3. We have considered rate by verifying it from market inquire. 4. We adopted Carpet area from Plans which are verified by grampanchayat. 5. We received Approved Layout & NA order (By District Collector of Raigad) Building/Villa Floor Plan & CC (By Grampanchayat, Chive, Tal. Sudhagad, Dist. Raigad). 6. On Site, we meet Mr.Vinod (Project manager) - 9769099014.
Plot No./Villa No. |  |  |  |  | Approved & C.C Updated date
1. Plot No.24B = Villa 24B |  |  |  |  | 2021-06-26
2. Plot No.16 = Villa 16 |  |  |  |  | 2021-07-01
3. Villa on.89, 91, 1, 48, 96, 19A, 101, 49, 122A & B |  |  |  |  | 2021-07-17
4. Plot No.108 = Villa 108 |  |  |  |  | 2021-07-31
5. Plot No.30 = Villa 30A & 30B |  |  |  |  | 2021-08-31
6. Plot No.36, 45 & 125B = Villa 36, 45 & 125B |  |  |  |  | 2021-09-23
7. Plot No.86 & 111 = Villa 86 & 111 |  |  |  |  | 2021-10-16
8. Plot No.31 = Villa 31 |  |  |  |  | 2021-10-22
9. Plot No.17 & 118 = Villa 17 & 118 |  |  |  |  | 2021-11-16
10. Plot No.44, 72, 128 = Villa 44, 72, 128 |  |  |  |  | 2021-12-27
11. Plot No.64 = Villa 64 |  |  |  |  | 2022-01-03
12. Plot No.62, 63, 112 & 114 = Villa 62, 63, 112 & 114 |  |  |  |  | 2022-01-21
13. Plot No.27A = Villa 27A |  |  |  |  | 2022-01-29
14. Plot No.94 = Villa 94 |  |  |  |  | 2022-02-25 |  |  |  |  | Construction Same (30/09/2022) - 16, 17, 19A, 27B, 31 (A&B), 48, 49, 58, 64, 96, 111, 127, 128
15. Plot No.25, 52, 92 = Villa 25, 52, 92 |  |  |  |  | 2022-03-09 |  |  |  |  | All Work Completed (30/09/2022) - 109, 120, 119, 84, 121A
16. Plot No.127 = Villa 127 Plot No.87 = Villa 87 Plot No.23A = Villa 23A, Plot No. 38B = Villa 38B |  |  |  |  | 14/06/2022 18/06/2022 20/06/2022
17. Plot No.24 & 61 = Villa 24A, 61 |  |  |  |  | 2022-07-02 |  |  |  |  | Construction Same (15/02/2023) - 17, 19A, 23A 91
18. Plot No.47 = Villa 47 |  |  |  |  | 2022-07-28 |  |  |  |  | All Work Completed (15/02/2023) - 109, 120, 119, 84, 121A,58,89, 93,111
18. Plot No.27 = Villa 27B |  |  |  |  | 2022-09-06
19. Plot No.121A = Villa 121A |  |  |  |  | 2022-09-30
20. Plot No.32A = Villa 32A |  |  |  |  | 2023-02-15
21. Plot No.76 = Villa 76 |  |  |  |  | 2023-03-14
22. Plot No.10 = Villa 10 |  |  |  |  | 2023-06-09
23. Plot No.126B = Villa 126B |  |  |  |  | 2023-09-07
24. Plot No.102 = Villa 102 |  |  |  |  | 2024-01-16
25. Plot No.66 = Villa 66 |  |  |  |  | 2024-01-31
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) Ie have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | City of Music
PHOTOGRAPHS OF PROPERTY : |  |  |  | City of Music
PHOTOGRAPHS OF PROPERTY : |  |  |  | City of Music
Google Map :

## C%
Plot no | land area Sq. Ft. | land area Sq. Mt | Floor |  | Excavation | Plinth | RCC | Brick work | Internal Plaster | Ext. Plaster | Flooring | Painting | Finishing | Possession | Progress % | Disbursement % | Stage of construction:
1 | 191.9361 | 2066 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
2 | 191.9361 | 2066
3 | 191.9361 | 2066
4 | 191.9361 | 2066
5 | 191.9361 | 2066
6 | 191.9361 | 2066
7 | 191.9361 | 2066
8 | 224.9164 | 2421
9 | 183.9465 | 1980
10 | 183.9465 | 1980 | G+1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
11 | 184.9684 | 1991
12 | 192.958 | 2077
13 | 192.958 | 2077
14 | 193.887 | 2087
15 | 193.887 | 2087
16 | 193.887 | 2087 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
17 | 194.909 | 2098 | G +1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
18 | 338.9075 | 3648
19A | 100.4738 | 1081.5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
19B | 100.4738 | 1081.5
20A | 100.4738 | 1081.5
20B | 100.4738 | 1081.5
21A | 113.4801 | 1221.5
21B | 113.4801 | 1221.5
22 | 222.7796 | 2398
23A | 106.466 | 1146 | Ground | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
23B | 106.466 | 1146
24A | 101.4493 | 1092 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
24B | 101.4493 | 1092 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
25 | 193.7941 | 2086 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
26A | 96.9435 | 1043.5
26B | 96.9435 | 1043.5
27A | 96.479 | 1038.5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
27B | 96.479 | 1038.5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
28 | 192.958 | 2077
29 | 192.958 | 2077
30A | 96.479 | 1038.5 | Ground | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
30B | 96.479 | 1038.5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
31A & B | 96.479 | 1038.5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 92.5% | 95% | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
31B | 96.479 | 1038.5
32A | 96.479 | 1038.5
32B | 96.479 | 1038.5 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
33A | 96.479 | 1038.5
33B | 96.479 | 1038.5 |  |  | 2 | [9 empty] | #DIV/0!
34 | 175.9569 | 1894
35 | 258.9186 | 2787
36 | 351.9138 | 3788 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
37 | 173.913 | 1872
38A | 154.4036 | 1662
38B | 154.4036 | 1662 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 82.5% | 92.5% | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 0.5 Floor, Painting upto 0.5 Floor Completed
39A | 110.9253 | 1194
39B | 110.9253 | 1194
40 | 503.809 | 5423
41 | 154.961 | 1668
42 | 99.9628 | 1076
43 | 99.9628 | 1076
44 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
45 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
46 | 99.9628 | 1076
47 | 195.9309 | 2109 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
48 | 150.9662 | 1625 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
49 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
50 | 99.9628 | 1076
51 | 99.9628 | 1076
52 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
53 | 99.9628 | 1076
54 | 99.9628 | 1076
55 | 99.9628 | 1076
56 | 99.9628 | 1076
57 | 149.9443 | 1614
58 | 175.9569 | 1894 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
59 | 99.9628 | 1076
60 | 99.9628 | 1076
61 | 99.9628 | 1076 | G + 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 100% | 100% | All work completed. Please provide OC.
62 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
63 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
64 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
65 | 99.9628 | 1076
66 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
67 | 99.9628 | 1076
68 | 99.9628 | 1076
69 | 184.9684 | 1991
70 | 184.9684 | 1991
71 | 99.9628 | 1076
72 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
73 | 99.9628 | 1076
74 | 99.9628 | 1076
75 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
76 | 99.9628 | 1076 | G+1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
77 | 99.9628 | 1076
78 | 99.9628 | 1076
79 | 99.9628 | 1076
80 | 99.9628 | 1076
81 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
82 | 149.9443 | 1614
83 | 149.9443 | 1614
84 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
85 | 99.9628 | 1076
86 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
87 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
88 | 99.9628 | 1076
89 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
90 | 99.9628 | 1076
91 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
92 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
93 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
94 | 99.9628 | 1076 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
95 | 149.9443 | 1614
96 | 174.935 | 1883 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
97 | 149.9443 | 1614
98 | 149.9443 | 1614
99 | 149.9443 | 1614
100 | 149.9443 | 1614
101 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
102 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  |  | 90% | 95% | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
103 | 149.9443 | 1614
104 | 149.9443 | 1614
105 | 149.9443 | 1614
106 | 149.9443 | 1614
107 | 149.9443 | 1614
108 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
109 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
110 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
111 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
112 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
113 | 149.9443 | 1614
114 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
115 | 149.9443 | 1614
116 | 149.9443 | 1614
117 | 149.9443 | 1614
118 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
119 | 149.9443 | 1614 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
120 | 171.9621 | 1851 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
121A | 127.4619 | 1372 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
121B | 127.4619 | 1372
122A | 127.4619 | 1372 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
122B | 127.4619 | 1372 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
123A | 127.4619 | 1372
123B | 127.4619 | 1372
124A | 127.4619 | 1372
124B | 127.4619 | 1372
125A | 127.4619 | 1372
125B | 127.4619 | 1372 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
126A | 127.4619 | 1372
126B | 127.4619 | 1372 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
127 | 254.9238 | 2744 | G + 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 100% | 100% | All work completed. Please provide OC.
128 | 262.9134 | 2830 | G + 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0 |  |  |  |  | 37.5% | 65% | Excavation work Completed. Plinth work completed, RCC upto 1 Slab, Brickwork upto 0.5 Floor, Internal Plaster upto 0.5 Floor Completed

## pLOT aREA
Plot no
1 | 191.9361 | 2066
2 | 191.9361 | 2066
3 | 191.9361 | 2066
4 | 191.9361 | 2066
5 | 191.9361 | 2066
6 | 191.9361 | 2066
7 | 191.9361 | 2066
8 | 224.9164 | 2421
9 | 183.9465 | 1980
10 | 183.9465 | 1980
11 | 184.9684 | 1991
12 | 192.958 | 2077
13 | 192.958 | 2077
14 | 193.887 | 2087
15 | 193.887 | 2087
16 | 193.887 | 2087
17 | 194.909 | 2098
18 | 338.9075 | 3648
19A | 100.4738 | 1081.5
19B | 100.4738 | 1081.5
20A | 100.4738 | 1081.5
20B | 100.4738 | 1081.5
21A | 113.4801 | 1221.5
21B | 113.4801 | 1221.5
22 | 222.7796 | 2398
23A | 106.466 | 1146
23B | 106.466 | 1146
24A | 101.4493 | 1092
24B | 101.4493 | 1092
25 | 193.7941 | 2086
26A | 96.9435 | 1043.5
26B | 96.9435 | 1043.5
27A | 96.479 | 1038.5
27B | 96.479 | 1038.5
28 | 192.958 | 2077
29 | 192.958 | 2077
30A | 96.479 | 1038.5
30B | 96.479 | 1038.5
31A | 96.479 | 1038.5
31B | 96.479 | 1038.5
32A | 96.479 | 1038.5
32B | 96.479 | 1038.5
33A | 96.479 | 1038.5
33B | 96.479 | 1038.5
34 | 175.9569 | 1894
35 | 258.9186 | 2787
36 | 351.9138 | 3788
37 | 173.913 | 1872
38A | 154.4036 | 1662
38B | 154.4036 | 1662
39A | 110.9253 | 1194
39B | 110.9253 | 1194
40 | 503.809 | 5423
41 | 154.961 | 1668
42 | 99.9628 | 1076
43 | 99.9628 | 1076
44 | 99.9628 | 1076
45 | 99.9628 | 1076
46 | 99.9628 | 1076
47 | 195.9309 | 2109
48 | 150.9662 | 1625
49 | 99.9628 | 1076
50 | 99.9628 | 1076
51 | 99.9628 | 1076
52 | 99.9628 | 1076
53 | 99.9628 | 1076
54 | 99.9628 | 1076
55 | 99.9628 | 1076
56 | 99.9628 | 1076
57 | 149.9443 | 1614
58 | 175.9569 | 1894
59 | 99.9628 | 1076
60 | 99.9628 | 1076
61 | 99.9628 | 1076
62 | 99.9628 | 1076
63 | 99.9628 | 1076
64 | 99.9628 | 1076
65 | 99.9628 | 1076
66 | 99.9628 | 1076
67 | 99.9628 | 1076
68 | 99.9628 | 1076
69 | 184.9684 | 1991
70 | 184.9684 | 1991
71 | 99.9628 | 1076
72 | 99.9628 | 1076
73 | 99.9628 | 1076
74 | 99.9628 | 1076
75 | 99.9628 | 1076
76 | 99.9628 | 1076
77 | 99.9628 | 1076
78 | 99.9628 | 1076
79 | 99.9628 | 1076
80 | 99.9628 | 1076
81 | 99.9628 | 1076
82 | 149.9443 | 1614
83 | 149.9443 | 1614
84 | 99.9628 | 1076
85 | 99.9628 | 1076
86 | 99.9628 | 1076
87 | 99.9628 | 1076
88 | 99.9628 | 1076
89 | 99.9628 | 1076
90 | 99.9628 | 1076
91 | 99.9628 | 1076
92 | 99.9628 | 1076
93 | 99.9628 | 1076
94 | 99.9628 | 1076
95 | 149.9443 | 1614
96 | 174.935 | 1883
97 | 149.9443 | 1614
98 | 149.9443 | 1614
99 | 149.9443 | 1614
100 | 149.9443 | 1614
101 | 149.9443 | 1614
102 | 149.9443 | 1614
103 | 149.9443 | 1614
104 | 149.9443 | 1614
105 | 149.9443 | 1614
106 | 149.9443 | 1614
107 | 149.9443 | 1614
108 | 149.9443 | 1614
109 | 149.9443 | 1614
110 | 149.9443 | 1614
111 | 149.9443 | 1614
112 | 149.9443 | 1614
113 | 149.9443 | 1614
114 | 149.9443 | 1614
115 | 149.9443 | 1614
116 | 149.9443 | 1614
117 | 149.9443 | 1614
118 | 149.9443 | 1614
119 | 149.9443 | 1614
120 | 171.9621 | 1851
121A | 127.4619 | 1372
121B | 127.4619 | 1372
122A | 127.4619 | 1372
122B | 127.4619 | 1372
123A | 127.4619 | 1372
123B | 127.4619 | 1372
124A | 127.4619 | 1372
124B | 127.4619 | 1372
125A | 127.4619 | 1372
125B | 127.4619 | 1372
126A | 127.4619 | 1372
126B | 127.4619 | 1372
127 | 254.9238 | 2744
128 | 262.9134 | 2830

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 5.88 | 2.98 | 17.5224 | CB | 1 | 2.75 | 2.75 |  |  | 0
|  |  |  | 0 | FB | 1 | 3.24 | 3.24 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.03 | 2.4 | 4.872 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.65 | 3.85 | 14.0525 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.43 | 1.35 | 3.2805 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 427.6257 | 39.7274 |  |  | 64.4764 | 5.99 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Sheet2
Plot No. | Stage of construction | Progress % | Disbursement %
1 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 75% | 90%
16 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 75% | 90%
17 | Excavation work Completed. Plinth work completed | 10% | 45%
19A | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 0.5 Floor Completed | 53.75% | 77.5%
24B | Excavation work Completed. Plinth work completed, RCC Slab Completed | 50% | 75%
25 | Excavation work Completed. Plinth work completed | 10% | 45%
27A | Excavation work Completed. Plinth work completed | 10% | 45%
30A | Excavation work Completed. Plinth work completed, RCC upto 1 Slab, Brickwork upto 0.25 Floor Completed | 51.88% | 76.25%
30B | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
31A & B | Excavation work Completed. Plinth work completed, RCC Slab Completed | 50% | 75%
36 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
44 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
45 | Excavation work Completed. Plinth work completed | 10% | 45%
48 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 0.6 Floor Completed | 54.5% | 78%
49 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 75% | 90%
52 | Excavation work Completed. Plinth work completed, RCC Slab Completed | 50% | 75%
58 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 0.75 Floor Completed | 72.5% | 88.75%
62 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 0.5 Floor, External Plaster upto 0.5 Floor Completed | 66.25% | 85%
63 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | 57.5% | 80%
64 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 75% | 90%
72 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
75 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 0.5 Floor Completed | 53.75% | 77.5%
81 | Excavation work Completed. Plinth work completed, RCC upto 1.5 Slab, Brickwork Completed | 47.5% | 72.5%
84 | All work completed. Please provide OC. | 100% | 100%
86 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 0.2 Floor Completed | 59.5% | 81%
89 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | 57.5% | 80%
91 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | 57.5% | 80%
92 | Excavation work Completed. Plinth work completed | 10% | 45%
93 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 0.5 Floor Completed | 70% | 87.5%
94 | Excavation work Completed. Plinth work completed | 10% | 45%
96 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | 57.5% | 80%
101 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster Completed | 65% | 85%
108 | Excavation work Completed. Plinth work completed, RCC upto 1.5 Slab, Brickwork Completed | 47.5% | 72.5%
109 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 0.6 Floor Completed | 63.5% | 83%
110 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 0.75 Floor Completed | 72.5% | 88.75%
111 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab, Brickwork upto 0.25 Floor Completed | 31.87% | 61.25%
112 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
114 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
118 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%
119 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 0.7 Floor Completed | 64.5% | 83.5%
120 | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed | 75% | 90%
122A | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | 57.5% | 80%
122B | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork Completed | 57.5% | 80%
125B | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 0.5 Floor Completed | 53.75% | 77.5%
128 | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | 30% | 60%

## Sheet3
G.No.148 = Plot No.75 G.No.97/8 = Plot No.81 G.No.22 = Plot No.47 & 48 G.No.22 = Plot No.49, 27B G.No.22 = Plot No.91 G.No.22 = Plot No.101 G.No.22 = Plot No.10 G.No.22 = Plot No.45 G.No.22 = Plot No.111 G.No.97/8 = Plot No.31 Plot No.17 Plot No.118 G.No.86 = Plot No.44, 62, 63, 64, 23A, 121A G.No.22 = Plot No.72 G.No.128 = Plot No.128 G.No.22 = Plot No.27A G.No.22 = Plot No.94 G.No86 = Plot No.25, 52 G.No.22 = Plot No.92 G.No.86 = Plot No.127 | Dated | . 25/01/2021. 28/10/2020. 25/01/2021. 24/01/2021. 25/01/2021. 25/05/2021. 25/05/2021. 25/05/2021. 25/05/2021. 25/05/2021. 25/01/2021. 25/01/2021. 25/05/2021. 25/01/2021. 25/01/2021. 25/05/2021. 28/10/2020. 27/09/2021. 27/09/2021. 27/09/2021. 25/05/2021. 27/09/2021. 25/01/2021. 25/01/2021. 25/05/2021. 25/05/2021. 27/09/2021. 25/05/2021. 27/09/2021.