## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Tristar Development LLP
Name of the builder company |  |  |  | Tristar Development LLP
Name of the Project |  |  |  | B C Corp Arista
Existing Building Name |  |  |  | Building No.12 (Sukhada Co-oprative Housing Society)
Provided Contact Details ( Name & Contact No.) |  |  |  | 022-23514427/ 23538110
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Ms Nidhi Pangal CRM 8356051630 |  |  |  | 9892929113
Name / No of the Building |  |  |  | Wing A & B |  |  |  | 07/02/2025 Check for Slabs of Wing B next visit
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51800046486
Project location details |  | B C Corp Arista, Survey No.341(Pt), CTS No.606(Pt) & Existing Building Name - Sukhada Co-oprative Housing Society, near Sarvoday Apartments, Road Number -7, Kherwadi, Bandra, Bandra East, Andheri, Mumbai - 400051.
Survey No |  | 341(Pt), CTS No.606(Pt) & Existing Building Name - Sukhada Co-oprative Housing Society
Locality |  | Kherwadi
Road |  | Road Number -7 |  | Locality/Village |  | Bandra
City |  | Bandra East |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400051
Nearby Landmark |  | Sarvoday Apartments |  | Distance from city centre: |  | 0.950KM from Bandra Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Sarvoday Apartments
West | NA | NA |  |  | Road Number - 4
North | NA | NA |  |  | Vivekaanand CHS
South | NA | NA |  |  | Shakti Sadan Chs
Does the boundaries at site match, as mentioned in the Docoumentation: NA | [7 empty] | changed on 18/08/2025
Latitude & Longitude |  | 19.058595, 72.845756 | [5 empty] | 19.0583 |  | 72.8457
Location Link |  | https://maps.app.goo.gl/7Tm1ujdN3HA1Agos9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1547.46
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 1.3378
Total FSI availaible for the project |  |  |  | 4.3378
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 6712.59
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | Mhada-95/959/2022 |  |  | Dated | 2022-07-05
Approved Floor plan No. |  | Mhada-95/959/2022 |  |  | Dated | 2022-07-05
Commencement-CC No Valid Up to: |  | MH/EE/BP/GM/MHADA-95/959/2023 |  |  | Dated | 2023-12-19
This further CC is issue for the extended work " upto top of 20th floor level with ht. 69.58mt. From AGL + LMR + OHT of wing A and upto top of 19th part floor level with ht. 66.60mt. From AGL + LMR + OHT of wing B, as per approved amended plans dt.18.12.2023.
AAI NOC No Valid Up to: |  | SNCR/WEST/B/090621/573962 |  |  | Dated | 2021-10-13
|  | Permissible Top Elevation in mtrs Above Mean Sea Level (AMSL) - 57.13M |  |  | Valid Upto Date | 2029-10-12
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 6712.59
Approved no of units |  |  | Wing A = Rehab Flats - 40, Sale Flats - 36 Wing B = Rehab Flats - 14, Sale Flats - 53
Approved no of Floors |  |  | Wing A = Gr + 3P + 4A + 5th to 20th Floor Wing B = Gr + 3P + 4A + 5th to 19th Floor |  |  |  |  | check
Proposed no of Floors |  |  | Wing A = Gr + 3P + 4A + 5th to 20th Floor
Wing B = Gr + 3P + 4A + 5th to 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr + 3P + 4A + 5th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 14 Floor, Painting upto 8 Floor Completed | , Flooring upto 14 Floor, Painting upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 14 Floor, Painting upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 84% |  | 93.5% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 14 | 70% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 40% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Construction details: |  | Wing B = Gr + 3P + 4A + 5th to 20th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 12 Floor, Painting upto 4 Floor Completed | , Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 12 Floor, Painting upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 20 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 12 Floor, Painting upto 4 Floor Completed | [5 empty] | Completed | Completed | 07/02/2025 Check for Slabs of Wing B next visit
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% | 77.62% |  | 90.5% |  | Excavation in process | 10
Plinth |  | 20 | 100% |  |  |  |  | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% |  |  |  |  | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 20 | 100% |  |  |  |  | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 15 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 60% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 20% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 15
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 20
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 23000
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1000000
Distressed valuation of the Property |  |  |  |  | 18400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Flats |  | Total Carpet Area |  | Total Saleable Area |  |  | visitor
Wing A | Rehab | 40 |  | 20577.5388 |  | 32924.0621 |  |  | 31900
| Sale | 36 |  | 17205.479 |  | 27528.7664
Wing B | Rehab | 14 |  | 8710.2288 |  | 13936.3661
B Wing (Flats) | Sale | 53 |  | 36830.1024 |  | 58928.1638
Total |  | 143 |  | 83323.349 |  | 133317.3584
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Sale / Rehab Unit | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Wing A
Ground Floor For Parking
1st, 2nd & 3rd Floor For Parking
4th Floor For Amenities
5th, 7th & 8th Floor For Residential | [8 empty] | 10.764
1 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 5th, 7th & 8th Floor For Residential |  |  | 46.962
2 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 5th, 7th & 8th Floor For Residential |  | 25630.7248
3 | Sale | 1.5BHK | 398.9138 | 0 | 638.2621 | 5th, 7th & 8th Floor For Residential |  | 33058.5171
4 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 5th, 7th & 8th Floor For Residential
5 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 5th, 7th & 8th Floor For Residential
6th Floor (Part Refuge Area)
1 | Sale | 3 | 751.7362 | 0 | 1202.778 | 6th Floor (Part Refuge Area) |  | 69.838 | 950.5688
2 | Refuge Area |  |  |  |  | 6th Floor (Part Refuge Area)
3 | [5 empty] | 6th Floor (Part Refuge Area)
4 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 6th Floor (Part Refuge Area) |  | 47.115
5 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 6th Floor (Part Refuge Area)
9th to 12th, 14th & 15th Floor
1 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 9th to 12th, 14th & 15th Floor
2 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 9th to 12th, 14th & 15th Floor
3 | Sale | 1.5BHK | 398.9138 | 0 | 638.2621 | 9th to 12th, 14th & 15th Floor
4 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 9th to 12th, 14th & 15th Floor
5 | Rehab | 2 | 514.5192 | 0 | 823.2307 | 9th to 12th, 14th & 15th Floor
13th Floor (Part Refuge Area)
1 | Sale | 2 | 578.565 | 0 | 925.704 | 13th Floor (Part Refuge Area) |  | 50.56
2 | Refuge Area |  |  |  |  | 13th Floor (Part Refuge Area)
3 | [5 empty] | 13th Floor (Part Refuge Area)
4 | Rehab | 2 | 512.9046 | 0 | 820.6474 | 13th Floor (Part Refuge Area)
5 | Rehab | 2 | 512.9046 | 0 | 820.6474 | 13th Floor (Part Refuge Area)
16th to 18th Floor
1 | Sale | 2 | 514.5192 | 0 | 823.2307 | 16th to 18th Floor
2 | Sale | 2 | 514.5192 | 0 | 823.2307 | 16th to 18th Floor
3 | Sale | 1.5BHK | 398.9138 | 0 | 638.2621 | 16th to 18th Floor
4 | Sale | 2 | 514.5192 | 0 | 823.2307 | 16th to 18th Floor
5 | Sale | 2 | 514.5192 | 0 | 823.2307 | 16th to 18th Floor
19th Floor
1 | Sale | 2 | 514.5192 | 0 | 823.2307 | 19th Floor
2 | Sale | 2 | 514.5192 | 0 | 823.2307 | 19th Floor
3 | Sale | 1.5BHK | 398.9138 | 0 | 638.2621 | 19th Floor
4 | Sale | 2 | 514.5192 | 0 | 823.2307 | 19th Floor |  | 27331.3416
5 | Sale | 2 | 514.5192 | 0 | 823.2307 | 19th Floor
20th Floor
1 | Sale | 2 | 514.5192 | 0 | 823.2307 | 20th Floor
2 | Sale | 2 | 514.5192 | 0 | 823.2307 | 20th Floor
3 | Sale | 1.5BHK | 398.9138 | 0 | 638.2621 | 20th Floor
4 | Sale | 2 | 514.5192 | 0 | 823.2307 | 20th Floor
5 | Sale | 2 | 514.5192 | 0 | 823.2307 | 20th Floor
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
Wing B
Ground Floor For Parking
1st, 2nd & 3rd Floor For Parking
4th Floor For Amenities
5th, 7th & 8th Floor For Residential
1 | Rehab | 2 | 622.1592 | 0 | 995.4547 | 5th, 7th & 8th Floor For Residential |  |  | 57.1425
2 | Rehab | 2 | 622.1592 | 0 | 995.4547 | 5th, 7th & 8th Floor For Residential
3 | Sale | 3 | 879.2035 | 0 | 1406.7256 | 5th, 7th & 8th Floor For Residential |  |  | 80.8905
4 | Rehab | 2 | 622.1592 | 0 | 995.4547 | 5th, 7th & 8th Floor For Residential
5 | Rehab | 2 | 622.1592 | 0 | 995.4547 | 5th, 7th & 8th Floor For Residential
6th Floor (Part Refuge Area)
1 | Refuge Area |  |  |  |  | 6th Floor (Part Refuge Area)
2 | [5 empty] | 6th Floor (Part Refuge Area)
3 | Sale | 3 | 879.2035 | 0 | 1406.7256 | 6th Floor (Part Refuge Area) |  | 80.488
4 | Rehab | 2 | 622.1592 | 0 | 995.4547 | 6th Floor (Part Refuge Area) |  | 57.5025
5 | Rehab | 2 | 622.1592 | 0 | 995.4547 | 6th Floor (Part Refuge Area)
9th to 12th, 14th & 15th Floor
1 | Sale | 2 | 622.1592 | 0 | 995.4547 | 9th to 12th, 14th & 15th Floor
2 | Sale | 2 | 622.1592 | 0 | 995.4547 | 9th to 12th, 14th & 15th Floor
3 | Sale | 3 | 879.2035 | 0 | 1406.7256 | 9th to 12th, 14th & 15th Floor
4 | Sale | 2 | 622.1592 | 0 | 995.4547 | 9th to 12th, 14th & 15th Floor
5 | Sale | 2 | 622.1592 | 0 | 995.4547 | 9th to 12th, 14th & 15th Floor
13th Floor (Part Refuge Area)
1 | Refuge Area |  |  |  |  | 13th Floor (Part Refuge Area)
2 | [5 empty] | 13th Floor (Part Refuge Area)
3 | Sale | 3 | 879.2035 | 0 | 1406.7256 | 13th Floor (Part Refuge Area)
4 | Sale | 2 | 622.1592 | 0 | 995.4547 | 13th Floor (Part Refuge Area) |  | 22602.7358
5 | Sale | 2 | 622.1592 | 0 | 995.4547 | 13th Floor (Part Refuge Area)
16th to 18th Floor
1 | Sale | 2 | 622.1592 | 0 | 995.4547 | 16th to 18th Floor
2 | Sale | 2 | 622.1592 | 0 | 995.4547 | 16th to 18th Floor
3 | Sale | 3 | 879.2035 | 0 | 1406.7256 | 16th to 18th Floor
4 | Sale | 2 | 622.1592 | 0 | 995.4547 | 16th to 18th Floor
5 | Sale | 2 | 622.1592 | 0 | 995.4547 | 16th to 18th Floor
19th Floor (Part Terrace Area)
3 | Sale | 3 | 879.2035 | 0 | 1406.7256 | 19th Floor (Part Terrace Area)
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
1 | Construction work is in process at the time of Visit. Internal photographs was not allowed
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Dry balcony + Balcony.
5 | We have considered proposed No. of Floor for Stage Calculation.
6 | We have considered rate by verifying it from market inquire.
7 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
8 | Car parking is subjected to authentic documentation.
9 | The Airport Authority of India's provided NOC is valid up to the 15th floor; therefore, for flats above the 15th floor the Airport Authority of India's NOC should be checked before disbursement.
10 | We have updated latest revised CC on (11/01/2024).
10 | ConsPlease provide revised approved CC for Wing B, As the construction work goes beyond the CC permission.
10 | Please provide revised approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Tushar Bhuwad |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | B C Corp Arista
Referance to Remark No. 9 :
Layout Plan :
Google Map :
Formulas:
Bandra = [Bandra, row above]
A
B
A
B
A
Wing B
B
A
A
B
A
B
A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted