## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-11
Name of the builder group |  |  |  | Vertical Realtors Private Limited
Name of the builder company |  |  |  | Vertical Realtors Private Limited
Name of the Project |  |  |  | Ekatva Onyx
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr.Santosh Dandekar - 9833119645
Site Person - Contact Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans & CC
RERA No. |  |  |  | P51700047272
Project location details |  | Ekatva Onyx, Plot No.A-A-280, Survey No.08, near Oxford Instruments India Pvt. Ltd., Internal Road, Neheru Nagar, Panchapakhadi, Thane, Thane, Thane - 400604.
Plot No |  | A-A-280, Survey No.08
Locality |  | Neheru Nagar
Road |  | Internal Road |  | Locality/Village |  | Panchapakhadi
City |  | Thane |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400604
Nearby Landmark |  | Oxford Instruments India Pvt. Ltd. |  | Distance from city centre: |  | 3.6KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Oxford Instruments India Pvt. Ltd.
South | NA | NA |  |  | Ramco Engineering Works
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude & Longitude |  | 19.200968, 72.954454
Location Link |  | https://goo.gl/maps/Xzn7qZQovyYKhCys8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1314
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 5.3
Total FSI availaible for the project |  |  |  | 6.3
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8278.2
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Industrial Development Corporation (MIDC)
Layout Approval No |  | DE&PAIII/THN/SPA/BPAMS/I-88421/2024 |  |  | Dated | 2024-12-11
Approved Floor plan No. |  | DE&PAIII/THN/SPA/BPAMS/I-88421/2024 |  |  | Dated | 2024-12-11
Combined Approval Letter No Valid Up to: |  | DE&PAIII/THN/SPA/BPAMS/I-88421/2024 |  |  | Dated | 2024-12-11
Gr + 1st to 13th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8278.2
Approved no of units |  |  | IT Unit - 142
Approved no of Floors |  |  | Gr + 1st to 13th Floor
Proposed no of Floors |  |  | Gr + 1st to 13th Floor
Expected Completion |  |  | As per RERA - 30/06/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr + 1st to 13th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor Completed | , Internal Plaster upto 8 Floor, External Plaster upto 5 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 13 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 8 Floor, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.25
Excavation |  | 13 | 100% | 65.96% |  | 85% |  | Excavation in process | 6.5
Plinth |  | 13 | 100% |  |  |  |  | Excavation Completed | 13
RCC (Including podiums) |  | 14 | 100% |  |  |  |  | Footing in Process | 3.25
Brickwork | Brickwork & Internal Plaster | 13 | 100% |  |  |  |  | Footing Completed | 6.5
Internal Plaster | Brickwork & Internal Plaster | 8 | 61.54% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 38.46% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 13
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft.
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the IT Unit Per Sq. Ft. |  |  |  |  | 11500 |  |  | Rate 11500 by SANJAY VERBAL On 25/02/2025
Recommended rate of the Office Per Sq. Ft. (4th & 5th Floor) |  |  |  |  | 9000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 9200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
IT Unit |  | 142 |  | 46960.0597 |  | 71499.1138
Total |  | 142 |  | 46960.0597 |  | 71499.1138
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Basement For Pump Room, Fire Tank & Parking | [9 empty] | 132
Ground Floor Entrance Lobby & Parking
1st Floor For Meter Room, Hirkani Kasha & Parking
2nd to 7th & 9th to 10th Floor For Commercial | [7 empty] | 8
1 |  | IT Unit | 338.714 | 0 | 338.714 | 0 | 508.071 | 10.764 | 32.1498 | 346.0604
2 |  | IT Unit | 323.2451 | 0 | 323.2451 | 0 | 484.8676
3 |  | IT Unit | 299.0928 | 0 | 299.0928 | 0 | 448.6392
4 |  | IT Unit | 282.372 | 0 | 282.372 | 0 | 423.558
5 |  | IT Unit | 269.4541 | 0 | 269.4541 | 0 | 404.1812
6 |  | IT Unit | 342.3426 | 0 | 342.3426 | 0 | 513.5138
7 |  | IT Unit | 315.2948 | 0 | 315.2948 | 0 | 472.9422
8 |  | IT Unit | 438.0227 | 0 | 438.0227 | 0 | 657.034
9 |  | IT Unit | 407.3926 | 0 | 407.3926 | 0 | 611.089
10 |  | IT Unit | 361.8189 | 0 | 361.8189 | 0 | 542.7284
11 |  | IT Unit | 337.291 | 0 | 337.291 | 0 | 505.9365
12 |  | IT Unit | 411.3409 | 0 | 411.3409 | 0 | 617.0113
8th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | IT Unit | 338.714 | 0 | 338.714 | 0 | 508.071
2 |  | IT Unit | 323.2451 | 0 | 323.2451 | 0 | 484.8676
3 |  | IT Unit | 299.0928 | 0 | 299.0928 | 0 | 448.6392
4 |  | IT Unit | 282.372 | 0 | 282.372 | 0 | 423.558
5 |  | IT Unit | 269.4541 | 0 | 269.4541 | 0 | 404.1812
6 |  | IT Unit | 342.3426 | 0 | 342.3426 | 0 | 513.5138
7 |  | IT Unit | 315.2948 | 0 | 315.2948 | 0 | 472.9422
8 |  | IT Unit | 438.0227 | 0 | 438.0227 | 0 | 657.034
9 |  | IT Unit | 407.3926 | 0 | 407.3926 | 0 | 611.089
10 |  | IT Unit | 361.8189 | 0 | 361.8189 | 0 | 542.7284
11 |  | IT Unit | 337.291 | 0 | 337.291 | 0 | 505.9365
12 |  | - | Refuge Area
11th Floor | [7 empty] | 1
1 |  | IT Unit | 334.4515 | 0 | 334.4515 | 0 | 501.6772
2 |  | IT Unit | 323.2451 | 0 | 323.2451 | 0 | 484.8676
3 |  | IT Unit | 299.0928 | 0 | 299.0928 | 0 | 448.6392
4 |  | IT Unit | 282.372 | 0 | 282.372 | 0 | 423.558
5 |  | IT Unit | 269.4541 | 0 | 269.4541 | 0 | 404.1812 |  | 144
6 |  | IT Unit | 290.8314 | 0 | 290.8314 | 0 | 436.2472
7 |  | IT Unit | 315.2948 | 0 | 315.2948 | 0 | 472.9422
8 |  | IT Unit | 436.2046 | 0 | 436.2046 | 0 | 654.307
9 |  | IT Unit | 408.7091 | 0 | 408.7091 | 0 | 613.0636
10 |  | IT Unit | 366.2989 | 0 | 366.2989 | 0 | 549.4484
11 |  | IT Unit | 341.3264 | 0 | 341.3264 | 0 | 511.9897
12 |  | IT Unit | 407.9556 | 0 | 407.9556 | 0 | 611.9334
12th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | IT Unit | 281.6939 | 0 | 281.6939 | 106.9511 | 502.7541 | 23.7348
2 |  | IT Unit | 268.2389 | 0 | 268.2389 | 64.584 | 499.2343
3 |  | IT Unit | 248.2178 | 0 | 248.2178 | 56.511 | 457.0933
4 |  | IT Unit | 234.8705 | 0 | 234.8705 | 56.511 | 437.0722
5 |  | IT Unit | 224.2141 | 0 | 224.2141 | 54.8964 | 418.6658
6 |  | IT Unit | 283.8467 | 0 | 283.8467 | 71.0424 | 532.3336
7 |  | IT Unit | 262.6416 | 0 | 262.6416 | 64.584 | 490.8384
8 |  | IT Unit | 247.7873 | 0 | 247.7873 | 184.5488 | 510.0925
9 |  | IT Unit | 292.2426 | 0 | 292.2426 | 62.9694 | 532.818
10 |  | IT Unit | 303.8677 | 0 | 303.8677 | 64.584 | 552.6776
11 |  | IT Unit | 283.9543 | 0 | 283.9543 | 64.584 | 522.8075
12 |  | - | Refuge Area
13th Floor | [7 empty] | 1
1 |  | IT Unit | 281.6939 | 0 | 281.6939 | 0 | 422.5408 | 25.5573
2 |  | IT Unit | 268.2389 | 0 | 268.2389 | 0 | 402.3583
3 |  | IT Unit | 248.2178 | 0 | 248.2178 | 0 | 372.3268
4 |  | IT Unit | 234.8705 | 0 | 234.8705 | 0 | 352.3057
5 |  | IT Unit | 224.2141 | 0 | 224.2141 | 0 | 336.3212
6 |  | IT Unit | 283.8467 | 0 | 283.8467 | 0 | 425.77
7 |  | IT Unit | 262.6416 | 0 | 262.6416 | 0 | 393.9624
8 |  | IT Unit | 247.7873 | 0 | 247.7873 | 0 | 371.6809
9 |  | IT Unit | 292.2426 | 0 | 292.2426 | 0 | 438.3639
10 |  | IT Unit | 303.8677 | 0 | 303.8677 | 0 | 455.8016
11 |  | IT Unit | 283.9543 | 0 | 283.9543 | 0 | 425.9315
12 |  | IT Unit | 295.5794 | 0 | 295.5794 | 0 | 443.3692
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor |  | Centrum Business Square |  | 9000 | 800M
55%
Basement Floor For Pump Room, Fire Tank & Parking
Ground Floor For Entrance Lobby & Parking
1st Floor For Commercial & Parking
1 |  | IT Unit | 304.8096 | 0 | 472.4548 | 1st Floor For Commercial & Parking
2 |  | IT Unit | 337.4223 | 0 | 523.0046
2 & 3rd Floor For Commercial
1 |  | IT Unit | 304.8096 | 0 | 472.4548 | 2 & 3rd Floor For Commercial
2 |  | IT Unit | 321.166 | 0 | 497.8073
3 |  | IT Unit | 297.0137 | 0 | 460.3713
4 |  | IT Unit | 280.7574 | 0 | 435.174
5 |  | IT Unit | 264.5011 | 0 | 409.9767
6 |  | IT Unit | 343.4604 | 0 | 532.3636
7 |  | IT Unit | 310.9477 | 0 | 481.969
8 |  | IT Unit | 443.4999 | 0 | 687.4249
9 |  | IT Unit | 378.8304 | 0 | 587.1871
10 |  | IT Unit | 361.2689 | 0 | 559.9668
11 |  | IT Unit | 330.1696 | 0 | 511.7628
12 |  | IT Unit | 411.1525 | 0 | 637.2864 |  |  | 374.6667 |  |  | 323.3333 |  | 423.3333
4th & 5th Floor For Commercial | [7 empty] | 8393.3548 |  |  | 8299.289 |  | 8316.5122
1 |  | IT Unit | 304.8096 | 0 | 472.4548 | 4th & 5th Floor For Commercial |  |  |  |  | Cost Sheet
2 |  | IT Unit | 321.166 | 0 | 497.8073
3 |  | IT Unit | 297.0137 | 0 | 460.3713 |  |  | 10.764 |  |  | 101 | 5249330 | 11121.4619
4 |  | IT Unit | 280.7574 | 0 | 435.174
5 |  | IT Unit | 264.5011 | 0 | 409.9767 | [5 empty] | 201 | 5749330 | 12169.0574
6 |  | IT Unit | 343.4604 | 0 | 532.3636 | [5 empty] | 204 | 4423505 | 10164.9113
7 |  | IT Unit | 310.9477 | 0 | 481.969 | [5 empty] | 208 | 6694917 | 9739.1248
8 |  | IT Unit | 443.4999 | 0 | 687.4249 | [7 empty] | 10691.0312
9 |  | IT Unit | 378.8304 | 0 | 587.1871
10 |  | IT Unit | 361.2689 | 0 | 559.9668
11 |  | IT Unit | 330.1696 | 0 | 511.7628
12 |  | IT Unit | 411.1525 | 0 | 637.2864
Remarks:
* | Construction work is in process at the time of Visit.
* | #REF!
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Please check for Fire Noc.
* | We have updated revised approved plan & CC on 11/02/2025.
* | Recommended Rates / Other charges of the Property have been revised on 25/02/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ekatva Onyx
Layout :
Google Map :
Formulas:
Panchapakhadi = [Panchapakhadi, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted