## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-11
Name of the builder group |  |  |  | M/s.Jollity Lavanya Developers
Name of the builder company |  |  |  | M/s.Jollity Lavanya Developers
Name of the Project |  |  |  | Jollity Lavanya
Contect Details ( Name & Contect No.) |  |  |  | 9763407741
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Saleable area, Cost Sheet
RERA No. |  |  |  | P99000024506
Project location details |  | Jollity Lavanya, Survey No.380 & Plot No.116, Mahim-Palghar Road, Mahim, Palghar, Palghar, Palghar.
Survey No |  | 380 & Plot No.116
Road |  | Mahim-Palghar Road |  | Village |  | Mahim
City |  | Palghar |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401402
Near by Landmark |  | Near, Icon Residency |  | Distance from city centre: |  | 3.7Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Icon Residency
West | NA | NA |  |  | Mahim-Palghar Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.6766 |  | Longitude |  | 72.7461
Location Link: |  | https://maps.app.goo.gl/gktTC1Zih2kMxACk7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 556
Permissible FSI |  |  |  | 1.19
Permissible TDR/Paid FSI |  |  |  | 0.01
Total FSI availaible for the project |  |  |  | 1.2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 667.2
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | JA.KR.SSNR-PALGHAR SHAKHA/BP/M.MAHIM/T.PALGHAR/S.KR.380/B.KR116/RAHIVASI & RASTAYASMUKH DUKANE/372 KR.MAHASUL/K.S1/MJ.1/ANAP/SR/242/18 |  |  | Dated | 14/02/2019. 30/05/2019.
Approved Floor plan No. |  | JA.KR.SSNR-PALGHAR SHAKHA/BP/M.MAHIM/T.PALGHAR/S.KR.380/B.KR116/RAHIVASI & RASTAYASMUKH DUKANE/372 KR.MAHASUL/K.S1/MJ.1/ANAP/SR/242/18 |  |  | Dated | 14/02/2019. 30/05/2019.
NA order cum Commencement Certificate No. |  | KR.MAHASUL/K.S1/MJ.1/ANAP/SR/242/18 |  |  | Dated | 30/05/2019.
Valid Up to: Gr. + 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 667.2
Approved no of units |  |  | Flats - 17 , Shops - 05
Approved no of Floors |  |  | Gr. + 4th Floor
Proposed no of Floors |  |  | Gr. + 4th Floor
Expected Completion |  |  | As per RERA - 29/05/2024
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Gr. + 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3.5 Floor, External Plaster upto 3 Floor Completed | , Internal Plaster upto 3.5 Floor, External Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3.5 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 71.56% |  | 88.12% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3.5 | 87.5% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3500 |  |  | OC Charges by Nikhil Dani |  | 2024-02-27
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000 |  |  | do not increase any charges
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 100000
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, , Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges, Electricity, Meter Installation & Water Connection Charges |  |  |  |  | 100000
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2800
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shop |  | 5 | 525.6061 |  | 1057.5
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Flats |  | 17 | 6217.717 |  | 9068
Grand Total |  | 22 | 6743.3231 |  | 10125.5
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Ground Floor for Commercial, Residential & Parking
1 |  | Shop | 107.4247 | 0 | 211.5 | Ground Floor for Commercial, Residential & Parking
2 |  | Shop | 103.1191 | 0 | 211.5
3 |  | Shop | 107.4247 | 0 | 211.5
4 |  | Shop | 104.6261 | 0 | 211.5
5 |  | Shop | 103.0115 | 0 | 211.5
1 |  | 1BHK | 330.2395 | 0 | 500
1st Floor
1 |  | 1BHK | 340.3577 | 0 | 500 | 1st Floor
2 |  | 1BHK | 382.5526 | 0 | 552
3 |  | 1BHK | 382.5526 | 61.7854 | 556
4 |  | 1BHK | 366.4066 | 15.5002 | 537
2nd, 3rd & 4th Floor
1 |  | 1BHK | 340.3577 | 0 | 500 | 2nd, 3rd & 4th Floor
2 |  | 1BHK | 382.5526 | 0 | 552
3 |  | 1BHK | 382.5526 | 0 | 552
4 |  | 1BHK | 366.4066 | 0 | 537
Remarks:
1. Construction work was stopped. Work is same as last visit (06/05/2024). 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Recommended Rates/Other Charges of the Property have been revised on 27/02/2024. 8. The project has received first CC on 30/05/2019, But construction work is not yet completed. 9. As per RERA, completion period of project Jollity Lavanya is expired on 29/05/2024 but still project is under construction. 10. As checked on RERA portal on date 11/08/2025, we have observed that above project " Jollity Lavanya " is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Jollity Lavanya
Google Map :

## Note
21/09/2020.

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.83 | 10.5325 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.13 | 2.25 | 4.7925 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.4 | 6.6 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.77 | 1.2 | 2.124 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.75 | 1.2 | 2.1 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.49 | 2.1 | 1.029 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 292.544 | 27.178 |  |  | 0 | 0 |  | 0 | 0
|  |  | 292.544 | 27.178