## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-11 |  |  |  | Construction % is given extra plz check while next visit.
Name of the builder group |  |  |  | Puranik Tokyo Bay Private Limited
Name of the builder company |  |  |  | Puranik Tokyo Bay Private Limited
Name of the Project |  |  |  | IKIGAI Phase 1
Contact Details ( Name & Contact No.) |  |  |  | Mr. Prathmesh Ghawane - 9152034971
Site Person - Contact Details (Name & Contact No.) |  |  |  | Security
Name / No of the Building |  |  |  | Building Type A1 (Hana ) Building Type A2 (Ayami)
Docouments Provided |  |  |  | Approved Plans, CC
RERA Name/No. |  |  |  | IKIGAI Phase 1 Building Type A1 (Hana ) Building Type A2 (Ayami) P51700006605
Project location details |  | IKIGAI Phase 1, Survey No.45/2/A, 45/2/B, 45/4, 45/5, 45/9/A, 45/9/B, 45/10/A & Amp; 45/10/B, near KIPL Morya, Internal Road, Owale, Thane West, Thane, Thane.
Survey No |  | 45/2/A, 45/2/B, 45/4, 45/5, 45/9/A, 45/9/B, 45/10/A & Amp; 45/10/B
Road |  | Internal Road |  | Locality/Village |  | Owale
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400615
Nearby Landmark |  | KIPL Morya |  | Distance from city centre: |  | 10.1 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot/Aarambh Apartment
West | NA | 40.0 M Wide D.P Road |  |  | Internal Road
North | NA | Other Plot |  |  | Open Plot
South | NA | Building Type B |  |  | Open Plot/KIPL Morya
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.262722,72.956250
Location Link |  | https://maps.app.goo.gl/aru7kYMfXdAY5mFy5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 9921.1
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 4.3398 |  |  |  | 5.4398
Total FSI availaible for the project |  |  |  | 5.4398
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 53969.1 |  |  |  | 5.4398 | without club house
Total number of Buildings |  |  |  | 2 Building |  |  |  | 54091.68
Approval Detail : Plan approval
Layout Approval No |  | TMCB/RB/2023/APL/00086 |  |  | Dated | 2023-10-31
Approved Floor plan No. |  | TMCB/RB/2023/APL/00086 |  |  | Dated | 2023-10-31
Commencement Certificate No. Valid Up to: |  | TMCB/RB/2023/APL/00086 |  |  | Dated | 2023-10-31
Building Type A1 = LG2 & LG1 + Gr/St + 1st to 40th Floor Building Type A2 = LG2 & LG1 + Gr/St + 1st to 40th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved Builtup Area of Building A1 & A2 (Sq.Mt) |  |  | 36176.6
Approved no of units |  |  | Flats - 624
Approved no of Floors |  |  | Building Type A1 (Hana) = LG2 & LG1 + Gr/St + 1st to 40th Floor Building Type A2 (Ayami) = LG2 & LG1 + Gr/St + 1st to 40th Floor
Proposed no of Floors |  |  | Building Type A1(Hana) & A2(Ayami) = LG2 & LG1 + Gr/St + 1st to 40th Floor |  |  |  |  | https://puraniks-ikigai.com/?cstm_ppc_keyword=Ikigai%20thane&cstm_ppc_placement=ProjectNewPrice&cstm_ppc_device=c&cstm_ppc_campaign=Brand&cstm_ppc_channel=GoogleSearch&SRD=7019F000000MKWaQAO&gclid=Cj0KCQiA2KitBhCIARIsAPPMEhL845gBifpM2ZUm6xg-8Ze5S2QFEyziYNSzExXGgXnDzEnkIFK9l9saAkHjEALw_wcB&utm_source=googlesearch&utm_medium=cpc&utm_campaign=brand
Building Type A2 = LG2 & LG1 + Gr/St + 1st to 40th Floor
Expected Completion |  |  | As per RERA - 30/12/2031
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Compound Wall, M.S Gate, Jogging Track, Sewage Treatment Plant, Rain Water Harvesting, Car Parking, Club Housem, Gymnasium, 24x7 Security, Yoga/Meditation Area, Landscaping & Tree Planting, Fire Fighting System, Flower Garden, 24X7 Water Supply, Power Backup, Fire Sprinklers, Children's Play Area, Closed Car Parking, Swimming Pool, Lifts etc. |  |  |  |  | https://housing.com/in/buy/projects/page/96142-ikigai-by-puraniks-builders-pvt-ltd-in-kasarvadavali-thane-west
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building Type A1(Hana) = LG2 & LG1 + Gr/St + 1st to 40th Floor Building Type A2(Ayami) = LG2 & LG1 + Gr/St + 1st to 40th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 9.1 Floor Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 40
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 15 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 9.1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10
Excavation |  | 40 | 100% | 31.17% |  | 59.96% |  | Excavation in process | 20
Plinth |  | 40 | 100% |  |  |  |  | Excavation Completed | 40
RCC (Including podiums) |  | 15 | 36.59% |  |  |  |  | Footing in Process | 10
Brickwork | Brickwork & Internal Plaster | 13 | 32.5% |  |  |  |  | Footing Completed | 20
Internal Plaster | Brickwork & Internal Plaster | 9.75 | 24.38% |  |  |  |  | Basement 1 | 30
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9.1 | 22.75% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 40
Construction details: |  | Building Type A2(Ayami) = LG2 & LG1 + Gr/St + 1st to 40th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 6 Floor, Internal Plaster upto 4.5 Floor, External Plaster upto 4.2 Floor Completed
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 40
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 6 Floor, Internal Plaster upto 4.5 Floor, External Plaster upto 4.2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10
Excavation |  | 40 | 100% | 20.82% |  | 52.69% |  | Excavation in process | 20
Plinth |  | 40 | 100% |  |  |  |  | Excavation Completed | 40
RCC (Including podiums) |  | 8 | 19.51% |  |  |  |  | Footing in Process | 10
Brickwork | Brickwork & Internal Plaster | 6 | 15% |  |  |  |  | Footing Completed | 20
Internal Plaster | Brickwork & Internal Plaster | 4.5 | 11.25% |  |  |  |  | Basement 1 | 30
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4.2 | 10.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 40
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000 |  |  | 8900 to 10000 | 2024-03-31 | Viraj
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 300000
Clubhouse Maintenance |  |  |  |  | 25000
Water Connection Charges |  |  |  |  | 25000
Gas Connection Charges |  |  |  |  | NA
Electric Meter Installation |  |  |  |  | 30000
Society Formation Charges |  |  |  |  | 10000
Advance Maintenance Charges (For 2Years) |  |  |  |  | 30000
Recommended rate of Parking |  |  |  |  | 5,00,000/-
Distressed valuation of the Property |  |  |  |  | 8000
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building Type A1 |  | 312 |  | 131894.3059 |  | 197841.4589 |  | 194
Building Type A2 |  | 312 |  | 118420.3613 |  | 177630.5419
Total |  | 624 |  | 250314.6672 |  | 375472.0008
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building Type A1 (Hana)
2nd & 1st Lower Ground Floor For Parking | [7 empty] | 312
Ground Floor For Entrance Lobby, Society Office, Fire Control Room, Meter Room, Driver's Room & Parking
1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor
1 |  | 2BHK | 468.9875 | 0 | 703.4812 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  | 41.1392 | 41.5608 |  | 12401,..,4001 | 12401 | 4001
2 |  | 2BHK | 468.9875 | 0 | 703.4812 | [5 empty] | 12402,..,4002 | 12402 | 4002
3 |  | 2BHK | 490.946 | 0 | 736.4191 | [5 empty] | 12403,..,4003 | 12403 | 4003
4 |  | 2BHK | 491.1613 | 0 | 736.742 | [5 empty] | 12404,..,4004 | 12404 | 4004
5 |  | 1BHK | 291.812 | 0 | 437.7181 | [5 empty] | 12405,..,4005 | 12405 | 4005
6 |  | 1BHK | 291.812 | 0 | 437.7181 |  |  | 9138.3024 |  |  | 12406,..,4006 | 12406 | 4006
7 |  | 1BHK | 385.2436 | 0 | 577.8653 |  |  | 9344.7377 |  |  | 12407,..,4007 | 12407 | 4007
8 |  | 2BHK | 485.4564 | 0 | 728.1846 | [5 empty] | 12408,..,4008 | 12408 | 4008
3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area)
1 |  | 2BHK | 468.9875 | 0 | 703.4812 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 301,..,3801 | 301 | 3801
2 |  | 2BHK | 468.9875 | 0 | 703.4812 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  | 9666.214 |  |  | 302,..,3802 | 302 | 3802
3 |  | 2BHK | 490.946 | 0 | 736.4191 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 303,..,3803 | 303 | 3803
4 |  | 2BHK | 491.1613 | 0 | 736.742 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 304,..,3804 | 304 | 3804
5 |  | 1BHK | 291.812 | 0 | 437.7181 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 305,..,3805 | 305 | 3805
6 |  | 1BHK | 291.812 | 0 | 437.7181 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 306,..,3806 | 306 | 3806
7 |  | Refuge Area |  |  |  | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 307,..,3807 | 307 | 3807
8 |  | 2BHK | 485.4564 | 0 | 728.1846 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 308,..,3808 | 308 | 3808
Building Type A2 ( Ayami)
2nd & 1st Lower Ground Floor For Parking
Ground Floor For Entrance Lobby, Society Office, Fire Control Room, Meter Room, Driver's Room & Parking
1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor
1 |  | 1BHK | 291.812 | 0 | 437.7181 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  | 25.654 |  |  | 12401,..,4001 | 12401 | 4001
2 |  | 1BHK | 291.812 | 0 | 437.7181 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  |  |  |  | 12402,..,4002 | 12402 | 4002
3 |  | 2BHK | 490.946 | 0 | 736.4191 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  |  |  |  | 12403,..,4003 | 12403 | 4003
4 |  | 2BHK | 491.1613 | 0 | 736.742 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  |  |  |  | 12404,..,4004 | 12404 | 4004
5 |  | 1BHK | 291.812 | 0 | 437.7181 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  |  |  |  | 12405,..,4005 | 12405 | 4005
6 |  | 1BHK | 291.812 | 0 | 437.7181 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  |  |  |  | 12406,..,4006 | 12406 | 4006
7 |  | 1BHK | 385.0283 | 0 | 577.5424 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  |  |  |  | 12407,..,4007 | 12407 | 4007
8 |  | 2BHK | 503.0017 | 0 | 754.5026 | 1st, 2nd, 4th to 7th, 9th to 12th, 14th to 17th, 19th to 22nd, 24th to 27th, 29th to 32nd, 34th to 37th, 39th & 40th Floor |  | 43.8338 |  |  | 12408,..,4008 | 12408 | 4008
3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area)
1 |  | 1BHK | 291.812 | 0 | 437.7181 | 3rd, 8th, 13th, 18th, 23rd, 28th, 33rd & 38th Floor (Part Refuge Area) |  |  |  |  | 301,..,3801 | 301 | 3801
2 |  | 1BHK | 291.812 | 0 | 437.7181 | [5 empty] | 302,..,3802 | 302 | 3802
3 |  | 2BHK | 490.946 | 0 | 736.4191 | [5 empty] | 303,..,3803 | 303 | 3803
4 |  | 2BHK | 491.1613 | 0 | 736.742 |  |  | 9612.5919 |  |  | 304,..,3804 | 304 | 3804
5 |  | 1BHK | 291.812 | 0 | 437.7181 | [5 empty] | 305,..,3805 | 305 | 3805
6 |  | 1BHK | 291.812 | 0 | 437.7181 | [5 empty] | 306,..,3806 | 306 | 3806
7 |  | Refuge Area | [8 empty] | 307,..,3807 | 307 | 3807
8 |  | 2BHK | 503.6476 | 0 | 755.4713 | [5 empty] | 308,..,3808 | 308 | 3808
Remarks:
1 | Construction work is in process at the time of visit. (Internal visit not allowed)
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet
5 | We have considered rate by verifying it from market inquire.
6 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes).
7 | Car parking is subjected to authentic documentation.
8 | We have done APF Report for Phase1 (Building Type A1 & A2) as it is registered on RERA.
9 | We have updated revised approved plan & CC for Building Type A1 & A2 (on 20/01/2024)
10 | Since Project's Builtup Area is above 20000 Sq.M. Please check for Environment Clearance Certificate.
9 | On Site, we meet Ms. Aashna (sales) - 8169789669
11 | Recommended Rates/Other Charges of the Property have been revised on 31/03/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | IKIGAI Phase 1
Layout :
Google Map :
Formulas:
Owale = [Owale, row above]
Building Type A1
Building Type A2
A2
A1
A1
Lower Ground 2
Ground Floor
Lower Ground 1
Lower Ground 2
Ground Floor
Lower Ground 1
Lower Ground 2
A1 & A2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  | 1bhk | 319 | 494.45 | 8089.7967 | 4000000
99 Acres |  | 2bhk | 535 | 829.25 | 8540.2472 | 7082000
Average |  |  |  |  | 8315.022
Valuation Adopted