## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/09/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-11
Name of the builder group |  |  |  | Macrotech Developers Limited
Name of the builder company |  |  |  | Macrotech Developers Limited
Name of the Project |  |  |  | Lodha Crown Kolshet - Tower 1 to 4
Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajendra Giri - 9820248856
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Rajendra Giri - 9820248856
Name / No of the Building |  |  |  | Tower 1 to 4
Docouments Provided |  |  |  | Approved Plans, CC
RERA Name & No. |  |  |  | Lodha Crown Kolshet­Tower 1 (P51700045858) Lodha Crown Kolshet ­Tower 2 (P51700049074) Lodha Crown Kolshet ­Tower 3 (P51700046319) Lodha Crown Kolshet-Tower 4 (P51700046037)
Project location details |  | Lodha Crown Kolshet - Tower 1 to 4, Survey No.54/1, 55/14, 55/15,59/1, 60/1, 60/2/A, 60/2/B, 61/1, …….. 104/1B, 104/1C, 104/2, 274/1, near Lodha Sterling Apartment, Kolshet Road, , Kolshet, Thane West, Thane, Thane - 400607.
Survey No |  | 54/1, 55/14, 55/15,59/1, 60/1, 60/2/A, 60/2/B, 61/1, …….. 104/1B, 104/1C, 104/2, 274/1
Locality |  | NA
Road |  | Kolshet Road |  | Village |  | Kolshet
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400607
Nearby Landmark |  | Lodha Sterling Apartment |  | Distance from city centre: |  | 6.0 KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 40.0 M Wide Kolshet Road |  |  | Kolshet Road
West | NA | Internal Road/ Tower A |  |  | Internal Road / Lodha Clariant Tower A- iThink
North | NA | MLCP/Tower 4 |  |  | Building
South | NA | Other Plot |  |  | Belgrave Square
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.2347373,72.9881413
Location Link |  | https://goo.gl/maps/D2zfaRD54Aup1m8y9
Area Statement Details :
Total land area of the project in Sq. Mt. (Plot B2) |  |  |  | 14936.18
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.6682
Total FSI availaible for the project |  |  |  | 3.7682
Total Approved Builtup area of the project (Sq.Mt) (Plot B2) |  |  |  | 56282.91 |  |  |  |  | 34021.93
Total number of Buildings |  |  |  | 4 Towers
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | The Municipal Corporation of The City of Thane
Layout Approval No |  | S05/0083/14/TMC/TD-DP/TPS/4442/23 |  |  | Dated | 2023-07-14
Approved Floor plan No. (Tower 1 = 2nd to 23rd Floor & Tower 4) |  | V.P.No.S05/0083/14/TMC/TD-DP/TPS/4135/22 |  |  | Dated | 2022-07-15
Approved Floor plan No. (Tower 1= Gr + 1st Floor & Tower 2) |  | S05/0083/14/TMC/TD-DP/TPS/4442/23 |  |  | Dated | 2023-07-14
Approved Floor plan No. (Tower 3) |  | NewS05/0083/14/TMC/TDD/0157/(P/C)/2024/AutoDCR |  |  | Dated | 2024-09-27
Commencement-CC No Valid Up to: Plot B2 |  | NewS05/0083/14/TMC/TDD/0157/(P/C)/2024/AutoDCR |  |  | Dated | 2024-09-27
Tower 1 = Gr/Stilt + 1st to 23rd Floor Tower 2 = Gr/Stilt + 1st to 23rd Floor Tower 3 = Gr/St Floor Tower 4 = Gr/Stilt + 1st to 6th (Part Parking + Part Resi.) + 7th to 23rd Floor
Environmental Clearance Certificate : |  | SEIAA-EC-0000000343 |  |  | Dated | 2018-06-13
Plot bearing S. No. 62, 63/1, 63/2, 63/3, 63/4, 63/5, 63/6, 63/7, 63/8,….274/1,60/8B, 60/9B, 60/10A,60/11B Total BUA area (sq. m.): 1410519.89 BUA Area of (Plot B) - 11325 sqm
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved Builtup Area of Tower 1 to 4 (Sq.Mt) |  |  | 54087.44 | [5 empty] | check bua during next update
Approved no of units |  |  | Flats - 1418, Shop - 15
Approved no of Floors |  |  | Tower 1 = Gr/Stilt + 1st to 23rd Floor Tower 2 = Gr/Stilt + 1st to 11th Floor Tower 3 = Gr/Stilt + 1st to 23rd Floor Tower 4 = Gr/Stilt + 1st to 7th Floor (Part Parking + Part Resi) + 8th to 23rd Floor
Proposed no of Floors |  |  | Tower 1 = Gr/Stilt + 1st to 23rd Floor
Tower 2 = Gr/Stilt + 1st to 23rd Floor
Tower 3 = Gr/St + 1st to 23rd Floor
Tower 4 = Gr/Stilt + 1st to 7th Floor (Part Parking + Part Resi) + 8th to 23rd Floor
Expected Completion |  |  | As per RERA - Tower 1 = 31/03/2026 Tower 2 = 31/07/2027 Tower 3 = 30/09/2027 Tower 4 = 31/05/2026
Projected life of the structure |  |  | 60 Years After Completion |  |  |  |  | https://housing.com/in/buy/projects/page/279911-lodha-crown-kolshet-tower-3-by-lodha-group-in-azad-nagar
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 24X7 Water Supply, Cycling & Jogging Track, Internal Roads Party Lawn, Video Door Security, CCTV, Lift(s), Paved Compound, Power Backup, Closed Car Parking, Jogging Track, Community Hall, Swimming Pool etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 12 Floor Completed | , Finishing upto 12 Floor
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Construction details: |  | Tower 1 = Gr/Stilt + 1st to 23rd Floor | [5 empty] | Completed | Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Piling Work in process | 5.75
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 12 Floor Completed | [5 empty] | Excavation in process | 11.5
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation Completed | 23
Excavation |  | 23 | 100% | 92.61% |  | 95% |  | Footing in Process | 5.75
Plinth |  | 23 | 100% |  |  |  |  | Footing Completed | 11.5
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Basement 1 | 0
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 3 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 4 | 0
Flooring & Fitting | Flooring & Fitting | 23 | 100% |  |  |  |  | Plinth in process | 17.25
Painting & Wooden |  | 23 | 100% |  |  |  |  | Plinth completed | 23
Building Common Amenities | Building Common Amenities | 12 | 52.17% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 22 Floor, External Plaster upto 20 Floor, Flooring upto 5 Floor Completed | , Internal Plaster upto 22 Floor, External Plaster upto 20 Floor, Flooring upto 5 Floor
Possession |  | 0 | 0% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork
Construction details: |  | Tower 2 = Gr/Stilt + 1st to 23rd Floor | [5 empty] | Completed | Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Piling Work in process | 5.75
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 22 Floor, External Plaster upto 20 Floor, Flooring upto 5 Floor Completed | [5 empty] | Excavation in process | 11.5
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation Completed | 23
Excavation |  | 23 | 100% | 75.54% |  | 90.22% |  | Footing in Process | 5.75
Plinth |  | 23 | 100% |  |  |  |  | Footing Completed | 11.5
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Basement 1 | 0
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster | Brickwork & Internal Plaster | 22 | 95.65% |  |  |  |  | Basement 3 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 86.96% |  |  |  |  | Basement 4 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 21.74% |  |  |  |  | Plinth in process | 17.25
Painting & Wooden |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Excavation, Plinth Completed
Possession |  | 0 | 0% |  |  |  |  | Excavation, Plinth
Construction details: |  | Tower 3 = Gr/St + 1st to 23rd Floor | [5 empty] | Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Piling Work in process | 5.75
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Excavation in process | 11.5
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation Completed | 23
Excavation |  | 23 | 100% | 10% |  | 45% |  | Footing in Process | 5.75
Plinth |  | 23 | 100% |  |  |  |  | Footing Completed | 11.5
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Basement 1 | 0
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 2 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 3 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 4 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Plinth in process | 17.25
Painting & Wooden |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 20 Floor Completed | , Flooring upto 22 Floor, Painting upto 20 Floor
Possession |  | 0 | 0% |  |  |  |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster |  | cost sheet | 2022-09-13
Construction details: |  | Tower 4 = Gr/Stilt + 1st to 7th Floor (Part Parking + Part Resi) + 8th to 23rd Floor | [5 empty] | Completed | Completed | Verbal | 2023-08-31
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Piling Work in process | 5.75 | #DIV/0!
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 20 Floor Completed | [5 empty] | Excavation in process | 11.5
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation Completed | 23
Excavation |  | 23 | 100% | 88.91% |  | 94.78% |  | Footing in Process | 5.75
Plinth |  | 23 | 100% |  |  |  |  | Footing Completed | 11.5
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Basement 1 | 0
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 2 | 0
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 3 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 4 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 95.65% |  |  |  |  | Plinth in process | 17.25
Painting & Wooden |  | 20 | 86.96% |  |  |  |  | Plinth completed | 23
Building Common Amenities | Building Common Amenities | 0 | 0%
Possession |  | 0 | 0% |  |  |  |  | 11300 to 11700 | Sanket
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  | 22000 to 29000 | SAnket
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 12400 |  |  | 12000 to 12400 by bhargav Tower 2 Flat 1114 on 20/09/2025
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 29000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Utility Connection & Related Expenses |  |  |  |  | 100000
Land under construction (LUC)Reimbursement charges |  |  |  |  | 50000
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges for 3 years |  |  |  |  | 90000
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 9920 |  |  |  | rate sheet
Commercial Area Details : Shop | [8 empty] | market | 19205.4301
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Plot B2 | Tower 1 | 15 |  | 2419.4243 |  | 3750.1076 |  |  | rate sheet
Total |  | 15 |  | 2419.4243 |  | 3750.1076
Residential Area Details : | [8 empty] | market
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | market
Plot B2 | Tower 1 | 412 |  | 132487.8329 |  | 205356.141 |  |  | 11300 | 19205.4301
| Tower 2 | 417 |  | 134626.1015 |  | 208670.4573
| Tower 3 | 355 |  | 187333.5344 |  | 290366.9784
| Tower 4 | 234 |  | 122080.5518 |  | 189224.8554
Total |  | 1418 |  | 576528.0206 |  | 893618.432
Grand Total |  | 1433 |  | 578947.4449 |  | 897368.5396
Building details Floor Wise
Details of Residential & Commercial in Building | [9 empty] | #DIV/0!
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached loft area | Saleable area Loading : | Floor
[5 empty] | 60% |  |  | 10.764
Plot B2
Tower 1 | [8 empty] | 23845.4473
Ground Floor for Residential & Parking | [8 empty] | 19205.4301
1 |  | Shop | 159.6301 | 0 | 247.4267 | Ground Floor for Residential & Parking |  | 20705.4906
2 |  | Shop | 177.606 | 0 | 275.2893
3 |  | Shop | 177.606 | 0 | 275.2893
4 |  | Shop | 159.6301 | 0 | 247.4267 |  |  |  | 21431.999
5 |  | Shop | 159.6301 | 0 | 247.4267 |  |  |  | 15252.715
6 |  | Shop | 177.606 | 0 | 275.2893 |  |  | 23037.127 |  | 11737.9577
7 |  | Shop | 177.606 | 0 | 275.2893
8 |  | Shop | 159.6301 | 0 | 247.4267
9 |  | Shop | 123.4631 | 0 | 191.3678 |  |  |  | 21431.999 |  | 281.1245
10 |  | Shop | 136.2722 | 0 | 211.222 |  |  |  | #DIV/0! |  | 28.2285
11 |  | Shop | 177.606 | 0 | 275.2893 |  |  | 23037.127
12 |  | Shop | 159.6301 | 0 | 247.4267
13 |  | Shop | 159.6301 | 0 | 247.4267
14 |  | Shop | 177.606 | 0 | 275.2893
15 |  | Shop | 136.2722 | 0 | 211.222
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 55% |  |  | 10.764
Plot B2
Tower 1 | [8 empty] | 12527.3388
Ground Floor for Residential & Parking | [8 empty] | 11737.9577
1 |  | 1 | 303.8516 | 0 | 470.9699 | Ground Floor for Residential & Parking |  | 12102.6832
2 |  | 1 | 303.8516 | 0 | 470.9699
3 |  | 1 | 303.8516 | 0 | 470.9699 |  |  | 28.2261
1st Floor
1 |  | 1 | 303.8516 | 0 | 470.9699 | 1st Floor
2 |  | 1 | 303.8516 | 0 | 470.9699
3 |  | 1 | 303.8516 | 0 | 470.9699
4 |  | 1 | 303.8516 | 0 | 470.9699
5 |  | 1 | 303.8516 | 0 | 470.9699
6 |  | 1 | 303.8516 | 0 | 470.9699
7 |  | 1 | 303.8516 | 0 | 470.9699
8 |  | 1 | 303.8516 | 0 | 470.9699
9 |  | 1 | 303.8516 | 0 | 470.9699
10 |  | 1 | 303.8516 | 0 | 470.9699
11 |  | 1 | 303.8516 | 0 | 470.9699
12 |  | 1 | 303.8516 | 0 | 470.9699
14 |  | 1 | 303.8516 | 0 | 470.9699
15 |  | 1 | 303.8516 | 0 | 470.9699
16 |  | 1 | 303.8516 | 0 | 470.9699
17 |  | 1 | 303.8516 | 0 | 470.9699
18 |  | 1 | 303.8516 | 0 | 470.9699
19 |  | 1 | 303.8516 | 0 | 470.9699 |  |  | 28.2261
2nd to 7th Floor, 9th to 12th Floor, 14th to 17th (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
1 |  | 1 | 322.1665 | 0 | 499.3581 | 2nd to 7th Floor, 9th to 12th Floor, 14th to 17th (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
2 |  | 1 | 322.1665 | 0 | 499.3581
3 |  | 1 | 322.1665 | 0 | 499.3581
4 |  | 1 | 322.1665 | 0 | 499.3581
5 |  | 1 | 322.1665 | 0 | 499.3581
6 |  | 1 | 322.1665 | 0 | 499.3581
7 |  | 1 | 322.1665 | 0 | 499.3581
8 |  | 1 | 322.1665 | 0 | 499.3581
9 |  | 1 | 322.1665 | 0 | 499.3581
10 |  | 1 | 322.1665 | 0 | 499.3581
11 |  | 1 | 322.1665 | 0 | 499.3581
12 |  | 1 | 322.1665 | 0 | 499.3581
13 |  | 1 | 322.1665 | 0 | 499.3581
14 |  | 1 | 322.1665 | 0 | 499.3581
15 |  | 1 | 322.1665 | 0 | 499.3581
16 |  | 1 | 322.1665 | 0 | 499.3581
17 |  | 1 | 322.1665 | 0 | 499.3581
18 |  | 1 | 322.1665 | 0 | 499.3581
8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
1 |  | 1 | 322.1665 | 0 | 499.3581 | 8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
2 |  | 1 | 322.1665 | 0 | 499.3581
3 |  | 1 | 322.1665 | 0 | 499.3581
4 |  | 1 | 322.1665 | 0 | 499.3581
5 |  | 1 | 322.1665 | 0 | 499.3581
6 |  | 1 | 322.1665 | 0 | 499.3581
7 |  | 1 | 322.1665 | 0 | 499.3581
8 |  | 1 | 322.1665 | 0 | 499.3581
9 |  | 1 | 322.1665 | 0 | 499.3581
10 |  | 1 | 322.1665 | 0 | 499.3581
11 |  | 1 | 322.1665 | 0 | 499.3581
12 |  | 1 | 322.1665 | 0 | 499.3581
13 |  | 1 | 322.1665 | 0 | 499.3581
14 |  | 1 | 322.1665 | 0 | 499.3581
15 |  | Refuge Area
16 |  | 1 | 322.1665 | 0 | 499.3581
17 |  | 1 | 322.1665 | 0 | 499.3581
18 |  | 1 | 322.1665 | 0 | 499.3581
23rd Floor (24th Floor as per Builder) (Part Refuge Area)
1 |  | 1 | 322.1665 | 0 | 499.3581 | 23rd Floor (24th Floor as per Builder) (Part Refuge Area)
2 |  | 1 | 322.1665 | 0 | 499.3581
3 |  | 1 | 322.1665 | 0 | 499.3581
4 |  | 1 | 322.1665 | 0 | 499.3581
5 |  | 1 | 322.1665 | 0 | 499.3581 |  |  |  |  | #DIV/0!
6 |  | 1 | 322.1665 | 0 | 499.3581
7 |  | 1 | 322.1665 | 0 | 499.3581
8 |  | 1 | 322.1665 | 0 | 499.3581
9 |  | 1 | 322.1665 | 0 | 499.3581
10 |  | 1 | 322.1665 | 0 | 499.3581
11 |  | 1 | 322.1665 | 0 | 499.3581 |  |  | 10012.8544
12 |  | 1 | 322.1665 | 0 | 499.3581
13 |  | 1 | 322.1665 | 0 | 499.3581
14 |  | 1 | 322.1665 | 0 | 499.3581 |  |  | 11429.0247
15 |  | Refuge Area
16 |  | 2 | 443.6921 | 0 | 687.7227
17 |  | 1 | 322.1665 | 0 | 499.3581 |  |  | 10.764
18 |  | 1 | 322.1665 | 0 | 499.3581
Tower 2 | [7 empty] | 28.1985 | 11803.3372
Ground Floor for Entrance Lobby, Society Office, Letter Box, Meter Room, Residential & Parking | [8 empty] | #DIV/0!
1 |  | 1 | 322.4894 | 0 | 499.8586 | Ground Floor for Entrance Lobby, Society Office, Letter Box, Meter Room, Residential & Parking
2 |  | 1 | 322.4894 | 0 | 499.8586
3 |  | 1 | 322.4894 | 0 | 499.8586 |  |  | 11403.2241
4 |  | 1 | 322.4894 | 0 | 499.8586
5 |  | 1 | 322.4894 | 0 | 499.8586
6 |  | Meter Room
7
8 |  | 1 | 322.4894 | 0 | 499.8586
9 |  | 1 | 322.4894 | 0 | 499.8586 |  |  | 28.2261
1st to 7th Floor, 9th to 12th Floor, 14th to 17th (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
1 |  | 1 | 322.4894 | 0 | 499.8586 | 1st to 7th Floor, 9th to 12th Floor, 14th to 17th (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
2 |  | 1 | 322.4894 | 0 | 499.8586
3 |  | 1 | 322.4894 | 0 | 499.8586
4 |  | 1 | 322.4894 | 0 | 499.8586
5 |  | 1 | 322.4894 | 0 | 499.8586
6 |  | 1 | 322.4894 | 0 | 499.8586
7 |  | 1 | 322.4894 | 0 | 499.8586
8 |  | 1 | 322.4894 | 0 | 499.8586
9 |  | 1 | 322.4894 | 0 | 499.8586
10 |  | 1 | 322.4894 | 0 | 499.8586
11 |  | 1 | 322.4894 | 0 | 499.8586
12 |  | 1 | 322.4894 | 0 | 499.8586
14 |  | 1 | 322.4894 | 0 | 499.8586
15 |  | 1 | 322.4894 | 0 | 499.8586
16 |  | 1 | 322.4894 | 0 | 499.8586
17 |  | 1 | 322.4894 | 0 | 499.8586
18 |  | 1 | 322.4894 | 0 | 499.8586
19 |  | 1 | 322.4894 | 0 | 499.8586
8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
1 |  | 1 | 322.4894 | 0 | 499.8586 | 8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
2 |  | 1 | 322.4894 | 0 | 499.8586
3 |  | 1 | 322.4894 | 0 | 499.8586
4 |  | 1 | 322.4894 | 0 | 499.8586
5 |  | 1 | 322.4894 | 0 | 499.8586
6 |  | 1 | 322.4894 | 0 | 499.8586
7 |  | 1 | 322.4894 | 0 | 499.8586
8 |  | 1 | 322.4894 | 0 | 499.8586
9 |  | 1 | 322.4894 | 0 | 499.8586
10 |  | 1 | 322.4894 | 0 | 499.8586
11 |  | 1 | 322.4894 | 0 | 499.8586
12 |  | 1 | 322.4894 | 0 | 499.8586
14 |  | Refuge Area
15 |  | 1 | 322.4894 | 0 | 499.8586
16 |  | 1 | 322.4894 | 0 | 499.8586
17 |  | 1 | 322.4894 | 0 | 499.8586
18 |  | 1 | 322.4894 | 0 | 499.8586
19 |  | 1 | 322.4894 | 0 | 499.8586 |  |  | 28.2261
23rd Floor (24th Floor as per Builder) (Part Refuge Area)
1 |  | 1 | 322.4894 | 0 | 499.8586 | 23rd Floor (24th Floor as per Builder) (Part Refuge Area)
2 |  | 1 | 322.4894 | 0 | 499.8586
3 |  | 1 | 322.4894 | 0 | 499.8586
4 |  | 1 | 322.4894 | 0 | 499.8586
5 |  | 1 | 322.4894 | 0 | 499.8586
6 |  | 1 | 322.4894 | 0 | 499.8586
7 |  | 1 | 322.4894 | 0 | 499.8586
8 |  | 1 | 322.4894 | 0 | 499.8586
9 |  | 1 | 322.4894 | 0 | 499.8586
10 |  | 1 | 322.4894 | 0 | 499.8586
11 |  | 1 | 322.4894 | 0 | 499.8586
12 |  | 2BHK | 470.4944 | 0 | 729.2664
14 |  | Refuge Area
15 |  | 1 | 322.4894 | 0 | 499.8586
16 |  | 1 | 322.4894 | 0 | 499.8586
17 |  | 1 | 322.4894 | 0 | 499.8586
18 |  | 1 | 322.4894 | 0 | 499.8586
19 |  | 1 | 322.4894 | 0 | 499.8586
Tower 3 | [7 empty] | 45.8604
Ground Floor For Residential & (Part Meter Room, Society Office & Parking Area)
1 |  | 2 | 530.6652 | 0 | 822.5311 | Ground Floor For Residential & (Part Meter Room, Society Office & Parking Area)
2 |  | 2 | 530.6652 | 0 | 822.5311
3 |  | 2 | 530.6652 | 0 | 822.5311
4 |  | Gents & Ledies Changing Room
5 |  | Meter Room Area
6
7 |  | 2 | 530.6652 | 0 | 822.5311
8 |  | 2 | 530.6652 | 0 | 822.5311
9 |  | 2 | 530.6652 | 0 | 822.5311 |  |  | 10.764
- |  | Society Office & Telecom Room
10 |  | 2 | 530.6652 | 0 | 822.5311
11 |  | 2 | 530.6652 | 0 | 822.5311
12 |  | 2 | 530.6652 | 0 | 822.5311 |  |  | 11371.1465
- |  | Entrance Lobby
13 |  | 2 | 530.6652 | 0 | 822.5311
1st to 7th Floor, 9th to 12th Floor, 14th to 17th (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
1 |  | 2 | 530.6652 | 0 | 822.5311 | 1st to 7th Floor, 9th to 12th Floor, 14th to 17th (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
2 |  | 2 | 530.6652 | 0 | 822.5311
3 |  | 2 | 530.6652 | 0 | 822.5311
4 |  | 2 | 530.6652 | 0 | 822.5311
5 |  | 2 | 530.6652 | 0 | 822.5311
6 |  | 2 | 530.6652 | 0 | 822.5311
7 |  | 2 | 530.6652 | 0 | 822.5311
8 |  | 2 | 530.6652 | 0 | 822.5311
9 |  | 2 | 530.6652 | 0 | 822.5311
10 |  | 2 | 530.6652 | 0 | 822.5311
11 |  | 2 | 530.6652 | 0 | 822.5311
12 |  | 2 | 530.6652 | 0 | 822.5311
14 |  | 2 | 530.6652 | 0 | 822.5311
15 |  | 2 | 530.6652 | 0 | 822.5311
16 |  | 2 | 530.6652 | 0 | 822.5311
8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
1 |  | 2 | 530.6652 | 0 | 822.5311 | 8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
2 |  | 2 | 530.6652 | 0 | 822.5311
3 |  | 2 | 530.6652 | 0 | 822.5311
4 |  | 2 | 530.6652 | 0 | 822.5311
5 |  | 2 | 530.6652 | 0 | 822.5311
6 |  | 2 | 530.6652 | 0 | 822.5311
7 |  | 2 | 530.6652 | 0 | 822.5311
8 |  | 2 | 530.6652 | 0 | 822.5311
9 |  | 2 | 530.6652 | 0 | 822.5311
10 |  | 2 | 530.6652 | 0 | 822.5311
11 |  | 1 | 380.2921 | 0 | 589.4528
- |  | Refuge Area
12 |  | 1 | 380.2921 | 0 | 589.4528
14 |  | 2 | 530.6652 | 0 | 822.5311
15 |  | 2 | 530.6652 | 0 | 822.5311
16 |  | 2 | 530.6652 | 0 | 822.5311
23rd Floor (24th Floor as per Builder) (Part Refuge Area)
1 |  | 2 | 530.6652 | 0 | 822.5311 | 23rd Floor (24th Floor as per Builder) (Part Refuge Area)
2 |  | 2 | 530.6652 | 0 | 822.5311
3 |  | 2 | 530.6652 | 0 | 822.5311
4 |  | 2 | 530.6652 | 0 | 822.5311
5 |  | 2 | 530.6652 | 0 | 822.5311
6 |  | 2 | 530.6652 | 0 | 822.5311
7 |  | 2 | 530.6652 | 0 | 822.5311
8 |  | 2 | 530.6652 | 0 | 822.5311
9 |  | 2 | 530.6652 | 0 | 822.5311
10 |  | 2 | 530.6652 | 0 | 822.5311
11 |  | 2 | 530.6652 | 0 | 822.5311
- |  | Refuge Area
12 |  | 1 | 380.2921 | 0 | 589.4528
14 |  | 2 | 530.6652 | 0 | 822.5311
15 |  | 2 | 530.6652 | 0 | 822.5311
16 |  | 2 | 530.6652 | 0 | 822.5311
Tower 4
Ground Floor for Parking
1st to 6th Floor for Residential & Parking
1 |  | OWC (Double Height) |  |  |  | 1st to 6th Floor for Residential & Parking
2 |  | 2 | 527.6513 | 0 | 817.8595
3 |  | 2 | 527.6513 | 0 | 817.8595
4 |  | 2 | 527.6513 | 0 | 817.8595
5 |  | 2 | 527.6513 | 0 | 817.8595
6 |  | 2 | 527.6513 | 0 | 817.8595
7 |  | 2 | 527.6513 | 0 | 817.8595
7th Floor
1 |  | OWC (Double Height) |  |  |  | 7th Floor
2 |  | 2 | 527.6513 | 0 | 817.8595
3 |  | 2 | 527.6513 | 0 | 817.8595
4 |  | 2 | 527.6513 | 0 | 817.8595
5 |  | 2 | 527.6513 | 0 | 817.8595
6 |  | 2 | 527.6513 | 0 | 817.8595
7 |  | 2 | 527.6513 | 0 | 817.8595
8 |  | Amenity Area
9 | [7 empty] | 12031.5048
10
11
12
8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
1 |  | 2 | 527.6513 | 0 | 817.8595 | 8th Floor, 13th & 18th Floor (14th & 19th Floor as per builder) (Part Refuge Area)
2 |  | 2 | 527.6513 | 0 | 817.8595
3 |  | 1 | 347.0314 | 0 | 537.8986
3b |  | 1 | 321.736 | 0 | 498.6907
4 |  | Refuge Area
5 |  | 2 | 527.6513 | 0 | 817.8595
6 |  | 2 | 527.6513 | 0 | 817.8595
7 |  | 2 | 527.6513 | 0 | 817.8595 |  |  | 11004.3353
8 |  | 2 | 527.6513 | 0 | 817.8595
9 |  | 2 | 527.6513 | 0 | 817.8595
10 |  | 2 | 527.6513 | 0 | 817.8595
11 |  | 2 | 527.6513 | 0 | 817.8595
12 |  | 2 | 527.6513 | 0 | 817.8595
9th to 12th Floor, 14th to 17th Floor (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
1 |  | 2 | 527.6513 | 0 | 817.8595 | 9th to 12th Floor, 14th to 17th Floor (15th to 18th Floor as per Builder), 19th to 22nd Floor (20th to 23rd Floor as per Builder)
2 |  | 2 | 527.6513 | 0 | 817.8595
3 |  | 2 | 527.6513 | 0 | 817.8595
4 |  | 2 | 527.6513 | 0 | 817.8595
5 |  | 2 | 527.6513 | 0 | 817.8595
6 |  | 2 | 527.6513 | 0 | 817.8595
7 |  | 2 | 527.6513 | 0 | 817.8595
8 |  | 2 | 527.6513 | 0 | 817.8595
9 |  | 2 | 527.6513 | 0 | 817.8595
10 |  | 2 | 527.6513 | 0 | 817.8595
11 |  | 2 | 527.6513 | 0 | 817.8595
12 |  | 2 | 527.6513 | 0 | 817.8595
23rd Floor (24th Floor as per Builder) (Part Refuge Area)
1 |  | 2 | 527.6513 | 0 | 817.8595 | 23rd Floor (24th Floor as per Builder) (Part Refuge Area)
2 |  | 2 | 527.6513 | 0 | 817.8595
3a |  | 1 | 347.0314 | 0 | 537.8986
3b |  | 2 | 478.0292 | 0 | 740.9453
4 |  | Refuge Area
5 |  | 2 | 527.6513 | 0 | 817.8595
6 |  | 2 | 527.6513 | 0 | 817.8595
7 |  | 2 | 527.6513 | 0 | 817.8595
8 |  | 2 | 527.6513 | 0 | 817.8595
9 |  | 2 | 527.6513 | 0 | 817.8595
10 |  | 2 | 527.6513 | 0 | 817.8595
11 |  | 2 | 527.6513 | 0 | 817.8595
12 |  | 2 | 527.6513 | 0 | 817.8595
Remarks:
* | Tower 1 to 4 = Construction work is in process at the time of Visit. Internal photographs not allowed. Tower 3 = Excavation work is in the process.
* | Construction Details Taken From Mr. Rajendra Giri.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet. | [10 empty] | On Site, we meet Mr. Afsal.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved Layout plan, Floor plans & CC for Tower 2 (on 22/07/2023).
* | In Tower 1 on 1st Floor, Tower 2 & 3, Flat No. 13 is not mentioned on any floor in approved plan.
* | We have updated approved Floor plans Ground Floor & 1st Floor for Tower 1 (on 22/07/2023).
* | We have updated approved Floor plans of Tower 3 and CC for all Towers(on 15/10/2024).
* | We have updated Environment Clearance Certificate on 13/03/2024.
* | Recommended Rates / Other charges of the Property (Commercial) have been revised on 20/09/2025 on basis of Cost sheet.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mr. Ajay Songare |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Lodha Crown Kolshet - Tower 1 to 4
Layout
Google Map :
T1
T2
T1
T2
T1
T1
T1
T4
4th Floor
2nd Floor
T1
T4
4th Floor
7th Floor
T2
Tower 1
Tower 3
Tower 4
Tower 2
Tower 1
Tower 2
Tower 3
Tower 4
T4
T4
T2
T1
T1
T2
T4
T1
T4
T2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted