## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 21/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-20
Name of the builder group |  |  |  | M/s.Aurum Platz IT Private Limited |  |  |  |  | Pandurang Bidkar
Name of the builder company |  |  |  | M/s.Aurum Platz IT Private Limited
Name of the Project |  |  |  | Q Islands R4 to R7
Contact Details ( Name & Contact No.) |  |  |  | Miss. Tejal-8169917399
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Sudesh Kadam - 8828079398 |  |  |  | Miss. Tejal-8169917399
Name / No of the Building |  |  |  | Building no.R4 & R5
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Q Islands R4 = P51700023775 Q Islands R5 = P51700023911 Q Islands R6 = P51700048523 Q Islands R7 = P51700048656
Project location details |  | Q Islands R4 to R7, Plot No.GEN -4/1, near Aurum Q Residences, Q Park Road, Ghansoli, Ghansoli, Thane, Thane.
Plot No |  | GEN -4/1
Road |  | Q Park Road |  | Locality |  | Ghansoli
City |  | Ghansoli |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400710
Nearby Landmark |  | Aurum Q Residences |  | Distance from city centre: |  | 1.7Km from Ghansoli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Aurum Ventures Pvt. Ltd
West | NA | NA |  |  | Road
North | NA | NA |  |  | Road
South | NA | NA |  |  | Q Park Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA | [7 empty] | Changed on 20/8/2025
Latitude,Longitude |  | 19.120597,73.007958 | [5 empty] | 19.1199784,73.0083409
Location Link |  | https://maps.app.goo.gl/W8rMrwXZ9Mm8GPpT7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | NA
Permissible FSI |  |  |  | NA
Permissible TDR/Paid FSI |  |  |  | NA
Total FSI availaible for the project |  |  |  | NA
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | NA
Total number of Buildings |  |  |  | 04 Buildings
Approval Detail : Plan approval
Layout Approval No |  | NA |  |  | Dated | NA
Wing R4
Approved Floor plan No. Wing R4 |  | EE/SPA/GEN-4/1/E-31223/of 2019 |  |  | Dated | 2019-12-26
Commencement Certificate No. Wing R4 |  | EE/SPA/GEN-4/1/E-31223/of 2019 |  |  | Dated | 2019-12-26
Valid Up to: Plinth Level
Wing R5
Approved Floor plan No. Wing R5 (Gr. + 21st Floor) |  | EE/Dn. II/MHP/SPA/GEN-4/1/C62272/of 2022 |  |  | Dated | 2022-08-03
Approved Floor plan No. Wing R5 (22nd to 39th Floor) |  | EE/Dn.II/MHP/SPA/I/1872/of 2023 |  |  | Dated | 2023-06-07
Commencement Certificate No. Wing R5 |  | EE/Dn. II/MHP/SPA/GEN-4/1/C62272/of 2022 |  |  | Dated | 2022-08-03
Valid Up to: G + 1st & 2nd Podium + 3rd to 21st Floor
Commencement Certificate No. Wing R5 |  | EE/Dn.II/MHP/SPA/I/1872/of 2023 |  |  | Dated | 2023-06-07
Valid Up to: 22nd to 39th Floor
Wing R6 & R7
Approved Floor plan No. Wing R6 & R7 |  | EE/SPA/GEN-4/1/E-31223/of 2019 |  |  | Dated | 2023-06-07
Commencement Certificate No. Wing R6 & R7 |  | EE/Dn.II/MHP/SPA/I/1872/of 2023 |  |  | Dated | 2023-06-07
Valid Up to: R6 & R7 = G + 1st & 2nd Podium(Pt.)/Resi(Pt.) + 3rd to 39th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | NA
Approved no of units |  |  | Flats - 254
Approved no of Floors |  |  | R5 = 1B + G + P1 + P2 + 3rd to 39th Floor R5 = 1B + G + P1 + P2 + 3rd to 39th Floor
Proposed no of Floors |  |  | R4 = 1B + G + P1 + P2 + 3rd to 39th Floor
R5 = 1B + G + P1 + P2 + 3rd to 39th Floor
R6 = 1B + G + P1 + P2 + 3rd to 39th Floor
R7 = 1B + G + P1 + P2 + 3rd to 39th Floor
Expected Completion |  |  | As per RERA Q Islands R4 = Completed Q Islands R5 = 30/12/2025 Q Islands R6 & R7 = 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | R4 = 1B + G + 1st & 2nd Podium(Pt.)/Resi(Pt.) + 3rd to 39th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 39
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Progress % |  | 100% |  | Disbursement % |  | 100%
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 100% |  | 100% |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 40 | 100% |  |  |  |  | Footing in Process | 9.75
Brickwork | Brickwork & Internal Plaster | 39 | 100% |  |  |  |  | Footing Completed | 19.5
Internal Plaster | Brickwork & Internal Plaster | 39 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 39 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 39 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 39 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 39 | 100% |  |  |  |  | Plinth in process | 29.25
Possession |  | 39 | 100% |  |  |  |  | Plinth completed | 39
Construction details: |  | R5 = 1B + G + 1st & 2nd Podium(Pt.)/Resi(Pt.) + 3rd to 39th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 39
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 93.33% |  | 95% |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 40 | 100% |  |  |  |  | Footing in Process | 9.75
Brickwork | Brickwork & Internal Plaster | 39 | 100% |  |  |  |  | Footing Completed | 19.5
Internal Plaster | Brickwork & Internal Plaster | 39 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 39 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 39 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 36 | 92.31% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 29 | 74.36% |  |  |  |  | Plinth in process | 29.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Construction details: |  | R6 = 1B + G + 1st & 2nd Podium(Pt.)/Resi(Pt.) + 3rd to 39th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 7 Slab, Brickwork upto 6 Floor Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 39
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 7 Slab, Brickwork upto 6 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 18.15% |  | 51.02% |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 7 | 17.5% |  |  |  |  | Footing in Process | 9.75
Brickwork | Brickwork & Internal Plaster | 6 | 15.38% |  |  |  |  | Footing Completed | 19.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 29.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Construction details: |  | R7 = 1B + G + 1st & 2nd Podium(Pt.)/Resi(Pt.) + 3rd to 39th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 38 Slab, Brickwork upto 37 Floor, Internal Plaster upto 29.6 Floor, External Plaster upto 27.75 Floor Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 39
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 38 Slab, Brickwork upto 37 Floor, Internal Plaster upto 29.6 Floor, External Plaster upto 27.75 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 9.75
Excavation |  | 39 | 100% | 67.92% |  | 85.6% |  | Excavation in process | 19.5
Plinth |  | 39 | 100% |  |  |  |  | Excavation Completed | 39
RCC (Including podiums) |  | 38 | 95% |  |  |  |  | Footing in Process | 9.75
Brickwork | Brickwork & Internal Plaster | 37 | 94.87% |  |  |  |  | Footing Completed | 19.5
Internal Plaster | Brickwork & Internal Plaster | 29.6 | 75.9% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 27.75 | 71.15% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 29.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 39
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) (Wing R4, R6 & R7) (Including Car Parking) |  |  |  |  | 12500 |  |  |  | 12000 to 12500 | 2023-06-30 | sanket
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) (Wing R5) |  |  |  |  | 14500 |  |  | Rate for Wing R5 is changed by Sanjay 10/06/2024
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | 600000
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 600000/-
Distressed valuation of the Property |  |  |  |  | 10000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing R5 |  | 254 |  | 166033.9263 |  | 249050.8894
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
5 |  |  |  | 0 | 0 | Ground Floor
6 |  |  |  | 0 | 0 | Ground Floor
7 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area (As per Index 2 or Plan ) | Attached Terrace area | Saleable area Loading : | Floor
50%
Building R4
Ground Floor For Parking
1st & 2nd Floor For Parking
5th Floor
1 |  | 2BHK |  | 0 | 0 | 5th Floor
2 |  | 2BHK |  | 0 | 0 | 5th Floor
3 |  | 2BHK |  | 0 | 0 | 5th Floor
4 |  | 2BHK | 724.0943 | 0 | 1086.1414 | 5th Floor
10th Floor
1 |  | 2BHK |  | 0 | 0 | 10th Floor
2 |  | 2BHK |  | 0 | 0 | 10th Floor
3 |  | 2BHK |  | 0 | 0 | 10th Floor
4 |  | 2BHK | 724.0943 | 0 | 1086.1414 | 10th Floor
5 |  | 1BHK |  | 0 | 0 | 10th Floor
6 |  | 2BHK |  | 0 | 0 | 10th Floor
7 |  | 2BHK |  | 0 | 0 | 10th Floor
8 |  | 1BHK |  | 0 | 0 | 10th Floor
4th Floor
1 |  | 2BHK |  | 0 | 0 | 4th Floor
2 |  | 2BHK |  | 0 | 0 | 4th Floor
3 |  | 2BHK |  | 0 | 0 | 4th Floor
4 |  | 2BHK |  | 0 | 0 | 4th Floor
5 |  | 1BHK |  | 0 | 0 | 4th Floor
6 |  | 2BHK |  | 0 | 0 | 4th Floor
7 |  | 2BHK |  | 0 | 0 | 4th Floor
8 |  | 1BHK |  | 0 | 0 | 4th Floor
5th to 17th Floor
1 |  | 2BHK |  | 0 | 0 | 5th to 17th Floor
2 |  | 2BHK |  | 0 | 0 | 5th to 17th Floor
3 |  | 2BHK |  | 0 | 0 | 5th to 17th Floor
4 |  | 2BHK |  | 0 | 0 | 5th to 17th Floor
5 |  | 1BHK |  | 0 | 0 | 5th to 17th Floor
6 |  | 2BHK |  | 0 | 0 | 5th to 17th Floor
7 |  | 2BHK |  | 0 | 0 | 5th to 17th Floor
8 |  | 1BHK |  | 0 | 0 | 5th to 17th Floor
18th Floor (Part Refuge Area)
1 |  | 2BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
2 |  | 2BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
3 |  | 2BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
4 |  | 2BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
5 |  | 1BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
6 |  | 2BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
7 |  | 2BHK |  | 0 | 0 | 18th Floor (Part Refuge Area)
8 |  | Refuge Area |  |  |  | 18th Floor (Part Refuge Area)
19th to 21st Floor
1 |  | 2BHK |  | 0 | 0 | 19th to 21st Floor
2 |  | 2BHK |  | 0 | 0 | 19th to 21st Floor
3 |  | 2BHK |  | 0 | 0 | 19th to 21st Floor
4 |  | 2BHK |  | 0 | 0 | 19th to 21st Floor
5 |  | 1BHK |  | 0 | 0 | 19th to 21st Floor
6 |  | 2BHK |  | 0 | 0 | 19th to 21st Floor
7 |  | 2BHK |  | 0 | 0 | 19th to 21st Floor
8 |  | 1BHK |  | 0 | 0 | 19th to 21st Floor
18th Floor
1 |  | 2BHK |  | 0 | 0 | 18th Floor
2 |  | 2BHK |  | 0 | 0 | 18th Floor
3 |  | 2BHK |  | 0 | 0 | 18th Floor
4 |  | 2BHK |  | 0 | 0 | 18th Floor
5 |  | 2BHK |  | 0 | 0 | 18th Floor
6 |  | 2BHK | 714.9449 | 0 | 1072.4173 | 18th Floor |  | 2023-02-13 | Rushikesh Naik |  | 12869007.84
7 |  | 2BHK |  | 0 | 0 | 18th Floor
8 |  | 2BHK |  | 0 | 0 | 18th Floor
22nd Floor
1 |  | 2BHK | 724.0943 | 0 | 1086.1414 | 22nd Floor |  | 2022-12-05
30th Floor
4 |  | 3.5BHK | 1260.0338 | 0 | 1890.0508 | 30th Floor |  | 2022-12-31
34th Floor
2 |  | 4.5BHK | 1491.1369 | 0 | 2236.7054 | 34th Floor |  | 2023-07-05 | Shubham
2 |  | 2BHK |  | 0 | 0 | 34th Floor
3 |  | 2BHK |  | 0 | 0 | 34th Floor
4 |  | 2BHK |  | 0 | 0 | 34th Floor
5 |  | 1BHK |  | 0 | 0 | 34th Floor
6 |  | 2BHK |  | 0 | 0 | 34th Floor
7 |  | 2BHK |  | 0 | 0 | 34th Floor
8 |  | 1BHK |  | 0 | 0 | 34th Floor
28th Floor (Part Refuge Area)
1 |  | 2BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
2 |  | 2BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
3 |  | 2BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
4 |  | 2BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
5 |  | 1BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
6 |  | 2BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
7 |  | 2BHK |  | 0 | 0 | 28th Floor (Part Refuge Area)
8 |  | Refuge Area |  |  |  | 28th Floor (Part Refuge Area)
29th Floor (Part Refuge Area)
1 |  | 2BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
2 |  | 2BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
3 |  | 2BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
4 |  | 2BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
5 |  | 1BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
6 |  | 2BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
7 |  | 2BHK |  | 0 | 0 | 29th Floor (Part Refuge Area)
8 |  | Refuge Area |  |  |  | 29th Floor (Part Refuge Area)
30th to 37th Floor
1 |  | 4BHK |  | 0 | 0 | 30th to 37th Floor
2 |  | 4BHK |  | 0 | 0 | 30th to 37th Floor
3 |  | 3BHK |  | 0 | 0 | 30th to 37th Floor
4 |  | 3BHK |  | 0 | 0 | 30th to 37th Floor
38th Floor (Part Refuge Area)
1 |  | 4BHK |  | 0 | 0 | 38th Floor (Part Refuge Area)
2 |  | 4BHK |  | 0 | 0 | 38th Floor (Part Refuge Area)
3 |  | 3BHK |  | 0 | 0 | 38th Floor (Part Refuge Area)
4 |  | 2BHK |  | 0 | 0 | 38th Floor (Part Refuge Area)
5 |  | Refuge Area |  |  |  | 38th Floor (Part Refuge Area)
39th Floor
1 |  | 4BHK |  | 0 | 0 | 39th Floor
2 |  | 4BHK |  | 0 | 0 | 39th Floor
3 |  | 3BHK |  | 0 | 0 | 39th Floor
4 |  | 3BHK |  | 0 | 0 | 39th Floor
Building R5
Ground Floor For Parking
1st & 2nd Floor For Parking
3rd & 4th Floor
1 |  | 1BHK | 467.0887 | 0 | 700.6331 | 3rd & 4th Floor
2 |  | 2BHK | 664.2302 | 0 | 996.3452
3 |  | 2BHK | 664.2302 | 0 | 996.3452
4 |  | 1BHK | 467.0887 | 0 | 700.6331
5 |  | 1BHK | 467.0887 | 0 | 700.6331
6 |  | 2BHK | 664.2302 | 0 | 996.3452
7 |  | 2BHK | 664.2302 | 0 | 996.3452
8 |  | 1BHK | 467.0887 | 0 | 700.6331
5th to 17th & 19th to 21st Floor
1 |  | 1BHK | 467.0887 | 0 | 700.6331 | 5th to 17th & 19th to 21st Floor
2 |  | 2BHK | 664.2302 | 0 | 996.3452
3 |  | 2BHK | 664.2302 | 0 | 996.3452
4 |  | 1BHK | 467.0887 | 0 | 700.6331
5 |  | 1BHK | 467.0887 | 0 | 700.6331
6 |  | 2BHK | 664.2302 | 0 | 996.3452
7 |  | 2BHK | 664.2302 | 0 | 996.3452
8 |  | 1BHK | 467.0887 | 0 | 700.6331
18th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 18th Floor (Part Refuge Area)
2 |  | 2BHK | 664.2302 | 0 | 996.3452
3 |  | 2BHK | 664.2302 | 0 | 996.3452
4 |  | 1BHK | 467.0887 | 0 | 700.6331
5 |  | 1BHK | 467.0887 | 0 | 700.6331
6 |  | 2BHK | 664.2302 | 0 | 996.3452
7 |  | 2BHK | 664.2302 | 0 | 996.3452
8 |  | 1BHK | 467.0887 | 0 | 700.6331
22nd to 27th & 29th Floor
1 |  | 1BHK | 467.0887 | 0 | 700.6331 | 22nd to 27th & 29th Floor
2 |  | 2BHK | 664.2302 | 0 | 996.3452
3 |  | 2BHK | 664.2302 | 0 | 996.3452
4 |  | 1BHK | 467.0887 | 0 | 700.6331
5 |  | 1BHK | 467.0887 | 0 | 700.6331
6 |  | 2BHK | 664.2302 | 0 | 996.3452
7 |  | 2BHK | 664.2302 | 0 | 996.3452
8 |  | 1BHK | 467.0887 | 0 | 700.6331
28th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 28th Floor (Part Refuge Area)
2 |  | 2BHK | 664.2302 | 0 | 996.3452
3 |  | 2BHK | 664.2302 | 0 | 996.3452
4 |  | 1BHK | 467.0887 | 0 | 700.6331
5 |  | 1BHK | 467.0887 | 0 | 700.6331
6 |  | 2BHK | 664.2302 | 0 | 996.3452
7 |  | 2BHK | 664.2302 | 0 | 996.3452
8 |  | 1BHK | 467.0887 | 0 | 700.6331
30th to 37th & 39th Floor
1 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783 | 30th to 37th & 39th Floor
2 |  | Merged with Flat No. 1
3 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783
4 |  | Merged with Flat No. 3
5 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783
6 |  | Merged with Flat No. 5
7 |  | Merged with Flat No. 8
8 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783
38th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 38th Floor (Part Refuge Area)
2 |  | 2BHK | 664.2302 | 0 | 996.3452
3 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783
4 |  | Merged with Flat No. 3
5 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783
6 |  | Merged with Flat No. 5
7 |  | Merged with Flat No. 8
8 |  | 3.5BHK | 1131.3189 | 0 | 1696.9783
7th Floor
1 |  | 2BHK |  | 0 | 0 | 7th Floor
2 |  | 2BHK |  | 0 | 0 | 7th Floor
3 |  | 2BHK |  | 0 | 0 | 7th Floor
5 |  | 1BHK | 504.724 | 0 | 757.0859 | 7th Floor
6 |  | 2BHK | 714.9449 | 0 | 1072.4173 | 7th Floor
Remarks:
1 | R4 = Construction work completed. Please provide OC. R5 = Finishing work is in process. (Internal visit Not allowed) R6 & R7 = Construction work is in process at the time of Visit. (Internal visit Not allowed). Details taken from sales person.
2 | We considered Saleable area as per our calculation/ Builder area sheet.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
2 | We have considered rate by verifying it from market inquire.
3 | Car parking is subjected to authentic documentation.
4 | On Site, we meet Mr. Sagar : 8828079398
5 | Flat's measurements/dimensions are not shown in MIDC approved plans of R4, R6 & R7, Please provide the RERA carpet area with architect letter & Sale Plans along with approved Plans for all typical Floors.
6 | Since Plans of Wing R5 was only provided with proper dimensions, Plan Area is drafted for Wing R5 only on 31/05/2024.
7 | Wing R4, R6 & R7 flat area is considered from index2 provided to us by bank officials.
8 | Wing R4, R6 & R7 flat area is considered from index2 provided to us by bank officials.
8 | Constrution work goes beyond CC. Please provide latest CC for R4 Wing.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Aakash Chaure |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Q Islands R4 to R7
Google Map :
Formulas:
Ghansoli = [Ghansoli, row above]
R5
R4
R7
R7
R6
R5
R4
R4
R5
R4
R5
R7
R7

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted