## Sheet1 (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/08/2025
CPC Name: |  |  |  |  | Axis Goregaon.
Date Of Property Visit |  |  |  |  | 2025-08-11
Name of the builder group |  |  |  |  | M/s. Ideal Group
Name of the builder company for Wing A to E |  |  |  |  | M/s. Ideal Properties Builder & Developers. |  |  |  |  | C - SHREE GANESH ENTERPRISES
Name of the builder company for Wing F |  |  |  |  | M/s.Rama And Shantiraj Builders and developers |  |  |  |  | E - AJIT DUDHANATH SINGH
Name of the Project |  |  |  |  | Ideal Park
Name / no of the Building |  |  |  |  | Building no.2 - Ideal Park Wing C - Type B2 Wing D - Type A1 Wing E - Type C1 Wing F - Type A1a
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No. |  |  |  |  | Wing C (Type B2) & Wing D (Type A1) = P99000015774 Wing E (Type C1) = P99000013553 Wing F (Type A1a) = P99000018527
Approved Layout Plan : |  | MHSL/K.1/MJ.1/NAP/SR/229/17 |  |  |  |  | Dated | 22/03/2019.
Project location details |  | Ideal City-Ideal Park, Building No.2, Gut No.179, 180 & 181, Sarpada, Umroli(E), Opp.Railway Station, Village. Umroli, Tal.Palghar, Dist.Palghar.
Gut No | 179, 180 & 181 |  |  | Plot No | NA | Locality | Umroli(E)
Road | Village Umroli(E) Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401 404.
Near by Landmark |  | Opp.Railway Station |  |  | Distance from city centre: |  | Near By Umroli Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Railway station |  | Open |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.7552112,72.763119
Location Link |  | https://maps.app.goo.gl/2BDjqsggS7eq2t9M6
Approval details:
Approved usage of the Property: Residential & Commercial. (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 12311.44
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 11080.296
Total number of Buildings |  |  |  |  | 4 Wings
Approval Detail : Plan approval
Layout Approval No |  | MHSL/K.1/MJ.1/NAP/SR/229/17 |  |  |  | Dated | 22/03/2019.
Building plan approval No (Type- D1a & C2a) |  | MHSL/U.1/M.1/NAP/SR/87/15 Approved no. of floors = Gr.+2nd Floor |  |  |  | Dated | 16/06/2016.
Building plan approval No (Type- B2, A1, C1 & A1a) |  | MHSL/K.1/MJ.1/NAP/SR/229/17 Approved no. of floors = Gr.+3rd Floor |  |  |  | Dated | 22/03/2019.
C.certificate No (Type-D1a, C2a, B2, A1, C1 & A1a) |  | MHSL/K.1/MJ.1/NAP/SR/229/17 Valid Up to: Type-D1a = Gr. + 1st to 4th Floor Type-C2a, B2, A1, C1 & A1a = Gr. +1st to 3rd Floor |  |  |  | Dated | 22/03/2019.
O. Certificate No.: NA |  | NA |  |  | Date of approval: NA | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | 22/03/2019. |  | Expected Completion |  | C & D Wing = 30/06/2026 E & F Wing = 31/12/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 11080.296 |  | Approved no of units residential |  | Shops = 30 & Flats = 93
Approved no of Floors |  | Type- D1a & C2a = Gr.+1st to 2nd Floor Type- B2, A1, C1 & A1a = Gr. + 1st to 3rd Floor
Proposed no of Floors |  | Wing C, D & E = Gr.+ 1st to 5th Floor Wing F = Gr/ST + 1st to 4th Floor
Quality of construction: Good |  |  |  |  | Projected life: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building No.2 : Type -B2 (C Wing) = Gr + 1st to 5th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 5 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 68.5% |  | 86% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 4 | 80% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 60% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 40% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 40% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.2 : Type -A1 (D Wing) = Gr + 1st to 5th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 5 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 61.83% |  | 81% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 5 | 83.33% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 4 | 80% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 60% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 40% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 40% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.2 : Type -C1 (E Wing) = Gr + 1st to 5th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed, Brickwork upto 5 Floor completed, Internal Plaster upto 5 Floor completed, External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 5 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 6 Slab completed, Brickwork upto 5 Floor completed, Internal Plaster upto 5 Floor completed, External Plaster upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 69% |  | 87% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 40% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.2 : Type -A1a (F Wing) = Gr + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 57.5% |  | 80% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Rate of the flat Per Sq. Ft. (on Saleable area) | [6 empty] | 3600
Rate of the shop Per Sq. Ft. (on Saleable area) | [6 empty] | 6000
Society formation charges | [6 empty] | 1,00,000/-
Development charges Per Sq. Ft. | [6 empty] | NA
Valuation as per Government reckoners rates | [6 empty] | NA
Distress valuation of the property Per Sq. Ft. | [6 empty] | 2880
Building details floor wise
Details of Flats in Building
Flat No. |  | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | PLC Y/N
Building No.2 - Ideal Park
Type- D1a (A Wing)
Ground Floor For Residential & Parking
1 |  | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683 | NA
2 |  | 1BHK | 359.5176 | 0 | 359.5176 | 0 | 521.3005 | NA
3 |  | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683 | NA
1st & 2nd Floor
1 | 1 | 1BHK | 485.887 | 0 | 485.887 | 0 | 704.5361 | NA
2 | 2 | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683 | NA
3 | 3 | 1BHK | 359.5176 | 0 | 359.5176 | 0 | 521.3005 | NA
4 | 4 | 1BHK | 375.7712 | 0 | 375.7712 | 0 | 544.8683 | NA
5 | 5 | 1BHK | 485.887 | 0 | 485.887 | 0 | 704.5361 | NA
Type -C2a (B Wing)
Ground Floor For Residential & Parking
1 | 1 | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | NA
2 | 2 | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | NA
1st & 2nd Floor
1 | 1 | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | NA
2 | 2 | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | NA
3 | 3 | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | NA
4 | 4 | 1BHK | 359.3023 | 0 | 359.3023 | 0 | 520.9884 | NA
Type -B2 (C Wing)
Ground Floor For Residential, Commercial & Parking
1 |  | 1RK | 251.2318 | 0 | 251.2318 | 0 | 364.2861 | NA
2 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
1 |  | Shop | 161.3524 | 0 | 161.3524 | 0 | 242.0285 | NA
2 |  | Shop | 133.9042 | 0 | 133.9042 | 0 | 200.8562 | NA
3 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
4 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
5 |  | Shop | 116.0359 | 0 | 116.0359 | 0 | 174.0539 | NA
6 |  | Shop | 156.2933 | 0 | 156.2933 | 0 | 234.4399 | NA
7 |  | Shop | 86.112 | 0 | 86.112 | 0 | 129.168 | NA
1st to 3rd Floor
1 |  | 1BHK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | NA
2 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
3 |  | 1BHK | 362.3162 | 0 | 362.3162 | 0 | 525.3585 | NA
4 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
5 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
6 |  | 1BHK | 361.4551 | 0 | 361.4551 | 0 | 524.1099 | NA
Type-A1 (D Wing)
Ground Floor For Parking & Commercial
1 |  | Shop | 161.3524 | 0 | 161.3524 | 0 | 242.0285 | NA
2 |  | Shop | 133.9042 | 0 | 133.9042 | 0 | 200.8562 | NA
3 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
4 |  | Shop | 132.6125 | 0 | 132.6125 | 0 | 198.9187 | NA
5 |  | Shop | 94.7232 | 0 | 94.7232 | 0 | 142.0848 | NA
6 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 | NA
7 |  | Shop | 144.4529 | 0 | 144.4529 | 0 | 216.6793 | NA
8 |  | Shop | 137.3486 | 0 | 137.3486 | 0 | 206.023 | NA
9 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
10 |  | Shop | 165.7656 | 0 | 165.7656 | 0 | 248.6484 | NA
11 |  | Shop | 112.9144 | 0 | 112.9144 | 0 | 169.3715 | NA
12 |  | Shop | 89.1259 | 0 | 89.1259 | 0 | 133.6889 | NA
1st to 3rd Floor
1 |  | 1RK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | NA
2 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
3 |  | 1BHK | 362.3162 | 0 | 362.3162 | 0 | 525.3585 | NA
4 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
5 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
6 |  | 1BHK | 361.4551 | 0 | 361.4551 | 0 | 524.1099 | NA
Type-C1 (E Wing)
Ground Floor For Parking & Commercial
1 |  | Shop | 189.2311 | 0 | 189.2311 | 0 | 283.8467 | NA
2 |  | Shop | 151.0189 | 0 | 151.0189 | 0 | 226.5284 | NA
3 |  | Shop | 151.0189 | 0 | 151.0189 | 0 | 226.5284 | NA
4 |  | Shop | 189.2311 | 0 | 189.2311 | 0 | 283.8467 | NA
1st to 3rd Floor
1 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
2 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
3 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
4 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
Type-A1a (F Wing)
Ground Floor For Parking, Residential & Commercial
1 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 547.9952 | NA
2 |  | 1RK | 257.4749 | 0 | 257.4749 | 0 | 386.2123 | NA
1 |  | Shop | 91.0634 | 0 | 91.0634 | 0 | 136.5952 | NA
2 |  | Shop | 114.8519 | 0 | 114.8519 | 0 | 172.2778 | NA
3 |  | Shop | 168.7795 | 0 | 168.7795 | 0 | 253.1693 | NA
4 |  | Shop | 168.7795 | 0 | 168.7795 | 0 | 253.1693 | NA
5 |  | Shop | 118.7269 | 0 | 118.7269 | 0 | 178.0904 | NA
6 |  | Shop | 155.5398 | 0 | 155.5398 | 0 | 233.3097 | NA
7 |  | Shop | 85.0356 | 0 | 85.0356 | 0 | 127.5534 | NA
1st to 3rd Floor
1 |  | 1RK | 361.4551 | 0 | 361.4551 | 0 | 524.1099 | NA
2 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
3 |  | 1RK | 295.1489 | 0 | 295.1489 | 0 | 427.9659 | NA
4 |  | 1BHK | 362.3162 | 0 | 362.3162 | 0 | 525.3585 | NA
5 |  | 1BHK | 365.3302 | 0 | 365.3302 | 0 | 529.7287 | NA
6 |  | 1RK | 339.4966 | 0 | 339.4966 | 0 | 492.27 | NA
Remarks: 1. Wing C, D & E = Construction work is in process at the time of visit. Wing F = Construction work is in process at the time of visit (Slow Speed). 2. We considered saleable area as per our calculation. 3. As per site inspection no workers found on site for work. 4. We updated revised Approved Plan of type-B2, A1, C1, A1a, Layout & CC on 05/04/2019. 5. We have given construction percentage as per proposed no. of floors (Gr + 4th Floor) 6. We have considered rate by verifying it from market inquire. 7. We have considered Other charges from cost sheet. 8. Car parking is subjected to authentic documentation. 9. Please provide latest approved floor plans & CC. 10. As per RERA, promoter name of Wing C & D is " Shree Ganesh Enterprises " & Wing E is "Ajit Dudhanath Singh", please check in legal report as well. 11. Wing C & D = Construction stage is reduced due to revision in proposed structure of project. 12. The project has received first CC on 22/03/2019, But construction work is not yet completed. 13. As checked on RERA portal on date 18/08/2025, we have observed that above project "Ideal Park (Wing C & D)" is kept under abeyance. Please check from your end. 9. On site, we meet Mr.Aniket Sawant (Sales) - 8369084688.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY: |  |  |  | Ideal Park
Google Map :
C Wing
C Wing
D Wing
E Wing
F Wing

## Note
14/03/2020. | Asmita | OLD APF
In previous report : We considered rate as per Builder cost sheet & shop's rate as per Market inquiry.
11/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.
22/03/2021 | Pratiksha

## C % 2A
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 5 | 5 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## C % B
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 60 | Progress |  |  | 10 | 32 | 9 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 24 | 9 | 0 | 0 | 0 | 0
| 5 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 9 | 9
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 51 | 63

## C % 2C,D
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 75 | Progress |  |  | 10 | 32 | 11.25 | 4 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 40 | Recommended |  |  | 30 | 24 | 11.25 | 4 | 0 | 0 | 0
| 4 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 1.6 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 11.25 | 11.25
| 4 | 0 |  | Plaster | 4 | 4
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 57.25 | 69.25

## C % 2E
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 80 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 4 | 60 | Progress |  |  | 10 | 32 | 9 | 2 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 20 | Recommended |  |  | 30 | 24 | 9 | 2 | 0 | 0 | 0
| 5 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 1 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 32 | 24
Finishing | Total Floor | completed Floor |  | Bricks | 9 | 9
| 5 | 0 |  | Plaster | 2 | 2
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 53 | 65

## C % 2F
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 40 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 2 | 0 | Progress |  |  | 10 | 16 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 12 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 5 | 0 | 0
Flooring | Total Floor | completed Floor
| 5 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 5 | 0 |  | RCC | 16 | 12
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 5 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 26 | 42

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
proptiger | Gunaji Vasudeo Complex | 1BHK | 0 | 585 | 3200 | 1872000
proptiger | Gunaji Vasudeo Complex | 1BHK | 0 | 645 | 3172.093 | 2046000
proptiger | Gunaji Vasudeo Complex | 2BHK | 0 | 800 | 3200 | 2560000
housing | Gunaji Vasudeo Complex | 4BHK | 0 | 585 | 3200 | 1872000
housing | Gunaji Vasudeo Complex | 4BHK | 0 | 645 | 3200 | 2064000
housing | Gunaji Vasudeo Complex | 3BHK | 0 | 800 | 3200 | 2560000
Average |  |  |  |  | 3195.3488
Valuation Adopted |  |  |  |  | 3200