## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-11
Name of the builder group |  |  |  |  | M/s. Konnark Buildcon
Name of the builder company |  |  |  |  | M/s. Konnark Buildcon
Name of the Project |  |  |  |  | Konnark Meadows
Contect Details ( Name & Contect No.) |  |  |  |  | 9920732532
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Deepak 9920732532
Name / no of the Building |  |  |  |  | Building No. 1, 4 & 8 (Wing A & B) Building No. 3, 5 & 7 (Wing A to C) Building No. 2 (A to D) Building No. 6
Docouments Provided |  |  |  |  | 1.Approved Layout 2. Approved Building Plan 3.CC 4.Cost Sheet.
RERA No. |  |  |  |  | P52000015880
Project location details |  | Konnark Meadows, S. No.5/9, 5/11, 5/12, 5/14, at Village-Chindran, Tal.Panvel, Dist.Raigad.
Plot No | NA | S No /G. No/ Khasra No./CTS No. |  |  | 5/9, 5/11, 5/12, 5/14 |  | Village | Chindran
Road | Village-Chindran Road |  |  |  | District | Raigad.
City | Navi Mumbai. |  |  |  | Pin Code | 410 206.
Near by Landmark |  | Near Taloja MIDC |  |  | Distance from city centre: |  | 8.7 Km from Navade Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Meadows Garden |  | Open |  | Open |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC(U/C)
Latitude & Longitude |  | Latitude |  | 19.0715 |  | Longitude |  | 73.1523
Location Link |  | https://goo.gl/maps/kL1KTKj17nNbrDfA9?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Commercial & Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 10600
Permissible FSI |  |  |  |  | 0.7
Permissible TDR/Paid FSI |  |  |  |  | 0.3
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 10600
Total number of Buildings |  |  |  |  | 20 Wings
Approval Detail : Plan approval
Layout Approval No Building No.1, 5, 6, 7 & 8 |  | CIDCO/NAINA/Panvel/Chindran/BP-202/CC/2018/1310 |  |  |  | Dated | 2018-02-23
Layout Approval No Building No. 2, 3 & 4 |  | CIDCO/NAINA/Panvel/Chindran/BP-00202/ACC/2020/0043 |  |  |  | Dated | 2020-07-28
Building plan approval No Building No.1, 5, 6, 7 & 8 |  | CIDCO/NAINA/Panvel/Chindran/BP-202/CC/2018/1310 |  |  |  | Dated | 2018-02-23 | Expiry date:NA
Building plan approval No Building No. 2, 3 & 4 |  | CIDCO/NAINA/Panvel/Chindran/BP-00202/ACC/2020/0043 |  |  |  | Dated | 2020-07-28 | Expiry date:NA
Commencement Certificate No. Building No.1, 5, 6, 7 & 8 |  | CIDCO/NAINA/Panvel/Chindran/BP-202/CC/2018/1309 |  |  |  | Dated | 2018-02-23
Commencement Certificate No. Building No. 2, 3 & 4 |  | CIDCO/NAINA/Panvel/Chindran/BP-00202/ACC/2020/0043 |  |  |  | Dated | 2020-07-28
Plinth Completion Certificate No. Building No. 2, 3, 4 & 6 |  | CIDCO/NAINA/Panvel/Chindharan/BP-00202/PCC/Part/2021/0117 |  |  |  | Dated | 2021-10-12
O. Certificate No.: |  |  |  |  | Date of approval: |  | Expiry date: NA
Commencement date of construction |  |  | 2018-02-23 |  | Expected Completion |  | 2026-01-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 10600 |  | Approved no of units residential |  |  | 285 |  | 139 | 146
Approved no of Floors |  | Bldg no.1, 2, 3, 7(Gr. + 1st to 4th Floor) Bldg No. 4, 5, 7(C Wing), 8 (Gr. + 1st to 3rd Floor) Bldg No.6 (Gr. + 1st to 2nd Floor)
Proposed no of Floors |  | Bldg no.1, 2, 3, 7 = (Gr.+1st to 4th Floor) Bldg No. 4, 5, 8 = (Gr.+1st to 3rd Floor) Bldg No.6 = (Gr.+1st to 2nd Floor)
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: Building no. 1 (A & B wings) = Gr.+1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 95% |  | 95%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth completed |  | 4
Possession |  | 0 | 0%
Construction details:Building no. 2 (A, B, C & D wings) = Gr.+1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 4 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 95% |  | 95%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth completed |  | 4
Possession |  | 0 | 0%
Construction details:Building no. 3 (A, B & C wings) = Gr.+1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 3 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 3 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 93.75% |  | 95%
Plinth |  | 4 | 100%
RCC |  | 5 | 100% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 4 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 3 | 75% | [5 empty] | Plinth completed |  | 4
Possession |  | 0 | 0%
Construction details:Building no.4 ( A & B wings) = Gr.+ 1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed, Finishing upto 3 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 100% |  | 100%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process |  | 1.5
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Excavation Completed |  | 3
Internal Plaster | Brickwork & Internal Plaster | 3 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Footing in Process |  | 0.75
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Footing Completed |  | 1.5
Painting & Wooden |  | 3 | 100% | [5 empty] | Plinth in process |  | 2.25
Building Common Amenities | Building Common Amenities | 3 | 100% | [5 empty] | Plinth completed |  | 3
Possession |  | 3 | 100%
Progress % |  |  | 100% |  |  | Disbursement % |  | 100%
Construction details:Building no.5 (A, B, C wings) = Gr.+ 1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed, Finishing upto 3 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 100% |  | 100%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process |  | 1.5
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Excavation Completed |  | 3
Internal Plaster | Brickwork & Internal Plaster | 3 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Footing in Process |  | 0.75
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Footing Completed |  | 1.5
Painting & Wooden |  | 3 | 100% | [5 empty] | Plinth in process |  | 2.25
Building Common Amenities | Building Common Amenities | 3 | 100% | [5 empty] | Plinth completed |  | 3
Possession |  | 3 | 100%
Progress % |  |  | 100% |  |  | Disbursement % |  | 100%
Construction details:Building no.6 = Gr.+1st to 2nd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed, Painting upto 2 Floor completed, Finishing upto 2 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 2 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 2 Floor completed, External Plaster upto 2 Floor completed, Flooring upto 2 Floor completed, Painting upto 2 Floor completed, Finishing upto 2 Floor completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 2 | 100% |  | 95% |  | 95%
Plinth |  | 2 | 100%
RCC |  | 3 | 100% | [5 empty] | Excavation in process |  | 1
Brickwork | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Excavation Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 2 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 100% | [5 empty] | Footing in Process |  | 0.5
Flooring & Fitting | Flooring & Fitting | 2 | 100% | [5 empty] | Footing Completed |  | 1
Painting & Wooden |  | 2 | 100% | [5 empty] | Plinth in process |  | 1.5
Building Common Amenities | Building Common Amenities | 2 | 100% | [5 empty] | Plinth completed |  | 2
Possession |  | 0 | 0%
Construction details:Building no.7 (A, B, C wings) = Gr.+1st to 4th Floor | [8 empty] | Excavation work completed, Plinth work completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 4 | All work Completed. Wait For OC.
Stage of construction: |  | Excavation work completed, Plinth work completed | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 4 | 100% |  | 10% |  | 45%
Plinth |  | 4 | 100%
RCC |  | 0 | 0% | [5 empty] | Excavation in process |  | 2
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Excavation Completed |  | 4
Internal Plaster | Brickwork & Internal Plaster | 0 | 0%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Footing in Process |  | 1
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Footing Completed |  | 2
Painting & Wooden |  | 0 | 0% | [5 empty] | Plinth in process |  | 3
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed |  | 4
Possession |  | 0 | 0%
Construction details:Building no 8 (A & B Wing) = Gr.+1st to 3rd Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Internal Plaster upto 3 Floor completed, External Plaster upto 3 Floor completed, Flooring upto 3 Floor completed, Painting upto 3 Floor completed, Finishing upto 3 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 3 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 3 | 100% |  | 100% |  | 100%
Plinth |  | 3 | 100%
RCC |  | 4 | 100% | [5 empty] | Excavation in process |  | 1.5
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Excavation Completed |  | 3
Internal Plaster | Brickwork & Internal Plaster | 3 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Footing in Process |  | 0.75
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Footing Completed |  | 1.5
Painting & Wooden |  | 3 | 100% | [5 empty] | Plinth in process |  | 2.25
Building Common Amenities | Building Common Amenities | 3 | 100% | [5 empty] | Plinth completed |  | 3
Possession |  | 3 | 100%
Progress % |  |  | 100% |  |  | Disbursement % |  | 100%
Wheather the construction is as per approved Building plan : under construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4500
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6500/-
Other Charges | [5 empty] | 25000/-
Development charges | [5 empty] | 55000/-
Distressed valuation of the Property | [5 empty] | 3600
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1
Ground Floor For Parking & Commercial (A & B )
1 |  | Shop | 103.216 |  | 0 | 154.824 | NA | Gr.
2 |  | Shop | 79.1154 |  | 0 | 118.6731 | NA | Gr.
3 |  | Shop | 101.7198 |  | 0 | 152.5797 | NA | Gr.
4 |  | Shop | 65.9295 |  | 0 | 98.8942 | NA | Gr.
5 |  | Shop | 101.7198 |  | 0 | 152.5797 | NA | Gr.
6 |  | Shop | 79.1154 |  | 0 | 118.6731 | NA | Gr.
7 |  | Shop | 94.185 |  | 0 | 141.2775 | NA | Gr.
8 |  | Shop | 105.1105 |  | 0 | 157.6657 | NA | Gr.
9 |  | Shop | 98.3291 |  | 0 | 147.4937 | NA | Gr.
10 |  | Shop | 75.348 |  | 0 | 113.022 | NA | Gr.
11 |  | Shop | 102.0965 |  | 0 | 153.1448 | NA | Gr.
12 |  | Shop | 65.9295 |  | 0 | 98.8942 | NA | Gr.
13 |  | Shop | 94.185 |  | 0 | 141.2775 | NA | Gr.
14 |  | Shop | 79.1154 |  | 0 | 118.6731 | NA | Gr.
15 |  | Shop | 100.8156 |  | 0 | 151.2234 | NA | Gr.
1st Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 61.7854 | 850 | NA | 1st
2 |  | 2BHK | 457.3947 |  | 142.6661 | 850 | NA | 1st
3 |  | 2BHK | 457.3947 |  | 140.9546 | 850 | NA | 1st
4 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 1st
B Wing
1 |  | 2BHK | 457.3947 |  | 61.7854 | 850 | NA | 1st
2 |  | 2BHK | 457.3947 |  | 142.6661 | 850 | NA | 1st
3 |  | 2BHK | 457.3947 |  | 140.9546 | 850 | NA | 1st
4 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 1st
2nd Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
2 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 2nd
3 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 2nd
4 |  | 2BHK | 457.3947 |  | 50.3863 | 850 | NA | 2nd
B Wing
1 |  | 2BHK | 457.3947 |  | 50.3863 | 850 | NA | 2nd
2 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 2nd
3 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 2nd
4 |  | 2BHK | 457.3947 |  | 52 | 850 | NA | 2nd
3rd Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 3rd
2 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 3rd
3 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 3rd
4 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 3rd
B Wing
1 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 3rd
2 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 3rd
3 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 3rd
4 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 3rd
4th Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
2 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
3 |  | 2BHK | 457.3947 |  | 50.3863 | 850 | NA | 4th
4 |  | 2BHK | 457.3947 |  | 50.3863 | 850 | NA | 4th
B Wing
1 |  | 2BHK | 457.3947 |  | 50.3863 | 850 | NA | 4th
2 |  | 2BHK | 457.3947 |  | 50.3863 | 850 | NA | 4th
3 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
4 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
Building No.2
Ground Floor For Parking (A, B, C & D)
1st & 3rd Floor
A Wing
1 |  | 1RK | 233.6434 |  | 33.9066 | 450 | NA | 1st & 3rd
2 |  | 1RK | 233.6434 |  | 36.3285 | 450 | NA | 1st & 3rd
3 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
4 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
B Wing
1 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
2 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
3 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
4 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
C Wing
1 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
2 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
3 |  | 1RK | 269.0785 |  | 0 | 450 | NA | 1st & 3rd
4 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
D Wing
1 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
2 |  | 1RK | 232.8361 |  | 0 | 450 | NA | 1st & 3rd
3 |  | 1RK | 269.8858 |  | 0 | 450 | NA | 1st & 3rd
4 |  | 1RK | 269.8858 |  | 33.9066 | 450 | NA | 1st & 3rd
2nd & 4th Floor
A Wing
1 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd & 4th
2 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd & 4th
3 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
4 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
B Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
2 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
3 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
4 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
C Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
2 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
3 |  | 1RK | 269.0785 |  | 0 | 450 | NA | 2nd & 4th
4 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
D Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd & 4th
2 |  | 1RK | 232.8361 |  | 0 | 450 | NA | 2nd & 4th
3 |  | 1RK | 269.8858 |  | 0 | 450 | NA | 2nd & 4th
4 |  | 1RK | 263.8472 |  | 0 | 450 | NA | 2nd & 4th
Building No.3
Ground Floor For Parking (A, B & C)
1st & 3rd Floor
A Wing
1 |  | 1RK | 233.6434 |  | 36.3285 | 450 | NA | 1st & 3rd
2 |  | 1RK | 233.6434 |  | 33.9066 | 450 | NA | 1st & 3rd
3 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
4 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
B Wing
1 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
2 |  | 1RK | 232.8361 |  | 33.9066 | 450 | NA | 1st & 3rd
3 |  | 1RK | 232.8361 |  | 33.8205 | 450 | NA | 1st & 3rd
4 |  | 1RK | 232.8361 |  | 36.3285 | 450 | NA | 1st & 3rd
C Wing
1 |  | 1RK | 232.8038 |  | 33.9066 | 450 | NA | 1st & 3rd
2 |  | 1RK | 269.0462 |  | 0 | 450 | NA | 1st & 3rd
3 |  | 1RK | 269.8535 |  | 0 | 450 | NA | 1st & 3rd
4 |  | 1RK | 233.6111 |  | 33.9066 | 450 | NA | 1st & 3rd
2nd & 4th Floor
A Wing
1 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
B Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
C Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 269.0785 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 269.8858 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd
Building No.4
Ground Floor For Parking (A & B Wing)
1st & 3rd Floor
A Wing
1 |  | 1RK | 232.8361 |  | 33.8205 | 450 | NA | 1st & 3rd
2 |  | 1RK | 269.0785 |  | 0 | 450 | NA | 1st & 3rd
3 |  | 1RK | 269.8858 |  | 0 | 450 | NA | 1st & 3rd
4 |  | 1RK | 233.6434 |  | 33.8205 | 450 | NA | 1st & 3rd
B Wing
1 |  | 1RK | 232.8361 |  | 33.8205 | 450 | NA | 1st & 3rd
2 |  | 1RK | 269.1108 |  | 0 | 450 | NA | 1st & 3rd
3 |  | 1RK | 233.6434 |  | 35.0368 | 450 | NA | 1st & 3rd
4 |  | 1RK | 232.8361 |  | 35.0368 | 450 | NA | 1st & 3rd
5 |  | 1RK | 232.8361 |  | 33.8205 | 450 | NA | 1st & 3rd
2nd Floor
A Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 269.0785 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 269.8858 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd
B Wing
1 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 232.8361 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 227.6048 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
5 |  | 1RK | 226.7975 |  | 0 | 450 | NA | 2nd
Building No. 5
Ground Floor For Parking (A, B, C)
1st & 3rd Floor
A Wing
1 |  | 1RK | 223.2669 |  | 33.8205 | 450 | NA | 1st & 3rd
2 |  | 1RK | 223.2669 |  | 36.2424 | 450 | NA | 1st & 3rd
3 |  | 1RK | 223.2669 |  | 36.2424 | 450 | NA | 1st & 3rd
4 |  | 1RK | 223.2669 |  | 33.8205 | 450 | NA | 1st & 3rd
B Wing
1 |  | 1RK | 223.2669 |  | 33.8205 | 450 | NA | 1st & 3rd
2 |  | 1RK | 223.2669 |  | 36.2424 | 450 | NA | 1st & 3rd
3 |  | 1RK | 223.2669 |  | 36.2424 | 450 | NA | 1st & 3rd
4 |  | 1RK | 223.2669 |  | 33.8205 | 450 | NA | 1st & 3rd
C Wing
1 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 1st & 3rd
2 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 1st & 3rd
3 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 1st & 3rd
4 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 1st & 3rd
2nd Floor
A Wing
1 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
B Wing
1 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
C Wing
1 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
4 |  | 1RK | 223.2669 |  | 0 | 450 | NA | 2nd
Building No.6
Ground Floor For Parking
1st Floor
1 |  | 1RK | 224.0742 |  | 0 | 450 | NA | 1st
2 |  | 1RK | 224.0742 |  | 33.8313 | 450 | NA | 1st
3 |  | 1RK | 224.0742 |  | 33.8313 | 450 | NA | 1st
2nd Floor
1 |  | 1RK | 224.0742 |  | 0 | 450 | NA | 2nd
2 |  | 1RK | 224.0742 |  | 0 | 450 | NA | 2nd
3 |  | 1RK | 224.0742 |  | 0 | 450 | NA | 2nd
Building No.7
Ground Floor For Parking & Residential (A, B, C)
A Wing
1 |  | 2BHK | 416.8682 |  | 0 | 850 | NA | Gr.
2 |  | 2BHK | 416.8682 |  | 0 | 850 | NA | Gr.
1st & 3rd Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 1st & 3rd
2 |  | 2BHK | 457.3947 |  | 63.5184 | 850 | NA | 1st & 3rd
3 |  | 2BHK | 457.3947 |  | 63.5184 | 850 | NA | 1st & 3rd
4 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 1st & 3rd
B Wing
1 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 1st & 3rd
2 |  | 2BHK | 457.3947 |  | 63.5184 | 850 | NA | 1st & 3rd
3 |  | 2BHK | 457.3947 |  | 63.5184 | 850 | NA | 1st & 3rd
4 |  | 1BHK | 355.029 |  | 58.8898 | 650 | NA | 1st & 3rd
5 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 1st & 3rd
6 |  | 2BHK | 457.3947 |  | 65.2298 | 850 | NA | 1st & 3rd
C Wing
1 |  | 1BHK | 313.4369 |  | 0 | 650 | NA | 1st & 3rd
2 |  | 1BHK | 313.4369 |  | 0 | 650 | NA | 1st & 3rd
2nd Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
2 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 2nd
3 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
4 |  | 2BHK | 457.3947 |  | 30.1392 | 850 | NA | 2nd
B Wing
1 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 2nd
2 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
3 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
4 |  | 1BHK | 355.029 |  | 0 | 650 | NA | 2nd
5 |  | 2BHK | 457.3947 |  | 48.2765 | 850 | NA | 2nd
6 |  | 2BHK | 457.3947 |  | 48.2765 | 850 | NA | 2nd
C Wing
1 |  | 1BHK | 313.4369 |  | 0 | 650 | NA | 2nd
2 |  | 1BHK | 313.4369 |  | 53.7016 | 650 | NA | 2nd
4th Floor
A Wing
1 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
2 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 4th
3 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
4 |  | 2BHK | 457.3947 |  | 30.1392 | 850 | NA | 4th
B Wing
1 |  | 2BHK | 457.3947 |  | 0 | 850 | NA | 4th
2 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
3 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 4th
4 |  | 1BHK | 355.029 |  | 0 | 650 | NA | 4th
5 |  | 2BHK | 457.3947 |  | 48.2765 | 850 | NA | 4th
6 |  | 2BHK | 457.3947 |  | 48.2765 | 850 | NA | 4th
C Wing For Terrace Area
Building No.8
Ground Floor For Parking (A & B)
1st & 3rd Floor
A Wing
1 |  | 1BHK | 307.0862 |  | 71.0639 | 650 | NA | 1st & 3rd
2 |  | 1BHK | 307.0862 |  | 74.8098 | 650 | NA | 1st & 3rd
3 |  | 2BHK | 457.3947 |  | 65.2191 | 850 | NA | 1st & 3rd
4 |  | 2BHK | 457.3947 |  | 65.2191 | 850 | NA | 1st & 3rd
B Wing
1 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 1st & 3rd
2 |  | 2BHK | 457.3947 |  | 65.176 | 850 | NA | 1st & 3rd
3 |  | 2BHK | 457.3947 |  | 65.176 | 850 | NA | 1st & 3rd
4 |  | 2BHK | 457.3947 |  | 61.8069 | 850 | NA | 1st & 3rd
2nd Floor
A Wing
1 |  | 1BHK | 307.0862 |  | 59.0513 | 650 | NA | 2nd
2 |  | 1BHK | 307.0862 |  | 34.5632 | 650 | NA | 2nd
3 |  | 2BHK | 457.3947 |  | 50.3755 | 850 | NA | 2nd
4 |  | 2BHK | 457.3947 |  | 52.4853 | 850 | NA | 2nd
B Wing
1 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
2 |  | 2BHK | 457.3947 |  | 52.496 | 850 | NA | 2nd
3 |  | 2BHK | 457.3947 |  | 48.2658 | 850 | NA | 2nd
4 |  | 2BHK | 457.3947 |  | 50.3755 | 850 | NA | 2nd
Remarks:
Building No. 1, 2, 3 & 6 |  |  | Finishing work is pending. | [6 empty] | Finishing Work is pending.
Building No. 6 |  |  | Work is same as Last visit dtd. 04/05/2024.
Building No. 7 |  |  | Construction work has recently resumed.
Building No. 4, 5 & 8 |  |  | All work Completed. Please provide OC.
2. We considered saleable area of Flat as per Builder area sheet. 3. We have considered rate by verifying it from market inquire. 4. We have considered Other charges from cost sheet. 5. Car parking is subjected to authentic documentation. 6. We have updated Approved plans & CC of Building No. 2, 3 & 4 (on 08/09/2021). As per the revised approved plan dtd. 28/07/2020 Building No. 3 Wing D & Building No. 4 Wing C is eliminated from the project. 7. Since the project has received first CC on 23/02/2018., But construction work of Building No. 7 is under construction. 8. On site we met Mr. Sanjay : 9920732532. 7. On site we meet Mr. Deepak Jadhav - 9920732532.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Konnark Meadows
PHOTOGRAPHS OF PROPERTY : |  |  |  | Konnark Meadows
Google Maps :
1A
1A
1B
2A
2B
2C
2D
3A
3B
3C
6
6
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7
Bldg No.7

## C %1(A,B)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 40 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 2 | 0 | Progress |  |  | 10 | 16 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 12 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 16 | 12
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 26 | 42

## C%2
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## C%3
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## C% 4
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## C% 5
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 12.5 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 0.5 | 0 | Progress |  |  | 10 | 5 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 3.75 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 5 | 3.75
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 15 | 33.75

## C% 6
Particulars | totaL floor | 2
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 3 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 2 | 0 | 0
Flooring | Total Floor | completed Floor
| 2 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 2 | 0 |  | RCC | 0 | 0 |  |  | Excavation in process | 1% | 2%
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0 |  |  | Excavation Completed | 1% | 3%
| 2 | 0 |  | Plaster | 0 | 0 |  |  | Footing in Process | 3% | 8%
|  |  |  | Flooring | 0 | 0 |  |  | Footing Completed | 5% | 15%
|  |  |  | Wood & painting | 0 | 0 |  |  | Plinth in process | 7% | 20%
|  |  |  | Finishing | 0 | 0 |  |  | Plinth completed | 10% | 30%
|  |  |  | total | 10 | 30

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## C% 8
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 0 | Progress |  |  | 10 | 40 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 50 | 60

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0