## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/08/2025
CPC Name: |  |  |  |  | Axis Sanpada.
Date Of Property Visit |  |  |  |  | 2025-08-11
Name of the builder |  |  |  |  | Mr.Manoj Kumar Singh
Name of the builder company |  |  |  |  | M/s.Aman Developers
Name of the Project |  |  |  |  | Aman Paradise
Contact Details ( Name & Contact No.) |  |  |  |  | 02265610111/8767599990/8850101255
Name / No of the Building |  |  |  |  | 01 Building
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000020873
Project location details |  | Aman Paradise, Plot No.A-35, Sector No.16, Aamar Marg, Ulwe, Kharkopar, Panvel, Raigad.
Plot No |  | A-35 |  |  | Sector No |  | 16
Road |  | Aamar Marg |  |  | Village |  | Ulwe
City |  | Kharkopar |  |  | District |  | Raigad
Taluka |  | Panvel |  |  | Pin Code |  | 410206
Near by Landmark |  | Ramsheth Thakur International Sports Complex |  |  | Distance from city centre: |  | About 1.1 Km from Kharkopar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Road |  | Open Plot |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 18.959844, 73.021327
Location Link |  | https://goo.gl/maps/boNkcG3BcH4qQF619
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 149.87
Permissible FSI |  |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 224.31
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-15661/TPO(NM & K)2018/2473 |  |  |  | Dated | 02/04/2018.
Approved Floor plan No. |  | CIDCO/BP-15661/TPO(NM & K)2018/2473 |  |  |  | Dated | 02/04/2018.
Commencement Certificate No. |  | CIDCO/BP-15661/TPO(NM & K)2018/2473 Valid Up to: G + 4th Floors |  |  |  | Dated | 06/04/2018. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 06/04/2018. |  | Expected Completion |  | 2024-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 224.31 |  | Approved no of units |  | Flats = 10
Approved no of Floors |  | G + 4th Floors |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 3 Floor, Painting upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 85% |  | 93.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 6200
Water, MSEB, Dev.charges | [5 empty] | 300000/-
Society formation charges | [5 empty] | 50000/-
Documentation Charges | [5 empty] | 15000/-
Recommended rate of Parking | [5 empty] | 100000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 4960
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
1 |  | 10 | 2819.6567 |  |  | 4349.4781
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Ground Floor is Parking
1st Floor
1 |  | 1 RK | 214.9033 |  | 0 | 311.6097 | N | 1st Floor
2 |  | 1 RK | 245.0694 |  | 0 | 355.3506 | N
3 |  | 1 BHK | 357.6339 |  | 0 | 518.5692 | N
2nd Floor
1 |  | 1 RK | 214.9033 |  | 0 | 311.6097 | N | 2nd Floor
2 |  | 1 RK | 245.0694 |  | 0 | 355.3506 | N
3 |  | 1 BHK | 357.6339 |  | 0 | 518.5692 | N
3rd Floor
1 |  | 1 RK | 213.8269 |  | 161.8906 | 390.9942 | N | 3rd Floor
2 |  | 1 BHK | 357.5263 |  | 172.7138 | 604.77 | N
4th Floor
1 |  | 1 RK | 240.6292 |  | 0 | 348.9124 | N | 4th Floor
2 |  | 1 BHK | 372.4613 |  | 93.6737 | 633.7426 | N
Remarks:
1. Construction work was stopped. Work is same as last visit( 09/08/2022). No official person available on site. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Cornice. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7.Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 8. We have considered Other charges from cost sheet. 9. The project has received first CC on 06/04/2018, But construction work is not yet completed. 10. As per RERA, completion period of project Aman Paradise is expired on 31/12/2024 but still project is under construction. | [8 empty] | Construction work was stopped. Work is same as last visit( 09/08/2022).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
Inspected By : |  | Mayur Ranvare |  | Report Prepared By : |  |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Aman Paradise
Google Map :

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 1 | 25% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 2.5 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 1.25 | 0 | 0
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 2.5 | 1.25
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 77.5% | 86.25% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Aman Paradise | 1BHK | 310 | 449.5 | 6674.0823 | 3000000
squareyards | Aman Paradise | 1BHK | 0 | 640 | 5300 | 3392000
squareyards | Aman Paradise | 1BHK | 0 | 665 | 5299.2481 | 3524000
squareyards | Aman Paradise | 1RK | 0 | 467 | 5599.5717 | 2615000
Average |  |  |  |  | 5718.2255
Valuation Adopted |  |  |  |  | 5700