## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-08-11 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Luxora Realtors Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Luxora Realtors Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Crystal Antara | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Namrata Maru 9892230344
Site Person - Contact Details (Name & Contact No.) |  |  |  | Namrata Maru 9892230344
Name / No of the Building |  |  |  | Building T6 & T7
Name / No of the Existing Building | [16 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700054437 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Crystal Antara, Gut No.64/1, 64/2, 64/3/1, 64/3/2, 68/1A, 68/1B, 68/2C, 68/3B, 59A/30/2/1, 59A/30/2/2, 59A/30/2/3, 67/1A, 67/1B, 67/2A, 67/2B, 67/3, 69/1, 69/2, 69/3, 69/4, near Crystal Spires Towers, Ghodbunder Service Road, Bhavani Nagar, Chitalsar Manpada, Thane West, Thane, Thane - 400607. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Gut No |  | 64/1, 64/2, 64/3/1, 64/3/2, 68/1A, 68/1B, 68/2C, 68/3B, 59A/30/2/1, 59A/30/2/2, 59A/30/2/3, 67/1A, 67/1B, 67/2A, 67/2B, 67/3, 69/1, 69/2, 69/3, 69/4 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Bhavani Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Ghodbunder Service Road |  | Locality/Village |  | Chitalsar Manpada | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Thane West |  | District |  | Thane | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Thane |  | Pin Code |  | 400607 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Crystal Spires Towers |  | Distance from city centre: |  | 8.2 KM from Thane Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Dev Tirth Co Op Society
West | NA | Row Houses |  |  | Row Houses
North | NA | Tower No.5 |  |  | Crystal Spires
South | NA | Nalla |  |  | Nalla
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.234393, 72.974294
Location Link |  | https://maps.app.goo.gl/VesrobeS7uB7U84L8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 54164.4
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.72118
Total FSI availaible for the project |  |  |  | 1.8212
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 98643.19
Total number of Buildings |  |  |  | 02 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Muncipal Cooperation (TMC) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | S04/0086/15-TMC/TD-DP/TPS/0009/23 |  |  | Dated | 2023-10-11 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | S04/0086/15-TMC/TD-DP/TPS/0009/23 |  |  | Dated | 2023-10-11 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | S04/0086/15-TMCB/TDD/0054/P/C/24 /Auto DCR |  |  | Dated | 2024-01-01 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Building No.T6 = G + 1st to 4th P + 1st to 48th Floor Building No.T7 = G + 1st to 4th P + 1st to 7th Floor | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | #REF! |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | SIA/MH/INFRA2/432238/2023 |  |  | Dated | 2024-02-02 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | Building No.T6 & T7 = G + 1st to 4th P + 1st to 48th Floor (180.40 Mt) | [15 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | Building No.T6 & T7 = G + 1st to 4th P + 1st to 48th Floor (180.40 Mt) |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building T6 & T7 (Sq.Mt) |  |  | 37513.22
Approved no of units |  |  | Flats - 208, Shops - 1
Approved no of Floors |  |  | Building No.T6 = G + 1st to 4th P + 1st to 48th Floor Building No.T7 = G + 1st to 4th P + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.T6 = G + 1st to 4th P + 1st to 48th Floor
Building No.T7 = G + 1st to 4th P + 1st to 48th Floor
Expected Completion |  |  | As per RERA - 31/12/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | swimming Pool, GYM, Kids Area, Indoor Games Area, Yoga, SPA, CCTV Monitoring, Banquet/Multi-Purpose Hall.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.T6 = G + 1st to 4th P + 1st to 48th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 1 Floor Completed | , RCC upto 7 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 48 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 12
Excavation |  | 48 | 100% | 15.87% |  | 49.39% |  | Excavation in process | 24
Plinth |  | 48 | 100% |  |  |  |  | Excavation Completed | 48
RCC (Including podiums) |  | 7 | 14.29% |  |  |  |  | Footing in Process | 12
Brickwork | Brickwork & Internal Plaster | 1 | 2.083% |  |  |  |  | Footing Completed | 24
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 36
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 48
Construction details: |  | Building No.T7 = G + 1st to 4th P + 1st to 48th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 1 Floor Completed | , RCC upto 7 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 48 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 12
Excavation |  | 48 | 100% | 15.87% |  | 49.39% |  | Excavation in process | 24
Plinth |  | 48 | 100% |  |  |  |  | Excavation Completed | 48
RCC (Including podiums) |  | 7 | 14.29% |  |  |  |  | Footing in Process | 12
Brickwork | Brickwork & Internal Plaster | 1 | 2.083% |  |  |  |  | Footing Completed | 24
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 36
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 48
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 15000 |  |  | 13000 to 15000 by viraj on 08/11/2024 | [8 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 24000 | [11 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
BCAM Charges for 18 months |  |  |  |  | 15000 | [11 empty] | 1200000 | 600000 | 300000 | 300000
FCAM Charges for 60 months |  |  |  |  | 20000 | [11 empty] | 1300000 | 700000 | 350000 | 400000
Other Charges |  |  |  |  | 50000 | [11 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 500000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 12000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. T6 |  | 1 |  | 1400.0735 |  | 2170.1139
Total |  | 1 |  | 1400.0735 |  | 2170.1139
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. T6 |  | 184 |  | 217625.045 |  | 326437.5676
Building No. T7 |  | 24 |  | 21428.8636 |  | 32143.2953
Total |  | 208 |  | 239053.9086 |  | 358580.8629
Grand Total |  | 209 |  | 240453.9821 |  | 360750.9768
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Building No. T6
Ground Floor for Commercial & Parking
1 |  | Shop | 1400.0735 | 0 | 1400.0735 | 0 | 2170.1139
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No. T6
1st to 3rd Podium Floor for Parking
4th Podium Floor for Recreational Activity Floor
1st Floor
1 |  | Multipurpose Hall
2 |  | 4BHK | 1495.8731 | 190.0922 | 1685.9653 | 0 | 2528.948
3 |  | 2BHK | 916.447 | 151.7724 | 1068.2194 | 0 | 1602.329 |  | 82.9462 | 14.095 | 97.0412
4 |  | Multipurpose Hall |  | 0 | 0 | 0 | 0
2nd Floor
1 |  | Fitness Center
2 |  | 4BHK | 1495.8731 | 190.0922 | 1685.9653 | 0 | 2528.948
3 |  | 1BHK | 522.8075 | 23.3579 | 546.1654 | 0 | 819.248 |  | 82.9462 | 14.095 | 97.0412
4 |  | Refuge Area |  | 0 | 0 | 0 | 0
3rd Floor
1 |  | 3BHK | 1109.4455 | 271.2528 | 1380.6983 | 0 | 2071.0474 |  | 12426.2845 | 16438.1619
2 |  | 4BHK | 1495.8731 | 190.0922 | 1685.9653 | 0 | 2528.948 |  | 15173.6879 | 10415.1388
3 |  | 3BHK | 916.447 | 151.7724 | 1068.2194 | 0 | 1602.329 |  | 9613.9742 | 8638.3522
4 |  | 2BHK | 736.4729 | 149.512 | 885.9848 | 0 | 1328.9773 |  | 7973.8636 | 0
4th, 5th, 7th to 9th, 11th to 13th, 15th to 17th, 19th to 21st, 23rd to 25th, 27th to 29th, 31st to 33rd, 35th to 37th, 39th to 41st, 43rd to 45th, 47th & 48th Floor
1 |  | 3BHK | 1108.692 | 170.3941 | 1279.0861 | 0 | 1918.6292
2 |  | 4BHK | 1495.8731 | 190.0922 | 1685.9653 | 0 | 2528.948
3 |  | 3BHK | 916.447 | 151.7724 | 1068.2194 | 0 | 1602.329
4 |  | 1BHK | 524.6374 | 23.3579 | 547.9952 | 0 | 821.9929
10th, 18th, 22nd, 30th, 34th, 38th & 46th Floor
1 |  | 3BHK | 1108.692 | 170.3941 | 1279.0861 | 0 | 1918.6292 |  |  |  | 10372.1054
2 |  | 4BHK | 1495.8731 | 190.0922 | 1685.9653 | 0 | 2528.948 |  |  |  | 13048.9687
3 |  | 3BHK | 916.447 | 151.7724 | 1068.2194 | 0 | 1602.329
4 |  | 3BHK | 918.1692 | 151.6648 | 1069.834 | 0 | 1604.7509
6th, 14th, 26th & 42nd Floor (Part Refuge Area)
1 |  | 3BHK | 1108.692 | 170.3941 | 1279.0861 | 0 | 1918.6292
2 |  | 4BHK | 1495.8731 | 190.0922 | 1685.9653 | 0 | 2528.948
3 |  | 3BHK | 916.447 | 151.7724 | 1068.2194 | 0 | 1602.329 |  |  |  | 14042.0597
4 |  | Refuge Area
Building No. T7
1st to 3rd Podium Floor for Parking
4th Podium Floor for Recreational Activity Floor
1st Floor
1 |  | 3BHK | 896.7488 | 130.0291 | 1026.778 | 0 | 1540.1669
2 |  | Multipurpose Hall |  | 0 | 0 | 0 | 0
3 |  | Multipurpose Hall
4 |  | 3BHK | 895.7801 | 130.1368 | 1025.9168 | 0 | 1538.8753 |  | 82.9462 | 14.095 | 10332.5873
2nd Floor
1 |  | 3BHK | 896.7488 | 130.0291 | 1026.778 | 0 | 1540.1669
2 |  | Fitness Center |  | 0 | 0 | 0 | 0
3 |  | Fitness Center |  | 1 | 1 | 1 | 2.5
4 |  | 2BHK | 639.0587 | 63.2923 | 702.351 | 0 | 1053.5265 |  |  |  | 11350.2929
3rd Floor
1 |  | 3BHK | 896.7488 | 130.0291 | 1026.778 | 0 | 1540.1669
2 |  | 2BHK | 704.7191 | 82.3446 | 787.0637 | 0 | 1180.5955
3 |  | 2BHK | 710.6393 | 82.3446 | 792.9839 | 0 | 1189.4758 |  | 66.5948
4 |  | 3BHK | 895.7801 | 130.1368 | 1025.9168 | 0 | 1538.8753
4th, 5th & 7th Floor
1 |  | 3BHK | 896.7488 | 130.0291 | 1026.778 | 0 | 1540.1669
2 |  | 2BHK | 704.7191 | 82.3446 | 787.0637 | 0 | 1180.5955
3 |  | 2BHK | 705.4726 | 82.3446 | 787.8172 | 0 | 1181.7257 |  | 66.5948
4 |  | 3BHK | 895.7801 | 130.1368 | 1025.9168 | 0 | 1538.8753
6th Floor (Part Refuge Area)
1 |  | 3BHK | 896.7488 | 130.0291 | 1026.778 | 0 | 1540.1669
2 |  | 2BHK | 704.7191 | 82.3446 | 787.0637 | 0 | 1180.5955 |  | 14399.5125
3 |  | 2BHK | 705.4726 | 82.3446 | 787.8172 | 0 | 1181.7257
4 |  | 1BHK | 490.0849 | 39.8268 | 529.9117 | 0 | 794.8676
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + Utility Area + E.P Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 08/11/2024.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Crystal Antara
Layout :
Google Map :
Formulas:
Chitalsar Manpada = [Chitalsar Manpada, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F107: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H138: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | There are inadequate transportation options to get to the project and the area is not developed.
15 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sales plan.
16 | River located on west side of the project.
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate