## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | M/s.Millennium Infra
Name of the builder company |  |  |  | M/s.Millennium Infra
Name of the Project |  |  |  | Millennium Flora
Contact Details ( Name & Contact No.) |  |  |  | 8080522229/9323035239
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P52000033391
Project location details |  | Millennium Flora, Plot No.09, Sector - 17, near Asha Harmony, IIG road, New Panvel, New Panvel, Panvel, Raigad - 410206.
Plot No |  | 09, Sector - 17
Road |  | IIG road |  | Locality/Village |  | New Panvel
City |  | New Panvel |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Asha Harmony |  | Distance from city centre: |  | 2.1 KM from Khandeshwar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | MPEDA Regional Centre
West | NA | NA |  |  | Internal road
North | NA | NA |  |  | Aura luxisca
South | NA | NA |  |  | More Hospital
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.0077184,73.1041488
Location Link |  | https://goo.gl/maps/GejAYYv1z2cUVvYv5?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2743.42
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 1.7165
Total FSI availaible for the project |  |  |  | 3.2165
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 8824.216
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | PMP/NRV/16092/JK-128/2022 |  |  | Dated | 2022-01-14
Approved Floor plan No. |  | PMP/NRV/16092/JK-128/2022 |  |  | Dated | 2022-01-14
Commencement Certificate No. |  | PMC/TP/N.Panvel/1709/21-22/16092/128/2022 |  |  | Dated | 2022-01-14
Valid Up to: G/St + 1st to 14th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 8824.216
Approved no of units |  |  | Flats - 102, Shops - 13
Approved no of Floors |  |  | G/St + 1st to 14th Floor
Proposed no of Floors |  |  | G/St + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 31/08/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Part I = G/St + 1st to 14th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 90.36% |  | 94.64% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 92.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 13 | 92.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 28.57% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Part II = G/St + 1st to 14th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed, Brickwork upto 6 Floor Completed, Internal Plaster upto 6 Floor Completed, External Plaster upto 3 Floor Completed.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed, Brickwork upto 6 Floor Completed, Internal Plaster upto 6 Floor Completed, External Plaster upto 3 Floor Completed. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 45.24% |  | 70.36% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 10 | 66.67% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 6 | 42.86% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 6 | 42.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 21.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Average Progress % (Part I & II) |  | 67.8% |  | Average Disbursement %(Part I & II) |  | 82.5% |  | Piling Work in process | 0
[8 empty] | Excavation in process | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. (on Saleable area) |  |  |  |  | 8500 |  |  |  | Mr smith pal | 2023-01-17 | cost sheet | 8000 to 8500 | 16000 to 17000
Recommended rate of the shop Per Sq. Ft. (on Saleable area) |  |  |  |  | 17000
Recommended rate of the Office Per Sq. Ft. (on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | 50/- from 4th Floor
Development Charges |  |  |  |  | 450000
Club membership |  |  |  |  | 150000
Legal Charges |  |  |  |  | 10000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 100000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 500000
Distressed valuation of the Property |  |  |  |  | 6800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 13 |  | 4968.2211 |  | 10280
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 102 |  | 63806.8823 |  | 115700
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Ground Floor for Commercial & Parking
1 |  | Shop | 395.4155 | 0 | 815 | Ground Floor for Commercial & Parking
2 |  | Shop | 350.7772 | 0 | 725
3 |  | Shop | 389.0433 | 0 | 805
4 |  | Shop | 389.0433 | 0 | 805
5 |  | Shop | 349.1734 | 0 | 725
6 |  | Shop | 349.1734 | 0 | 725
7 |  | Shop | 522.9689 | 0 | 1080
8 |  | Shop | 349.1734 | 0 | 725
9 |  | Shop | 349.1734 | 0 | 725
10 |  | Shop | 389.0433 | 0 | 805
11 |  | Shop | 389.0433 | 0 | 805
12 |  | Shop | 350.7772 | 0 | 725
13 |  | Shop | 395.4155 | 0 | 815
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
1st & 2nd Floor for Parking
3rd Floor for Recreational Area
4th, 5th, 6th, 7th, 9th Floor for Residential
401,..,901 |  | 1BHK | 388.3113 | 0 | 740 | 4th, 5th, 6th, 7th, 9th Floor for Residential |  |  | 1.9057
402,..,902 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
403,..,903 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
404,..,904 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
405,..,905 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
406,..,906 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
407,..,907 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
408,..,908 |  | 3BHK | 762.5971 | 0 | 1390 |  |  |  | 1.8227
409,..,909 |  | 2BHK | 587.0578 | 0 | 1040 |  |  |  | 1.7715
410,..,910 |  | 2BHK | 587.0578 | 0 | 1040 |  |  |  | 1.7715
411,..,911 |  | 3BHK | 762.5971 | 0 | 1390 |  |  |  | 1.8227
412,..,912 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
8th Floor (Part Refuge Area)
801 |  | 1BHK | 388.3113 | 0 | 740 | 8th Floor (Part Refuge Area) |  |  | 1.9057
802 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
803 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
804 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
805 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
806 |  | 3BHK | 762.5971 | 0 | 1390 |  |  |  | 1.8227
807 |  | 2BHK | 587.0578 | 0 | 1040 |  |  |  | 1.7715
808 |  | 2BHK | 587.0578 | 0 | 1040 |  |  |  | 1.7715
809 |  | 3BHK | 762.5971 | 0 | 1390 |  |  |  | 1.8227
810 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
10th Floor (Part Terrace Area)
1001 |  | 1BHK | 388.3113 | 0 | 740 | 10th Floor (Part Terrace Area) |  |  | 1.9057
1002 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
1003 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
1004 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
1005 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
1006 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
1007 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
1008 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
11th Floor
1101 |  | 1BHK | 388.3113 | 0 | 740 | 11th Floor |  | 369.8107 | 1.9057
1102 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
1103 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
1104 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
1105 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
1106 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
12th, 13th & 14th Floor
1201 ,.., 1401 |  | 1BHK | 388.3113 | 0 | 740 | 12th, 13th & 14th Floor |  |  | 1.9057
1202 ,.., 1402 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
1203 ,.., 1403 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
1204 ,.., 1404 |  | 2BHK | 686.022 | 0 | 1210 |  |  |  | 1.7638
1205 ,.., 1405 |  | 3BHK | 877.998 | 0 | 1580 |  |  |  | 1.7995
1206 ,.., 1406 |  | 1BHK | 388.3113 | 0 | 740 |  |  |  | 1.9057
Remarks:
* | Part I = Construction work is in process at the time of Visit. Part II = Work is same as last visit (08/08/2024).
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony .
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Miss. Shaila - 7400449982.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mayur Ranvare |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Millennium Flora
Google Map :
Formulas:
New Panvel = [New Panvel, row above]
Part I
Part II
Part II
Part I
Part II
Part II
Part I
Part I
Part II

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted