## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 22/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-20
Name of the builder group |  |  |  | Nhi Developers LLP
Name of the builder company |  |  |  | Nhi Developers LLP
Name of the Project |  |  |  | Akshaya and Jayshree Redevelopment
Provided Contact Details ( Name & Contact No.) |  |  |  | 02228997038 / 28338466
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Piyush : 7304275528
Name / No of the Building |  |  |  | Building No.1 & 2
Name of existing Building |  |  |  | Akshaya & Jayshree CHS LTD
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800049511
Project location details |  | Akshaya and Jayshree Redevelopment, CTS No.263/B & Redevelopment of Akshaya & Jayshree CHS LTD, near Jai Abhilasha CHS, Mahisha Mardini Temple Road, Jayraj Nagar, Borivali, Borivali (W), Borivali, Mumbai - 400092.
CTS No |  | 263/B & Redevelopment of Akshaya & Jayshree CHS LTD
Locality |  | Jayraj Nagar
Road |  | Mahisha Mardini Temple Road |  | Locality/Village |  | Borivali
City |  | Borivali (W) |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400092
Nearby Landmark |  | Jai Abhilasha CHS |  | Distance from city centre: |  | 1.9 KM from Borivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Building
North | NA | NA |  |  | Baburao Paranjape Marg
South | NA | NA |  |  | Yoganand Society
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.2329498, 72.8429295
Location Link |  | https://goo.gl/maps/zxTjxqrmxjUmJRQ68
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4445.19
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.3958
Total FSI availaible for the project |  |  |  | 2.3958
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10649.9
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No Building No.01 |  | P-8454/2021/(263/B)/R/C WARD/BORIVALI-R/C/337/1/NEW |  |  | Dated | 2022-01-31
Approved Floor plan No. Building No.01 |  | P-8454/2021/(263/B)/R/C WARD/BORIVALI-R/C/337/1/NEW |  |  | Dated | 2022-01-31
Layout Approval No Building No.02 |  | P-8454/2021/(263/B)/R/C WARD/BORIVALI-R/C/337/1/NEW |  |  | Dated | 2022-01-29
Approved Floor plan No. Building No.02 |  | P-8454/2021/(263/B)/R/C WARD/BORIVALI-R/C/337/1/NEW |  |  | Dated | 2022-01-29
Commencement-CC No Valid Up to: Building No.2 |  | P-8454/2021/(263/B)/R/C Ward/BORIVALI-R/C/CC/1/New |  |  | Dated | 2023-01-12
|  | This C.C. is granted for work up to plinth level only as per approved IOD plans dated 29.01.2022. |  |  | Valid Upto Date | 2024-01-11
Commencement-CC No Valid Up to: |  | P-8453/2021/(263/B)/R/C Ward/BORIVALI-R/C/FCC/1/New |  |  | Dated | 2023-08-23
|  | This C.C. is granted and further extended for entire work of building comprising of Wing ‘A’ and ‘B’ consisting of ground (pt.)/Stilt (Pt) + 1st to 4th Floor for Podium + 5th to 22nd Upper Floors + LMR/OHT as per approved IOD plan dated 31.01.2022. |  |  | Valid Upto Date | 2024-01-11
Airport Authority of India NOC No. |  | JUHU/WEST/B/092821/625234 Valid Upto : 185.41 M |  |  | Date Valid Upto: | 28/10/2021 27/10/2029
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 422.67
Approved no of units |  |  | Flats - 210, Rehab Shops - 07, Sale Offices - 07
Approved no of Floors |  |  | Building No.1(Wing A & B) = Gr/Stilt + 1st to 4th (Part Podium) + 5th to 22nd Floor Building No.2 = Gr/Stilt + 1st to 4th Floor (Commercial)
Proposed no of Floors |  |  | Building No.1(Wing A) = Gr/Stilt + 1st to 4th (Part Podium) + 5th to 22nd Floor
Building No.1(Wing B) = Gr/Stilt + 1st to 4th (Part Podium) + 5th to 22nd Floor
Building No.2 = Gr/Stilt + 1st to 4th Floor (Commercial)
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1(Wing A) = Gr/Stilt + 1st to 4th (Part Podium) + 5th to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 21 Floor, Flooring upto 19 Floor, Painting upto 19 Floor Completed | , External Plaster upto 21 Floor, Flooring upto 19 Floor, Painting upto 19 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 21 Floor, Flooring upto 19 Floor, Painting upto 19 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 87.5% |  | 94.09% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 95.45% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 19 | 86.36% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 19 | 86.36% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Building No.1(Wing B) = Gr/Stilt + 1st to 4th (Part Podium) + 5th to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 18 Floor, Painting upto 18 Floor Completed | , External Plaster upto 20 Floor, Flooring upto 18 Floor, Painting upto 18 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 20 Floor, Flooring upto 18 Floor, Painting upto 18 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 86.36% |  | 93.64% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 20 | 90.91% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 18 | 81.82% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 81.82% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Building No.2 = Gr/Stilt + 1st to 4th Floor (Commercial) | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 2
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 19000 |  |  | 17000 to 19000 | Nikhil | 2024-02-22 | Verbal
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 28000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 22000
Floor Rise Rate
Development Charges |  |  |  |  | 330000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1000000
Distressed valuation of the Property |  |  |  |  | 22400
Commercial Area Details : Building No. 02
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop | Rehab | 7 |  | 1899.5769 |  | 3039.323
Office | Sale | 7 |  | 3555.9009 |  | 5689.4414
Total |  | 14 |  | 5455.4778 |  | 8728.7644
Residential Area Details : Building No. 01
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 104 |  | 71581.6764 |  | 110951.5984
Wing B |  | 106 |  | 64712.7374 |  | 100304.743
Total |  | 210 |  | 136294.4138 |  | 211256.3415
Grand Total |  | 224 |  | 141749.8916 |  | 219985.1059
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Rehab/ Sale | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Building No.2
Ground Floor for Commercial & Parking
1 | Rehab | Shop | 330.8988 | 0 | 529.4381 | Ground Floor for Commercial & Parking |  |  | 36831.5009
2 | Rehab | Shop | 288.7914 | 0 | 462.0662
3 | Rehab | Shop | 176.0116 | 0 | 281.6185
4 | Rehab | Shop | 199.0398 | 0 | 318.4637
5 | Rehab | Shop | 222.3708 | 0 | 355.7933 |  |  |  | 39348.6941
6 | Rehab | Shop | 347.1928 | 0 | 555.5085
7 | Rehab | Shop | 335.2717 | 0 | 536.4347
1st Floor
1 | Sale | Office | 619.818 | 0 | 991.7088 | 1st Floor
2 | Sale | Office | 462.26 | 0 | 739.616
3 | Sale | Office | 634.78 | 0 | 1015.648
4 | Sale | Office | 232.5024 | 0 | 372.0038
2nd & 3rd Floor Parking
4th Floor for Commercial & Society Office (Part Terrace Area)
1 | Sale | Office | 691.3044 | 0 | 1106.0871 | 4th Floor for Commercial & Society Office (Part Terrace Area)
2 | Sale | Office | 462.26 | 0 | 739.616
3 | Sale | Office | 452.976 | 0 | 724.7616
Flat No. (Approved Plan) | Sale/ Rehab | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Building No.1
Wing A
Ground Floor for Parking
1st to 3rd Podium floor for Parking
4th Podium Floor for Parking & Fitness Center
5th Floor for Residential
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 5th Floor for Residential
2 | - | 2BHK | 652.9442 | 0 | 1012.0636
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533 |  |  | 81.185
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
6th & 7th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 6th & 7th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
8th Floor (Part Refuge Area)
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 8th Floor (Part Refuge Area)
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | Refuge Area
4
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
9th & 10th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 9th & 10th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
11th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 11th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
12th & 13th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 12th & 13th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
14th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 14th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
15th Floor (Part Refuge Area)
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 15th Floor (Part Refuge Area)
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | Refuge Area
4
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
16th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 16th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 679.7466 | 0 | 1053.6072
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
17th Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 17th Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 707.1948 | 0 | 1096.1519
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
18th to 22nd Floor
1 | - | 1BHK | 454.1332 | 0 | 703.9064 | 18th to 22nd Floor
2 | - | 2BHK | 658.111 | 0 | 1020.072
3 | - | 2BHK | 713.6532 | 0 | 1106.1625
4 | - | 1BHK | 441.1087 | 0 | 683.7185
5 | - | 3BHK | 933.1312 | 0 | 1446.3533
6 | - | 3BHK | 924.4123 | 0 | 1432.8391
Wing B
Ground Floor for Parking
1st to 3rd Podium floor for Parking
4th Podium Floor for Parking & Fitness Center
5th Floor for Residential
1 | - | 3BHK | 780.8206 | 0 | 1210.2719 | 5th Floor for Residential
2 | - | 3BHK | 780.8206 | 0 | 1210.2719
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | - | 2BHK | 595.6798 | 0 | 923.3036
5 | - | 2BHK | 543.7973 | 0 | 842.8858
6 | - | 1BHK | 403.3271 | 0 | 625.157
6th & 7th Floor
1 | - | 3BHK | 780.8206 | 0 | 1210.2719 | 6th & 7th Floor
2 | - | 3BHK | 780.8206 | 0 | 1210.2719
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | - | 2BHK | 595.6798 | 0 | 923.3036
5 | - | 2BHK | 543.7973 | 0 | 842.8858
6 | - | 1BHK | 403.3271 | 0 | 625.157
8th Floor (Part Refuge Area)
1 | - | 3BHK | 780.8206 | 0 | 1210.2719 | 8th Floor (Part Refuge Area)
2 | - | 3BHK | 780.8206 | 0 | 1210.2719
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | Refuge Area
5 | - | 2BHK | 543.7973 | 0 | 842.8858
6 | - | 1BHK | 403.3271 | 0 | 625.157
9th & 10th Floor
1 | - | 3BHK | 780.8206 | 0 | 1210.2719 | 9th & 10th Floor
2 | - | 3BHK | 780.8206 | 0 | 1210.2719
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | - | 2BHK | 595.6798 | 0 | 923.3036
5 | - | 2BHK | 543.7973 | 0 | 842.8858
6 | - | 1BHK | 424.6398 | 0 | 658.1917
11th Floor
1 | - | 3BHK | 780.8206 | 0 | 1210.2719 | 11th Floor
2 | - | 3BHK | 780.8206 | 0 | 1210.2719
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | - | 2BHK | 595.6798 | 0 | 923.3036
5 | - | 2BHK | 543.7973 | 0 | 842.8858
6 | - | 1BHK | 424.6398 | 0 | 658.1917
12th & 13th Floor
1 | - | 3BHK | 789.4318 | 0 | 1223.6192 | 12th & 13th Floor
2 | - | 3BHK | 789.4318 | 0 | 1223.6192
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | - | 2BHK | 595.6798 | 0 | 923.3036
5 | - | 2BHK | 610.4264 | 0 | 946.161
6 | - | 1BHK | 424.6398 | 0 | 658.1917
14th Floor
1 | - | 3BHK | 806.7618 | 0 | 1250.4808 | 14th Floor
2 | - | 3BHK | 806.7618 | 0 | 1250.4808
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | - | 2BHK | 595.6798 | 0 | 923.3036
5 | - | 2BHK | 610.4264 | 0 | 946.161
6 | - | 1BHK | 424.6398 | 0 | 658.1917
15th Floor (Part Refuge Area)
1 | - | 3BHK | 806.7618 | 0 | 1250.4808 | 15th Floor (Part Refuge Area)
2 | - | 3BHK | 806.7618 | 0 | 1250.4808
3 | - | 1BHK | 446.9213 | 0 | 692.728
4 | Refuge Area
5 | - | 2BHK | 610.4264 | 0 | 946.161
6 | - | 1BHK | 424.6398 | 0 | 658.1917
16th Floor
1 | - | 3BHK | 806.7618 | 0 | 1250.4808 | 16th Floor
2 | - | 3BHK | 806.7618 | 0 | 1250.4808
3 | - | 1BHK | 469.9562 | 0 | 728.4322
4 | - | 2BHK | 636.4753 | 0 | 986.5367
5 | - | 2BHK | 610.4264 | 0 | 946.161
6 | - | 1BHK | 424.6398 | 0 | 658.1917
17th Floor
1 | - | 3BHK | 806.7618 | 0 | 1250.4808 | 17th Floor
2 | - | 3BHK | 806.7618 | 0 | 1250.4808
3 | - | 1BHK | 469.9562 | 0 | 728.4322
4 | - | 2BHK | 636.4753 | 0 | 986.5367
5 | - | 2BHK | 610.4264 | 0 | 946.161
6 | - | 1BHK | 424.6398 | 0 | 658.1917
18th to 22nd Floor
1 | - | 3BHK | 806.7618 | 0 | 1250.4808 | 18th to 22nd Floor
2 | - | 3BHK | 806.7618 | 0 | 1250.4808
3 | - | 1BHK | 469.9562 | 0 | 728.4322
4 | - | 2BHK | 636.4753 | 0 | 986.5367
5 | - | 2BHK | 610.4264 | 0 | 946.161
6 | - | 1BHK | 424.6398 | 0 | 658.1917
Remarks:
* | Building No.1 = Construction work is in process at the time of visit. Building No.2 = Work not yet Started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 22/02/2024
* | We refer latest CC for Building No.01 from Rera & for Building No.02 from MCGM site.
* | We refer Aviation NOC from MCGM site.
* | Sale/ Rehab Statement is not provided in latest approved floor plan of Building No.01 dtd (31/01/2022)
* | We have updated revised approved CC on 08/04/2024.
* | Since building no.2 have received CC on 12/01/2023, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Roshan Kudalkar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Akshaya and Jayshree Redevelopment
Layout :
Google Map :
Formulas:
Borivali = [Borivali, row above]
Building No.02
Building No.01
Wing B
Building No.01
Wing A
Building No.02
Building No.01 (A Wing)
Building No.01 (B Wing)
A Wing
B Wing
Wing B
Wing A
Wing B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted