## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-14
Name of the builder group |  |  |  | M/s.Ananta Developers
Name of the builder company |  |  |  | M/s.Ananta Developers
Name of the Project |  |  |  | Anant Apartment
Contect Details ( Name & Contect No.) |  |  |  | 8237410994
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Arif 7498088998
Name / No of the Building |  |  |  | A Wing
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet
RERA No. |  |  |  | P99000026731
Project location details |  | Anant Apartment, Gut No.240, Plot No.34 & Gut No.234, Plot No.29, New Satpati Road, Alyali, Palghar West, Palghar, Palghar.
Gut No |  | 240, Plot No.34 & Gut No.234, Plot No.29
Road |  | New Satpati Road |  | Village |  | Alyali
City |  | Palghar West |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Near by Landmark |  | Bandhan Marriage Lawns |  | Distance from city centre: |  | 3Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | House
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | New Satpati Road
South | NA | NA |  |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.696543, 72.745444
Location Link |  | https://goo.gl/maps/674tASTRBVU3TLY18?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1192.8
Permissible FSI |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  | 0.15614
Total FSI availaible for the project |  |  |  | 1.3561
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 1617.6
Total number of Buildings |  |  |  | 01 Wing
Approval Detail : Plan approval
Layout Approval No |  | B.V.109 |  |  | Dated | 19/03/2018.
Approved Floor plan No. |  | B.V.109 |  |  | Dated | 19/03/2018.
Commencement Certificate No. |  | P.N.P/BD/KA-109/2017-2018 |  |  | Dated | 19/03/2018.
Valid Up to: A Wing = Gr. + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 1617.6
Approved no of units |  |  | Flats - 31, Shops - 04
Approved no of Floors |  |  | A Wing = Gr. + 1st to 4th Floor
Proposed no of Floors |  |  | A Wing = Gr. + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | A Wing = Gr. + 1st to 4th Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 1 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 4 Floor completed, Flooring upto 4 Floor completed, Painting upto 4 Floor completed, Finishing upto 1 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 1
Excavation |  | 4 | 100% | 91.25% |  | 95% |  | Excavation in process |  | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed |  | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process |  | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed |  | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 1 | 25% |  |  |  |  | Plinth in process |  | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3900
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6000/-
Floor Rise Rate Per Sq.ft |  |  |  |  | NA |  |  | 18
Development Charges |  |  |  |  | 100000/- |  |  | 15.6208
Club Charges |  |  |  |  | NA |  |  | 17.8899
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Charges |  |  |  |  | 60000/-
1Year Maintenance Charges |  |  |  |  | 1,00,000/- |  |  | 5328 | 63936
Recommended rate of Parking |  |  |  |  | 150000/- |  |  | 10530 | 126360
Distressed valuation of the Property |  |  |  |  | 3120
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Shop |  | 4 | 845.4046 |  | 1698
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  | Total Saleable Area
Flat |  | 31 | 7415.9654 |  | 10995.3399
Grand Total |  | 35 | 8261.37 |  | 12693.3399
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area | Attached Terrace area | Saleable area | Floor
A Wing
Ground Floor for Commercial, Residential & Parking
1 |  | Shop | 246.7109 | 0 | 490 | Ground Floor for Commercial, Residential & Parking |  | 370.0663
2 |  | Shop | 175.9914 | 0 | 359 |  |  | 1.9861
3 |  | Shop | 175.9914 | 0 | 359
4 |  | Shop | 246.7109 | 0 | 490
1 |  | 1RK | 185.4637 | 0 | 268.9224 |  |  | 16.705
2 |  | 1RK | 185.4637 | 0 | 268.9224
3 |  | 1RK | 194.8284 | 0 | 282.5012
1st & 3rd Floor
101 & 301 |  | 1BHK | 361.4551 | 60.5475 | 584.6574 | 1st & 3rd Floor |  | 4332.4516
102 & 302 |  | 1BHK | 361.4551 | 60.5475 | 584.6574
103 & 303 |  | 1RK | 185.4637 | 0 | 268.9224
104 & 304 |  | 1RK | 185.4637 | 0 | 268.9224
105 & 305 |  | 1RK | 194.8284 | 0 | 282.5012
106 & 306 |  | 1RK | 211.9432 | 0 | 307.3176 | [5 empty] | 5472
107 & 307 |  | 1RK | 211.9432 | 0 | 307.3176 | [5 empty] | 5256
2nd Floor | [10 empty] | 7074
201 |  | 1BHK | 361.4551 | 0 | 524.1099 | 2nd Floor |  | 4242.6214 |  |  | 6426
202 |  | 1BHK | 361.4551 | 0 | 524.1099 | [5 empty] | 6057
203 |  | 1RK | 185.4637 | 0 | 268.9224 |  |  | 3691.7714
204 |  | 1RK | 185.4637 | 0 | 268.9224
205 |  | 1RK | 194.8284 | 0 | 282.5012 |  |  | 3658.7458
206 |  | 1RK | 211.9432 | 0 | 307.3176
207 |  | 1RK | 211.9432 | 0 | 307.3176
4th Floor
401 |  | 1BHK | 361.4551 | 0 | 524.1099 | 4th Floor
402 |  | 1BHK | 361.4551 | 0 | 524.1099
403 |  | 1RK | 185.4637 | 0 | 268.9224
404 |  | 1RK | 185.4637 | 0 | 268.9224
405 |  | 1RK | 194.8284 | 0 | 282.5012
406 |  | 1RK | 211.9432 | 0 | 307.3176
407 |  | 1RK | 211.9432 | 0 | 307.3176
Remarks:
1. Construction work is same as last visit (dtd. 08/02/2025). Lift & finishing work is pending, The Land owner is planning to construct 5th Floor, but not yet received any authority approval. 2. We considered Saleable area as per Builder area sheet for shop & as per our calculation for Flat. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. The project has received first CC on 19/03/2018, But construction work is not yet completed. 9. As checked on RERA portal on dated 18/08/2025, we have observed that above project is kept under abeyance. 8. As per RERA, completion period of project Anant Apartment is expired on 30/12/2023 but still project is under construction. 8. On Site, we meet Mr.Avinash Rai (Builder) - 8237410994/ 9370742362.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Anant Apartment
Google Map :

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.5 | 2.75 | 9.625 | CB | 2.75 | 1 | 2.75 |  |  | 0
|  |  |  | 0 | FB | 2.75 | 1 | 2.75 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.25 | 2.75 | 6.1875 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.75 | 7.5625 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.1 | 1.35 | 2.835 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 1.35 | 1.35 |  |  |  | 0 |  |  | 0
| passage2 | 2.1 | 0.45 | 0.945 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 306.8278 | 28.505 |  |  | 59.202 | 5.5 |  | 0 | 0
|  |  | 366.0298 | 34.005

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Ghodela Homes | 1BHK | 0 | 500 | 3300 | 1650000
housing. | Ghodela Homes | 2BHK | 0 | 600 | 3000 | 1800000
Average |  |  | 0 | 0 | 3150
Valuation Adopted |  |  |  |  | 3150

## Note
24/10/2020. | Dhanashree | NEW APF
1. We have matched Given Costsheet.
2020-12-17 | Pratiksha | Old APF