## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | Golden Mile Builders LLP
Name of the builder company |  |  |  | Golden Mile Builders LLP
Name of the Project |  |  |  | HOH Kalyan
Name of the Project as per RERA |  |  |  | HOH Kalyan Bldg A­Oakwood Bldg B­Bridgewood Bldg C­Greenwood
Provided Contact Details ( Name & Contact No.) |  |  |  | 8928233577
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr.Vinod 8169878066 Mr. Shriniwas 9821470766
Name / No of the Building |  |  |  | Building A, B & C
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700050785
Project location details |  | HOH Kalyan, Survey No.98/3, 98/5, 98/15, 98/16/1, 98/24/ 98/32, 98/33, 98/34/1, 98/34/2, 98/34/3, 98/35/A, 98/35/B, 98/35/C, 98/40, 98/49/1, 98/49/2, 98/50, 99/6/B, 99/8, 99/9, 99/10, near Pardev Complex, Kalyan Bhiwandi Road, Saravali, Gove, Kalyan West, Bhiwandi, Thane - 421311.
Survey No |  | 98/3, 98/5, 98/15, 98/16/1, 98/24/ 98/32, 98/33, 98/34/1, 98/34/2, 98/34/3, 98/35/A, 98/35/B, 98/35/C, 98/40, 98/49/1, 98/49/2, 98/50, 99/6/B, 99/8, 99/9, 99/10
Locality |  | Saravali
Road |  | Kalyan Bhiwandi Road |  | Locality/Village |  | Gove
City |  | Kalyan West |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421311
Nearby Landmark |  | Pardev Complex |  | Distance from city centre: |  | 5.9KM from Kalyan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Maruti Suzuki ARENA
West | NA | NA |  |  | Pardev Complex
North | NA | NA |  |  | Kalyan Bhiwandi Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.251393, 73.098549
Location Link |  | https://goo.gl/maps/aa9KXhH1jMp8ybjh9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 17213.5
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1393
Total FSI availaible for the project |  |  |  | 2.2393
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 38545.85
Total number of Buildings |  |  |  | 3 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mumbai Metropolitan Region Development Authority (MMRDA)
Layout Approval No |  | SROT/BSNA/2501/BP/GOVE-15/CC/202/2023 |  |  | Dated | 2023-02-10
Approved Floor plan No. |  | SROT/BSNA/2501/BP/GOVE-15/CC/202/2023 |  |  | Dated | 2023-02-10
Commencement-CC No Valid Up to: |  | SROT/BSNA/2501/BP/GOVE-15/CC/202/2023 |  |  | Dated | 2023-02-10
Building A = Gr/St + 1st to 25th Floor Building B = Gr/St + 1st to 17th Floor Building C = Gr/St + 1st to 25th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 38545.85
Approved no of units |  |  | Flats - 531
Approved no of Floors |  |  | Building A (Oakwood) = Gr/St + 1st to 25th Floor Building B (Bridgewood) = Gr/St + 1st to 17th Floor Building C (Greenwood) = Gr/St + 1st to 25th Floor
Proposed no of Floors |  |  | Building A (Oakwood) = Gr/St + 1st to 25th Floor
Building B (Bridgewood) = Gr/St + 1st to 28th Floor
Building C (Greenwood) = Gr/St + 1st to 25th Floor
Expected Completion |  |  | As per RERA - 31/01/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Lounge, Cricket Pitch, Badminton Court, Yoga/Meditation Area, Indoor Games, Sewage Treatment Plant, Rain Water Harvesting, Gymnasium
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building A (Oakwood) = Gr/St + 1st to 25th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 7.8 Floor Completed | , RCC upto 15 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 7.8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 25 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 13 Floor, Internal Plaster upto 9.75 Floor, External Plaster upto 7.8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 43.02% |  | 68.42% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 15 | 57.69% |  |  |  |  | Footing in Process | 6.25
Brickwork | Brickwork & Internal Plaster | 13 | 52% |  |  |  |  | Footing Completed | 12.5
Internal Plaster | Brickwork & Internal Plaster | 9.75 | 39% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7.8 | 31.2% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25
Construction details: |  | Building B (Bridgewood) = Gr/St + 1st to 28th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 19.5 Floor, External Plaster upto 19.5 Floor, Flooring upto 8 Floor Completed | , RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 19.5 Floor, External Plaster upto 19.5 Floor, Flooring upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 28 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 27 Slab, Brickwork upto 26 Floor, Internal Plaster upto 19.5 Floor, External Plaster upto 19.5 Floor, Flooring upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 69.25% |  | 85.97% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 27 | 93.1% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 26 | 92.86% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 19.5 | 69.64% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 19.5 | 69.64% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 8 | 28.57% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Construction details: |  | Building C (Greenwood) = Gr/St + 1st to 25th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 21 Floor, External Plaster upto 21 Floor, Flooring upto 10 Floor Completed | , Internal Plaster upto 21 Floor, External Plaster upto 21 Floor, Flooring upto 10 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 25 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 21 Floor, External Plaster upto 21 Floor, Flooring upto 10 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6.25
Excavation |  | 25 | 100% | 76.2% |  | 90.4% |  | Excavation in process | 12.5
Plinth |  | 25 | 100% |  |  |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 26 | 100% |  |  |  |  | Footing in Process | 6.25
Brickwork | Brickwork & Internal Plaster | 25 | 100% |  |  |  |  | Footing Completed | 12.5
Internal Plaster | Brickwork & Internal Plaster | 21 | 84% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 84% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 40% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 25
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7100
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 400000 |  |  | Development 400000 @ Bhargav COst sheet on 26/11/2024.
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 5680
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building A (Oakwood) |  | 198 |  | 108984.6927 |  | 163477.039
Building B (Bridgewood) |  | 135 |  | 88581.2347 |  | 132871.852
Building C (Greenwood) |  | 198 |  | 108984.6927 |  | 163477.039
Total |  | 531 |  | 306550.6201 |  | 459825.9301
Grand Total |  | 531 |  | 306550.6201 |  | 459825.9301
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building A Oakwood | [8 empty] | 10.764
Stilt Floor For Electric & Meter Room, Entrance Lobby & Parking | [7 empty] | Net carpet = carpet + balcony
1st Floor For Residential & Double Enrance Lobby | [8 empty] | 3.072
1 |  | 2 | 641.05 | 0 | 961.575 | 1st Floor For Residential & Double Enrance Lobby |  |  | 54.608 | 2.337 | 56.945 | 0.9375
2 |  | Double Entrance Lobby
3 |  | 1 | 450.4734 | 0 | 675.7101 |  |  |  | 37.0937 | 2.337 | 39.4307 | 2.805
4 |  | 2 | 641.05 | 0 | 961.575 |  |  |  | 2.3563
5 |  | 2 | 639.8929 | 0 | 959.8393
6 |  | 1 | 466.2965 | 0 | 699.4447
7 |  | 1 | 466.2965 | 0 | 699.4447
8 |  | 2 | 639.8929 | 0 | 959.8393
2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
20th Floor (Part Refuge Area)
1 |  | 2 | 641.05 | 0 | 961.575 | 20th Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 20th Floor (Part Refuge Area)
3 |  | 1 | 450.4734 | 0 | 675.7101 | 20th Floor (Part Refuge Area)
4 |  | 2 | 641.05 | 0 | 961.575 | 20th Floor (Part Refuge Area)
5 |  | 2 | 639.8929 | 0 | 959.8393 | 20th Floor (Part Refuge Area)
6 |  | 1 | 466.2965 | 0 | 699.4447 | 20th Floor (Part Refuge Area)
7 |  | 1 | 466.2965 | 0 | 699.4447 | 20th Floor (Part Refuge Area)
8 |  | 2 | 639.8929 | 0 | 959.8393 | 20th Floor (Part Refuge Area)
3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
24th Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 24th Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 24th Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 24th Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 24th Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 24th Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 24th Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 24th Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 24th Floor
25th Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 25th Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 25th Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 25th Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 25th Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 25th Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 25th Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 25th Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 25th Floor
Building B (Bridgewood)
Stilt Floor For Electric & Meter Room, Entrance Lobby & Parking
1st Floor For Residential & Double Enrance Lobby
1 |  | 2 | 641.1577 | 0 | 961.7365 | 1st Floor For Residential & Double Enrance Lobby
2 |  | Double Entrance Lobby |  |  |  | 1st Floor For Residential & Double Enrance Lobby
3 |  | 2 | 671.1623 | 0 | 1006.7435 | 1st Floor For Residential & Double Enrance Lobby
4 |  | 2 | 641.1577 | 0 | 961.7365 | 1st Floor For Residential & Double Enrance Lobby
5 |  | 2 | 641.1577 | 0 | 961.7365 | 1st Floor For Residential & Double Enrance Lobby
6 |  | 2 | 671.5929 | 0 | 1007.3893 | 1st Floor For Residential & Double Enrance Lobby
7 |  | 2 | 671.5929 | 0 | 1007.3893 | 1st Floor For Residential & Double Enrance Lobby
8 |  | 2 | 641.1577 | 0 | 961.7365 | 1st Floor For Residential & Double Enrance Lobby
2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
1 |  | 2 | 641.1577 | 0 | 961.7365 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
2 |  | 2 | 671.1623 | 0 | 1006.7435 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
3 |  | 2 | 671.1623 | 0 | 1006.7435 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
4 |  | 2 | 641.1577 | 0 | 961.7365 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
5 |  | 2 | 641.1577 | 0 | 961.7365 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
6 |  | 2 | 671.5929 | 0 | 1007.3893 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
7 |  | 2 | 671.5929 | 0 | 1007.3893 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
8 |  | 2 | 641.1577 | 0 | 961.7365 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th & 16th Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
1 |  | 2 | 641.1577 | 0 | 961.7365 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
2 |  | 2 | 671.1623 | 0 | 1006.7435 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
3 |  | 2 | 671.1623 | 0 | 1006.7435 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
4 |  | 2 | 641.1577 | 0 | 961.7365 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
5 |  | 2 | 641.1577 | 0 | 961.7365 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
6 |  | 2 | 671.5929 | 0 | 1007.3893 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
7 |  | 2 | 671.5929 | 0 | 1007.3893 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
8 |  | 2 | 641.1577 | 0 | 961.7365 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th & 17th Floor
Building C (Greenwood)
Stilt Floor For Electric & Meter Room, Entrance Lobby & Parking
1st Floor For Residential & Double Enrance Lobby
1 |  | 2 | 641.05 | 0 | 961.575 | 1st Floor For Residential & Double Enrance Lobby
2 |  | Double Entrance Lobby |  |  |  | 1st Floor For Residential & Double Enrance Lobby
3 |  | 1 | 450.4734 | 0 | 675.7101 | 1st Floor For Residential & Double Enrance Lobby
4 |  | 2 | 641.05 | 0 | 961.575 | 1st Floor For Residential & Double Enrance Lobby
5 |  | 2 | 639.8929 | 0 | 959.8393 | 1st Floor For Residential & Double Enrance Lobby
6 |  | 1 | 466.2965 | 0 | 699.4447 | 1st Floor For Residential & Double Enrance Lobby
7 |  | 1 | 466.2965 | 0 | 699.4447 | 1st Floor For Residential & Double Enrance Lobby
8 |  | 2 | 639.8929 | 0 | 959.8393 | 1st Floor For Residential & Double Enrance Lobby
2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 2nd, 4th, 6th, 8th, 10th, 12th, 14th, 16th, 18th & 22nd Floor
20th Floor (Part Refuge Area)
1 |  | 2 | 641.05 | 0 | 961.575 | 20th Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 20th Floor (Part Refuge Area)
3 |  | 1 | 450.4734 | 0 | 675.7101 | 20th Floor (Part Refuge Area)
4 |  | 2 | 641.05 | 0 | 961.575 | 20th Floor (Part Refuge Area)
5 |  | 2 | 639.8929 | 0 | 959.8393 | 20th Floor (Part Refuge Area)
6 |  | 1 | 466.2965 | 0 | 699.4447 | 20th Floor (Part Refuge Area)
7 |  | 1 | 466.2965 | 0 | 699.4447 | 20th Floor (Part Refuge Area)
8 |  | 2 | 639.8929 | 0 | 959.8393 | 20th Floor (Part Refuge Area)
3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th, 17th, 19th, 21st & 23rd Floor
24th Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 24th Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 24th Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 24th Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 24th Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 24th Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 24th Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 24th Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 24th Floor
25th Floor
1 |  | 2 | 641.05 | 0 | 961.575 | 25th Floor
2 |  | 1 | 450.4734 | 0 | 675.7101 | 25th Floor
3 |  | 1 | 450.4734 | 0 | 675.7101 | 25th Floor
4 |  | 2 | 641.05 | 0 | 961.575 | 25th Floor
5 |  | 2 | 639.8929 | 0 | 959.8393 | 25th Floor
6 |  | 1 | 466.2965 | 0 | 699.4447 | 25th Floor
7 |  | 1 | 466.2965 | 0 | 699.4447 | 25th Floor
8 |  | 2 | 639.8929 | 0 | 959.8393 | 25th Floor
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Oakwood, Bridgewood & Greenwood = Construction work is in process at the time of Visit. Internal Visit was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + balcony + Elevation.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 26/11/2024
* | Construction work of Building B Bridgewood goes beyond approved no. of floor. Please provide approved plans & CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | HOH Kalyan
Layout :
Google Map :
Formulas:
Gove = [Gove, row above]
A
B
C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted