## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | M/s.Shreenath Enterrpises
Name of the builder company |  |  |  | M/s.Shreenath Enterrpises
Name of the Project |  |  |  | Parasnath Township
Contact Details ( Name & Contact No.) |  |  |  | 7709011112/7774090078
Name / No of the Building |  |  |  | Building No. 1 (B1 & B2 Type) Building No. 2 (B, A & D Type)
Documents Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | P99000015590
Project location details |  | Parasnath Township, Gut No.392, 393, 394A, 394B, near Raj Mandir Garden, Umroli Station Road, Panchali , Boisar West, Palghar, Palghar.
Gut No |  | 392, 393, 394A, 394B
Road |  | Umroli Station Road |  | Locality/Village |  | Panchali
City |  | Boisar West |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401404
Nearby Landmark |  | Raj Mandir Garden |  | Distance from city centre: |  | 1.5 KM from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Internal Road
North | NA | NA |  |  | Rawat Road
South | NA | NA |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.7641 |  | Longitude |  | 72.7555
Location link |  | https://goo.gl/maps/dLishpKQerKTcbnN8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 18596
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 2.5812e-05
Total FSI availaible for the project |  |  |  | 1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 18596.48
Total number of Buildings |  |  |  | 5 Wings
Approval Detail : Plan approval
Layout Approval No |  | MHASUL/K-1/MJ1/BSP/SR/CR/11/2018 |  |  | Dated | 2019-06-27
Approved Floor plan No. |  | MHASUL/K-1/MJ1/BSP/SR/CR/11/2018 |  |  | Dated | 2019-06-27
Commencement Certificate No. |  | MHASUL/KS.1/T.1/NAP/SR-11/2018 |  |  | Dated | 2019-06-27
Valid Up to: Building No. 1 - B1 & B2 Type = G + 1st to 4th Floor Building No. 2 - B, A & D Type = G + 1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 18596.48
Approved no of units |  |  | Shops - 63, Flats -130
Approved no of Floors |  |  | Building No. 1 (B1 & B2 Type) = G + 1st to 4th Floor Building No. 2 (B, A & D Type) = G + 1st to 4th Floor
Proposed no of Floors |  |  | Building No. 1 (B1 Type) (Wing A) = G + 1st to 4th Floor
Building No. 1 (B2 Type) (Wing B) = G + 1st to 4th Floor
Building No. 2 (B & A Type) (Wing A & B) = G + 1st to 4th Floor
Building No. 2 (D Type) (Wing C) = G + 1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/03/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes
Construction details: |  | Building No. 1 (B1 Type) (Wing A) = G + 1st to 4th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% |  |  |  |  | Plinth in process | 3
Possession |  | 4 | 100% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 1 (B2 Type) (Wing B) = G + 1st to 4th Floor | [5 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 93.75% |  | 95% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 75% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (B & A Type) (Wing A & B) = G + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 3 Floor, External Plaster upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 68.12% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (D Type) (Wing C) = G + 1st to 4th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3.5 Floor, Flooring upto 3 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 3.5 Floor, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 85% |  | 93.12% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3.5 | 87.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3500
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 4500
Society Maintainance Charges |  |  |  |  | 65000
Society Formation Charges |  |  |  |  | 75000
Devlopment Charges |  |  |  |  | 150000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2800
Commercial Area Details : | [8 empty] | rate sheet
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | builder | visitor
Building No.1 | Wing A | 10 |  | 1530.2102 |  | 2900 |  | flat | 4000 | 3000
| Wing B | 15 |  | 2019.0035 |  | 3927.6821 |  | shop
Building No.2 | Wing A | 14 |  | 1855.1754 |  | 3670
| Wing B | 14 |  | 1440.6538 |  | 3040
| Wing C | 10 |  | 637.9823 |  | 1515
Total |  | 63 |  | 7483.0252 |  | 15052.6821
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 | Wing A | 34 |  | 11819.5178 |  | 19225
| Wing B | 24 |  | 8761.896 |  | 14360
Building No.2 | Wing A | 24 |  | 9338.8464 |  | 15355.2545
| Wing B | 24 |  | 9338.8464 |  | 15355.2545
| Wing C | 24 |  | 8439.8371 |  | 13709.1141
Total |  | 130 |  | 47698.9438 |  | 78004.6232
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable Area | Floor
Building No. 1
Type - B1 (Wing - A)
Ground Floor for Commercial & Parking
1 |  | Shop | 124.0013 | 0 | 255 | Ground Floor for Commercial & Parking |  | 255 | 2.0564
2 |  | Shop | 129.5986 | 0 | 245 |  |  | 245 | 1.8905
3 |  | Shop | 165.7656 | 0 | 310 |  |  | 310 | 1.8701
4 |  | Shop | 165.7656 | 0 | 310 |  |  | 310 | 1.8701
5 |  | Shop | 156.7238 | 0 | 290 |  |  | 290 | 1.8504
6 |  | Shop | 156.7238 | 0 | 290 |  |  | 290 | 1.8504
7 |  | Shop | 165.7656 | 0 | 315 |  |  | 315 | 1.9003
8 |  | Shop | 165.7656 | 0 | 315 |  |  | 315 | 1.9003
9 |  | Shop | 129.5986 | 0 | 245 |  |  | 245 | 1.8905
10 |  | Shop | 170.5018 | 0 | 325 |  |  | 325 | 1.9061
Building No. 1 | [8 empty] | #DIV/0!
Type - B2 (Wing - B) | [8 empty] | #DIV/0!
Ground Floor for Commercial & Parking | [8 empty] | #DIV/0!
1 |  | Shop | 170.5018 | 0 | 325 | Ground Floor for Commercial & Parking |  | 325 | 1.9061
2 |  | Shop | 129.5986 | 0 | 245 |  |  | 245 | 1.8905
3 |  | Shop | 165.7656 | 0 | 310 |  |  | 310 | 1.8701
4 |  | Shop | 145.7446 | 0 | 285 |  |  | 285 | 1.9555
5 |  | Shop | 101.8274 | 0 | 200 |  |  | 200 | 1.9641 | 4537.5
6 |  | Shop | 165.1198 | 0 | 320 |  |  | 320 | 1.938
7 |  | Shop | 73.841 | 0 | 147.6821 |  |  | 230 | 2
8 |  | Shop | 100.1052 | 0 | 215 |  |  | 215 | 2.1477
9 |  | Shop | 101.8274 | 0 | 200 |  |  | 200 | 1.9641
10 |  | Shop | 145.7446 | 0 | 285 |  |  | 285 | 1.9555
11 |  | Shop | 165.7656 | 0 | 315 |  |  | 315 | 1.9003
12 |  | Shop | 129.5986 | 0 | 245 |  |  | 245 | 1.8905
13 |  | Shop | 170.5018 | 0 | 330 |  |  | 330 | 1.9355
14 |  | Shop | 146.498 | 0 | 285 |  |  | 285 | 1.9454
15 |  | Shop | 106.5636 | 0 | 220 |  |  | 220 | 2.0645
Building No. 2 | [8 empty] | #DIV/0!
Type - B (Wing - A) | [8 empty] | #DIV/0!
Ground Floor for Commercial & Parking | [8 empty] | #DIV/0!
1 |  | Shop | 124.0013 | 0 | 255 | Ground Floor for Commercial & Parking |  | 255 | 2.0564
2 |  | Shop | 127.1228 | 0 | 240 |  |  | 240 | 1.8879
3 |  | Shop | 165.7656 | 0 | 310 |  |  | 310 | 1.8701
4 |  | Shop | 145.7446 | 0 | 285 |  |  | 285 | 1.9555
5 |  | Shop | 101.8274 | 0 | 200 |  |  | 200 | 1.9641
6 |  | Shop | 151.5571 | 0 | 300 |  |  | 300 | 1.9795
7 |  | Shop | 77.5008 | 0 | 220 |  |  | 220 | 2.8387
8 |  | Shop | 118.0811 | 0 | 245 |  |  | 245 | 2.0748
9 |  | Shop | 105.2719 | 0 | 205 |  |  | 205 | 1.9473
10 |  | Shop | 150.8036 | 0 | 290 |  |  | 290 | 1.923
11 |  | Shop | 171.6858 | 0 | 320 |  |  | 320 | 1.8639
12 |  | Shop | 127.5534 | 0 | 245 |  |  | 245 | 1.9208
13 |  | Shop | 135.8417 | 0 | 260 |  |  | 260 | 1.914
14 |  | Shop | 152.4182 | 0 | 295 |  |  | 295 | 1.9355
Building No. 2 | [8 empty] | #DIV/0!
Type - A (Wing - B) | [8 empty] | #DIV/0!
Ground Floor for Commercial & Parking | [8 empty] | #DIV/0!
1 |  | Shop | 152.4182 | 0 | 295 | Ground Floor for Commercial & Parking |  | 295 | 1.9355
2 |  | Shop | 135.8417 | 0 | 260 |  |  | 260 | 1.914
3 |  | Shop | 127.5534 | 0 | 245 |  |  | 245 | 1.9208
4 |  | Shop | 171.6858 | 0 | 320 |  |  | 320 | 1.8639
5 |  | Shop | 150.8036 | 0 | 290 |  |  | 290 | 1.923 | 4475.8621
6 |  | Shop | 105.2719 | 0 | 205 |  |  | 205 | 1.9473
7 |  | Shop | 137.6716 | 0 | 275 |  |  | 275 | 1.9975
8 |  | Shop | 77.5008 | 0 | 230 |  |  | 230 | 2.9677
9 |  | Shop | 63.7229 | 0 | 160 |  |  | 160 | 2.5109
10 |  | Shop | 63.6152 | 0 | 145 |  |  | 145 | 2.2793
11 |  | Shop | 63.6152 | 0 | 155 |  |  | 155 | 2.4365
12 |  | Shop | 63.6152 | 0 | 155 |  |  | 155 | 2.4365
13 |  | Shop | 63.6152 | 0 | 145 |  |  | 145 | 2.2793
14 |  | Shop | 63.7229 | 0 | 160 |  |  | 160 | 2.5109
Building No. 2 | [8 empty] | #DIV/0!
Type - D (Wing - C) | [8 empty] | #DIV/0!
Ground Floor for Commercial & Parking | [8 empty] | #DIV/0!
1 |  | Shop | 63.6152 | 0 | 155 | Ground Floor for Commercial & Parking |  |  | 2.4365
2 |  | Shop | 63.6152 | 0 | 145 |  |  |  | 2.2793
3 |  | Shop | 63.6152 | 0 | 155 |  |  |  | 2.4365
4 |  | Shop | 63.6152 | 0 | 155 |  |  |  | 2.4365
5 |  | Shop | 64.584 | 0 | 145 |  |  |  | 2.2451
6 |  | Shop | 63.6152 | 0 | 155 |  |  |  | 2.4365
7 |  | Shop | 64.4764 | 0 | 150 |  |  |  | 2.3264
8 |  | Shop | 63.6152 | 0 | 155 |  |  |  | 2.4365
9 |  | Shop | 63.6152 | 0 | 145 |  |  |  | 2.2793
10 |  | Shop | 63.6152 | 0 | 155 |  |  |  | 2.4365
#DIV/0!
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable Area | Floor
Building No. 1
Type - B1 (Wing - A)
Ground Floor for Residential
1 |  | 1BHK | 370.6045 | 0 | 550 | Ground Floor for Residential |  | 34.3875 | 550 | 1.4841 |  | #REF! | #REF! | #NUM!
2 |  | 2BHK | 458.4388 | 0 | 675 |  |  |  | 675 | 1.4724 |  | #REF! | #REF! | #NUM!
1st to 4th Floor for Residential | [9 empty] | #DIV/0!
1 |  | 1BHK | 370.6045 | 0 | 600 | 1st to 4th Floor for Residential |  | 34.3875 | 600 | 1.619 |  | 101 to 401 | 101 | 401
2 |  | 1BHK | 370.6045 | 0 | 600 |  |  |  | 725 | 1.619 |  | 102 to 402 | 102 | 402
3 |  | 1RK | 218.0786 | 0 | 385 |  |  |  | 457 | 1.7654 |  | 103 to 403 | 103 | 403
4 |  | 1RK | 218.0786 | 0 | 385 |  |  |  | 457 | 1.7654 |  | 104 to 404 | 104 | 404
5 |  | 1BHK | 370.6045 | 0 | 600 |  |  |  | 725 | 1.619 |  | 105 to 405 | 105 | 405
6 |  | 1BHK | 370.6045 | 0 | 600 |  |  |  | 600 | 1.619 |  | 106 to 406 | 106 | 406
7 |  | 2BHK | 458.4388 | 0 | 730 |  |  |  | 730 | 1.5924 |  | 107 to 407 | 107 | 407
8 |  | 1BHK | 370.6045 | 0 | 600 |  |  |  | 600 | 1.619 |  | 108 to 408 | 108 | 408
Building No. 1 | [9 empty] | #DIV/0!
Type - B2 (Wing - B) | [9 empty] | #DIV/0!
1st to 4th Floor for Residential | [9 empty] | #DIV/0!
1 |  | 1BHK | 362.6392 | 0 | 600 | 1st to 4th Floor for Residential |  | 34.3875 |  | 1.6545 |  | 101 to 401 | 101 | 401
2 |  | 1BHK | 369.0976 | 0 | 600 |  |  | 4000 |  | 1.6256 |  | 102 to 402 | 102 | 402
3 |  | 1BHK | 369.0976 | 0 | 600 |  |  |  |  | 1.6256 |  | 103 to 403 | 103 | 403
4 |  | 1BHK | 369.0976 | 0 | 600 |  |  |  |  | 1.6256 |  | 104 to 404 | 104 | 404
5 |  | 1BHK | 369.0976 | 0 | 600 |  |  |  |  | 1.6256 |  | 105 to 405 | 105 | 405
6 |  | 1BHK | 351.4446 | 0 | 590 |  |  |  |  | 1.6788 |  | 106 to 406 | 106 | 406
Building No. 2 | [9 empty] | #DIV/0!
Type - B (Wing - A) | [9 empty] | #DIV/0!
1st to 4th Floor for Residential | [9 empty] | #DIV/0!
1 |  | 1BHK | 362.6392 | 0 | 675 | 1st to 4th Floor for Residential |  | 34.3875 | 675 | 1.8614 |  | 101 to 401 | 101 | 401
2 |  | 1BHK | 369.0976 | 0 | 590.5561 |  |  |  | 725 | 1.6 |  | 102 to 402 | 102 | 402
3 |  | 1BHK | 369.0976 | 0 | 600 |  |  |  | 600 | 1.6256 | 3537.1849 | 103 to 403 | 103 | 403
4 |  | 2BHK | 441.2164 | 0 | 705 |  |  | 2116.3121 | 705 | 1.5979 |  | 104 to 404 | 104 | 404
5 |  | 2BHK | 441.2164 | 0 | 705.9462 |  |  |  | 855 | 1.6 |  | 105 to 405 | 105 | 405
6 |  | 1BHK | 351.4446 | 0 | 562.3114 |  |  | 356.3422 | 771 | 1.6 |  | 106 to 406 | 106 | 406
Building No. 2 | [9 empty] | #DIV/0!
Type - A (Wing - B) | [9 empty] | #DIV/0!
1st to 4th Floor for Residential | [9 empty] | #DIV/0!
1 |  | 1BHK | 351.4446 | 0 | 562.3114 | 1st to 4th Floor for Residential |  | 34.3875 | 2119.822 | 1.6 |  | 101 to 401 | 101 | 401
2 |  | 2BHK | 441.2164 | 0 | 705.9462 |  |  |  |  | 1.6 |  | 102 to 402 | 102 | 402
3 |  | 2BHK | 441.2164 | 0 | 705 |  |  |  |  | 1.5979 |  | 103 to 403 | 103 | 403
4 |  | 1BHK | 369.0976 | 0 | 600 |  |  |  |  | 1.6256 |  | 104 to 404 | 104 | 404
5 |  | 1BHK | 369.0976 | 0 | 590.5561 |  |  |  |  | 1.6 |  | 105 to 405 | 105 | 405
6 |  | 1BHK | 362.6392 | 0 | 675 |  |  |  |  | 1.8614 |  | 106 to 406 | 106 | 406
Building No. 2 | [9 empty] | #DIV/0!
Type - D (Wing - C) | [9 empty] | #DIV/0!
1st to 4th Floor for Residential | [9 empty] | #DIV/0!
1 |  | 1BHK | 360.2711 | 0 | 580 | 1st to 4th Floor for Residential |  | 34.3875 |  | 1.6099 |  | 101 to 401 | 101 | 401
2 |  | 1BHK | 347.5696 | 0 | 580 |  |  |  |  | 1.6687 |  | 102 to 402 | 102 | 402
3 |  | 1BHK | 347.5696 | 0 | 556.1113 |  |  | 352.1443 |  | 1.6 |  | 103 to 403 | 103 | 403
4 |  | 1BHK | 359.41 | 0 | 575.0559 |  |  |  |  | 1.6 |  | 104 to 404 | 104 | 404
5 |  | 1BHK | 347.5696 | 0 | 556.1113 |  |  |  |  | 1.6 |  | 105 to 405 | 105 | 405
6 |  | 1BHK | 347.5696 | 0 | 580 |  |  | 2055.1724 |  | 1.6687 |  | 106 to 406 | 106 | 406
2nd Floor | [9 empty] | #DIV/0!
201 |  |  |  | 0 | #REF! | 2nd Floor |  |  |  | #REF!
202 |  |  |  | 0 | #REF! | 2nd Floor |  |  |  | #REF!
203 |  |  |  | 0 | #REF! | 2nd Floor |  |  |  | #REF!
204 |  |  |  | 0 | #REF! | 2nd Floor |  |  |  | #REF!
205 |  |  |  | 0 | #REF! | 2nd Floor |  |  |  | #REF!
206 |  |  |  | 0 | #REF! | 2nd Floor |  |  |  | #REF!
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor | [9 empty] | #DIV/0!
301,..,1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | #REF! |  | 301,..,1501 | 301 | 1501
302,..,1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | #REF! |  | 302,..,1502 | 302 | 1502
303,..,1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | #REF! |  | 303,..,1503 | 303 | 1503
304,..,1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | #REF! |  | 304,..,1504 | 304 | 1504
305,..,1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | #REF! |  | 305,..,1505 | 305 | 1505
306,..,1506 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  |  | #REF! |  | 306,..,1506 | 306 | 1506
1st to 4th Floor | [9 empty] | #DIV/0!
101 to 401 |  |  |  | 0 | #REF! | 1st to 4th Floor |  |  |  | #REF! |  | 101 to 401 | 101 | 401
102 to 402 |  |  |  | 0 | #REF! | 1st to 4th Floor |  |  |  | #REF! |  | 102 to 402 | 102 | 402
103 to 403 |  |  |  | 0 | #REF! | 1st to 4th Floor |  |  |  | #REF! |  | 103 to 403 | 103 | 403
104 to 404 |  |  |  | 0 | #REF! | 1st to 4th Floor |  |  |  | #REF! |  | 104 to 404 | 104 | 404
105 to 405 |  |  |  | 0 | #REF! | 1st to 4th Floor |  |  |  | #REF! |  | 105 to 405 | 105 | 405
106 to 406 |  |  |  | 0 | #REF! | 1st to 4th Floor |  |  |  | #REF! |  | 106 to 406 | 106 | 406
2nd & 5th Floor | [9 empty] | #DIV/0!
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  |  | #REF! |  | 201 & 501 | 201 | 501
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  |  | #REF! |  | 202 & 502 | 202 | 502
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  |  | #REF! |  | 203 & 503 | 203 | 503
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  |  | #REF! |  | 204 & 504 | 204 | 504
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  |  | #REF! |  | 205 & 505 | 205 | 505
206 & 506 |  |  |  | 0 | #REF! | 2nd & 5th Floor |  |  |  | #REF! |  | 206 & 506 | 206 | 506
Remarks: | [9 empty] | #DIV/0!
1 | Building No.01 (Wing A) = All work completed. Please provide OC. Building No.01 (Wing B) = Finishing Work & lift work is pending (Slow Speed). Some flats are occupied by tenants but still lift & finishing work is pending. Work is same as last visit (12/08/2024). Building No.02 Wing A & B = Construction work is same as last visit (30/11/2024). Building No.02 Wing C = Construction work is in process at the time of visit.
2 | We considered Saleable area of Flat as per Builder area Sheet.
3 | We considered Saleable area of Commercial as per Builder area Sheet.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area.
6 | We have considered rate by verifying it from market inquire.
7 | Car parking is subjected to authentic documentation.
8 | On Site, we meet Mr.Shahid (Supervisor) - 9049054882.
8 | As per Approved plan |  |  | As per Sale plan
| Building No. 1 (Wing A) |  |  | Building No. 2 (Wing A)
| Building No. 1 (Wing B) |  |  | Building No. 2 (Wing B)
| Building No. 2 (Wing A) |  |  | Building No. 3 (Wing A)
| Building No. 2 (Wing B) |  |  | Building No. 3 (Wing B)
| Building No. 2 (Wing C) |  |  | Building No. 3 (Wing C)
9 | The project has received first CC on 27/06/2019, But construction work is not yet completed.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Parasnath Township
Google Map :
Layout Plan :
Formulas:
Panchali = [Panchali, row above]
Approved layout plan
Bldg No. 1
Bldg No. 2
Sale plan
Sale plan
Building No.2
Wing A & B
Building No.2
Wing C
Building No.1 Wing B
Building No.2 Wing A
Building No.2 Wing B
Building No.2 Wing C
Building No.2 Wing C
Bldg No. 2C
Bldg No. 2B
Bldg No. 2A
Bldg No. 2B
Bldg No. 2C
Bldg No. 2C
Bldg No. 1A
Bldg No. 1B
Bldg No. 1A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted