## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | M/s.Construxus Infra LLP
Name of the builder company |  |  |  | M/s.Construxus Infra LLP
Name of the Project |  |  |  | Planet 6
Contact Details ( Name & Contact No.) |  |  |  | Mr. Ratan Choudhary - 8169136148
Site Meet Person Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | A to F Wing
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000028999
Project location details |  | Planet 6, Plot No.K-1-147, K-2-146 & Sector No.3, near TES Calista Apartments, JNPT Road, Pushpak, Dapoli, Panvel, Raigad - 410206.
Plot No |  | K-1-147, K-2-146 & Sector No.3
Road |  | JNPT Road |  | Village |  | Pushpak
City |  | Dapoli |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | TES Calista Apartments |  | Distance from city centre: |  | 6.5Km from Panvel Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | JNPT Road
North | NA | NA |  |  | Open Plot
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 18.9718573,73.0730093
Location Link |  | https://goo.gl/maps/1PQGHFGeUYwQwGEn6?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 8557.8
Permissible FSI |  |  |  | 2
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 2
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 17115.6
Total number of Buildings |  |  |  | 06 Wings
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-17808/TPO(NM & K)/2021/8342 |  |  | Dated | 17/03/2021.
Approved Floor plan No. |  | CIDCO/BP-17808/TPO(NM & K)/2021/8342 |  |  | Dated | 17/03/2021.
Commencement Certificate No. |  | CIDCO/BP-17808/TPO(NM & K)/2021/8342 |  |  | Dated | 17/03/2021.
Valid Up to: A to F Wing = Gr/St + 1st to 11st Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 17115.6
Approved no of units |  |  | Flats - 348, Shops - 26, Offices - 26
Approved no of Floors |  |  | A to F Wing = Gr/St + 1st to 11st Floor
Proposed no of Floors |  |  | A Wing = Gr/St + 1st to 11st Floor
B to D Wing = Gr/St + 1st to 11st Floor
E & F Wing = Gr/St + 1st to 11st Floor
B Wing = B1 to B4 + G + 20th Floor
C Wing = B1 to B4 + G + 20th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | A & F Wing = Gr/St + 1st to 11st Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 6 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 6 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 2.75
Excavation |  | 11 | 100% | 69.39% |  | 85.68% |  | Excavation in process |  | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed |  | 11
RCC |  | 11 | 91.67% |  |  |  |  | Footing in Process |  | 2.75
Brickwork | Brickwork & Internal Plaster | 9 | 81.82% |  |  |  |  | Footing Completed |  | 5.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 63.64% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 6 | 54.55% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 11
Construction details: |  | E Wing = Gr/St + 1st to 11st Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 5 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 5 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 2.75
Excavation |  | 11 | 100% | 68.48% |  | 85.23% |  | Excavation in process |  | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed |  | 11
RCC |  | 11 | 91.67% |  |  |  |  | Footing in Process |  | 2.75
Brickwork | Brickwork & Internal Plaster | 9 | 81.82% |  |  |  |  | Footing Completed |  | 5.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 63.64% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 5 | 45.45% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 11
Construction details: |  | B Wing = Gr/St + 1st to 11st Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 8 Floor completed, Internal Plaster upto 8 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 5 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 8 Floor completed, Internal Plaster upto 8 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 5 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 2.75
Excavation |  | 11 | 100% | 68.48% |  | 85.23% |  | Excavation in process |  | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed |  | 11
RCC |  | 11 | 91.67% |  |  |  |  | Footing in Process |  | 2.75
Brickwork | Brickwork & Internal Plaster | 8 | 72.73% |  |  |  |  | Footing Completed |  | 5.5
Internal Plaster | Brickwork & Internal Plaster | 8 | 72.73% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 5 | 45.45% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 11
Construction details: |  | D Wing = Gr/St + 1st to 11st Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 4 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 7 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 4 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 2.75
Excavation |  | 11 | 100% | 66.21% |  | 83.86% |  | Excavation in process |  | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed |  | 11
RCC |  | 11 | 91.67% |  |  |  |  | Footing in Process |  | 2.75
Brickwork | Brickwork & Internal Plaster | 7 | 63.64% |  |  |  |  | Footing Completed |  | 5.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 63.64% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 36.36% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 11
Construction details: |  | C Wing = Gr/St + 1st to 11st Floor | [5 empty] | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 4 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 11 Slab completed, Brickwork upto 9 Floor completed, Internal Plaster upto 7 Floor completed, External Plaster upto 7 Floor completed, Flooring upto 4 Floor completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process |  | 2.75
Excavation |  | 11 | 100% | 67.58% |  | 84.77% |  | Excavation in process |  | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed |  | 11
RCC (Including podiums) |  | 11 | 91.67% |  |  |  |  | Footing in Process |  | 2.75
Brickwork | Brickwork & Internal Plaster | 9 | 81.82% |  |  |  |  | Footing Completed |  | 5.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 63.64% |  |  |  |  | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 63.64% |  |  |  |  | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 4 | 36.36% |  |  |  |  | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process |  | 8.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed |  | 11
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 6300
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) |  |  |  |  | 9700/- |  |  | 8500 to 9700 | Smith | verbal | 2023-06-17 | high side
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft (From 3rd Floor) |  |  |  |  | 40/- from 3rd Floor
Development Charges |  |  |  |  | 350000/-
Club Charges |  |  |  |  | 1,50,000/-
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | 2,00,000/-
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 3,00,000/-
Distressed valuation of the Property |  |  |  |  | 5040
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shop |  | 26 |  | 14322.7076 |  | 22916.3321
Office |  | 26 |  | 12353.1431 |  | 19765.029
Total |  | 52 |  | 26675.8507 |  | 42681.3611 |  |  | 214693.7172
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 65 |  | 32141.1533 |  | 48211.73
B Wing |  | 50 |  | 34198.5627 |  | 51573.4886
C Wing |  | 71 |  | 39242.2179 |  | 59556.3939
D Wing |  | 43 |  | 29592.1735 |  | 44713.0478
E Wing |  | 54 |  | 20703.2838 |  | 30469.6333
F Wing |  | 65 |  | 32140.4752 |  | 48210.7128
Total |  | 348 |  | 188017.8665 |  | 282735.0064
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
A, B, C, D, E, F Wings
Ground Floor
1 |  | Shop | 489.1269 | 0 | 782.6031 | Ground Floor
2 |  | Shop | 719.5411 | 0 | 1151.2658
3 |  | Shop | 482.7654 | 0 | 772.4246
4 |  | Shop | 482.7654 | 0 | 772.4246
5 |  | Shop | 617.8536 | 0 | 988.5658
6 |  | Shop | 921.3446 | 0 | 1474.1513
7 |  | Shop | 616.3359 | 0 | 986.1374
8 |  | Shop | 616.4005 | 0 | 986.2407
9 |  | Shop | 545.7348 | 0 | 873.1757
10 |  | Shop | 545.7348 | 0 | 873.1757
11 |  | Shop | 597.951 | 0 | 956.7215
12 |  | Shop | 705.7417 | 0 | 1129.1867
13 |  | Shop | 379.1081 | 0 | 606.5729
14 |  | Shop | 379.1081 | 0 | 606.5729
15 |  | Shop | 600.9541 | 0 | 961.5266
16 |  | Shop | 527.027 | 0 | 843.2431
17 |  | Shop | 482.7654 | 0 | 772.4246
18 |  | Shop | 482.7654 | 0 | 772.4246
19 |  | Shop | 543.1191 | 0 | 868.9906
20 |  | Shop | 545.315 | 0 | 872.504
21 |  | Shop | 801.4874 | 0 | 1282.3799
22 |  | Shop | 647.0779 | 0 | 1035.3246
23 |  | Shop | 484.5953 | 0 | 775.3524
24 |  | Shop | 456.9318 | 0 | 731.0909
25 |  | Shop | 330.9607 | 0 | 529.5371
26 |  | Shop | 320.1967 | 0 | 512.3147
1st Floor for Parking
2nd Floor
201 |  | Office | 519.2877 | 0 | 830.8602 | 2nd Floor
202 |  | Office | 572.6448 | 0 | 916.2317
203 |  | Office | 429.4836 | 0 | 687.1738
204 |  | Office | 429.4728 | 0 | 687.1565
205 |  | Office | 572.6448 | 0 | 916.2317
206 |  | Office | 708.6479 | 0 | 1133.8367
207 |  | Office | 483.1744 | 0 | 773.0791
208 |  | Office | 483.1744 | 0 | 773.0791
209 |  | Office | 429.4836 | 0 | 687.1738
210 |  | Office | 429.4836 | 0 | 687.1738
211 |  | Office | 468.8583 | 0 | 750.1733
212 |  | Office | 468.8583 | 0 | 750.1733
213 |  | Office | 377.8164 | 0 | 604.5062
214 |  | Office | 398.4833 | 0 | 637.5732
215 |  | Office | 468.8583 | 0 | 750.1733
216 |  | Office | 468.8583 | 0 | 750.1733
217 |  | Office | 429.4836 | 0 | 687.1738
218 |  | Office | 429.4836 | 0 | 687.1738
219 |  | Office | 483.1744 | 0 | 773.0791
220 |  | Office | 483.1744 | 0 | 773.0791
221 |  | Office | 708.6479 | 0 | 1133.8367
222 |  | Office | 572.6448 | 0 | 916.2317
223 |  | Office | 429.4836 | 0 | 687.1738
224 |  | Office | 429.4836 | 0 | 687.1738
225 |  | Office | 339.5719 | 0 | 543.3151
226 |  | Office | 338.7646 | 0 | 542.0234
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
A Wing
3rd Floor
301 |  | 1BHK | 390.195 | 0 | 585.2925 | 3rd Floor
302 |  | 2BHK | 583.1935 | 0 | 874.7903
303 |  | 2BHK | 594.1728 | 0 | 891.2592
304 |  | 2BHK | 594.1728 | 0 | 891.2592
305 |  | 2BHK | 583.1935 | 0 | 874.7903
4th to 10th Floor
401 to 1001 |  | 1BHK | 390.195 | 0 | 585.2925 | 4th to 10th Floor | [6 empty] | 401 to 1001 | 401 | 1001
402 to 1002 |  | 2BHK | 583.1935 | 0 | 874.7903 | [7 empty] | 402 to 1002 | 402 | 1002
403 to 1003 |  | 2BHK | 594.1728 | 0 | 891.2592 | [7 empty] | 403 to 1003 | 403 | 1003
404 to 1004 |  | 2BHK | 594.1728 | 0 | 891.2592 | [7 empty] | 404 to 1004 | 404 | 1004
405 to 1005 |  | 2BHK | 583.1935 | 0 | 874.7903 | [7 empty] | 405 to 1005 | 405 | 1005
406 to 1006 |  | 1BHK | 372.7143 | 0 | 559.0714 | [7 empty] | 406 to 1006 | 406 | 1006
407 to 1007 |  | 1BHK | 372.7143 | 0 | 559.0714 | [7 empty] | 407 to 1007 | 407 | 1007
408 to 1008 |  | 1BHK | 372.7143 | 0 | 559.0714 | [7 empty] | 408 to 1008 | 408 | 1008
11th Floor
1101 |  | Terrace Floor |  |  |  | 11th Floor
1102 |  | 2BHK | 583.1935 | 0 | 874.7903
1103 |  | 2BHK | 594.1728 | 0 | 891.2592
1104 |  | 2BHK | 594.1728 | 0 | 891.2592
1105 |  | 2BHK | 583.1935 | 0 | 874.7903
B Wing
3rd Floor
301 |  | 3BHK | 806.2236 | 273.3303 | 1346.0005 | 3rd Floor
302 |  | 3BHK | 801.0784 | 163.8604 | 1283.5478
303 |  | 2BHK | 572.8601 | 57.0492 | 916.3393
304 |  | 2BHK | 583.2043 | 0 | 874.8064
4th to 10th Floor
401 to 1001 |  | 3BHK | 873.7139 | 0 | 1310.5708 | 4th to 10th Floor | [6 empty] | 401 to 1001 | 401 | 1001
402 to 1002 |  | 3BHK | 855.9748 | 0 | 1283.9622 | [7 empty] | 402 to 1002 | 402 | 1002
403 to 1003 |  | 2BHK | 589.9748 | 0 | 884.9623 | [7 empty] | 403 to 1003 | 403 | 1003
404 to 1004 |  | 2BHK | 583.2043 | 0 | 874.8064 | [7 empty] | 404 to 1004 | 404 | 1004
405 to 1005 |  | 2BHK | 583.2043 | 0 | 874.8064 | [7 empty] | 405 to 1005 | 405 | 1005
406 to 1006 |  | 2BHK | 589.9748 | 0 | 884.9623 | [7 empty] | 406 to 1006 | 406 | 1006
11th Floor
1101 |  | 3BHK | 873.7139 | 0 | 1310.5708 | 11th Floor
1102 |  | 3BHK | 855.9748 | 0 | 1283.9622
1103 |  | 2BHK | 589.9748 | 0 | 884.9623
1104 |  | 2BHK | 583.2043 | 0 | 874.8064
C Wing
3rd Floor
301 |  | 2BHK | 538.1462 | 273.0612 | 943.7498 | 3rd Floor
302 |  | 2BHK | 538.1354 | 280.6498 | 947.528
303 |  | 2BHK | 564.8409 | 278.7123 | 986.6175
304 |  | 2BHK | 538.1354 | 280.6498 | 947.528
305 |  | 2BHK | 538.1462 | 273.0612 | 943.7498
4th to 7th, 9th, 10th Floor
401,..,1001 |  | 2BHK | 599.8239 | 0 | 899.7359 | 4th to 7th, 9th, 10th Floor | [6 empty] | 401,..,1001 | 401 | 1001
402,..,1002 |  | 2BHK | 599.8131 | 0 | 899.7197 | [7 empty] | 402,..,1002 | 402 | 1002
403,..,1003 |  | 2BHK | 620.0602 | 0 | 930.0903 | [7 empty] | 403,..,1003 | 403 | 1003
404,..,1004 |  | 2BHK | 599.8131 | 0 | 899.7197 | [7 empty] | 404,..,1004 | 404 | 1004
405,..,1005 |  | 2BHK | 599.8239 | 0 | 899.7359 | [7 empty] | 405,..,1005 | 405 | 1005
406,..,1006 |  | 2BHK | 575.9924 | 0 | 863.9886 | [7 empty] | 406,..,1006 | 406 | 1006
407,..,1007 |  | 1BHK | 396.169 | 0 | 594.2535 | [7 empty] | 407,..,1007 | 407 | 1007
408,..,1008 |  | 1BHK | 396.169 | 0 | 594.2535 | [7 empty] | 408,..,1008 | 408 | 1008
409,..,1009 |  | 2BHK | 575.9924 | 0 | 863.9886 | [7 empty] | 409,..,1009 | 409 | 1009
8th Floor
801 |  | 2BHK | 599.8239 | 0 | 899.7359 | 8th Floor
802 |  | 2BHK | 599.8131 | 0 | 899.7197
803 |  | Refuge Area
804 |  | 2BHK | 599.8131 | 0 | 899.7197
805 |  | 2BHK | 599.8239 | 0 | 899.7359
806 |  | 2BHK | 575.9924 | 0 | 863.9886
807 |  | 1BHK | 396.169 | 0 | 594.2535
808 |  | 1BHK | 396.169 | 0 | 594.2535
809 |  | 2BHK | 575.9924 | 0 | 863.9886
11th Floor
1101 |  | 2BHK | 599.8239 | 0 | 899.7359 | 11th Floor
1102 |  | 2BHK | 599.8131 | 0 | 899.7197
1103 |  | Terrace Floor
1104 |  | 2BHK | 599.8131 | 0 | 899.7197
1105 |  | 2BHK | 599.8239 | 0 | 899.7359
D Wing
3rd Floor
301 |  | 3BHK | 806.2021 | 280.9189 | 1349.7625 | 3rd Floor
302 |  | 3BHK | 790.8634 | 524.1853 | 1317.3414
303 |  | 2BHK | 497.1353 | 106.5636 | 798.9848
304 |  | 2BHK | 582.8814 |  | 874.322
4th to 10th Floor
401 to 1001 |  | 3BHK | 873.6924 | 0 | 1310.5385 | 4th to 10th Floor | [6 empty] | 401 to 1001 | 401 | 1001
402 to 1002 |  | 3BHK | 873.5309 | 0 | 1310.2963 | [7 empty] | 402 to 1002 | 402 | 1002
403 to 1003 |  | 2BHK | 524.2606 | 0 | 786.3909 | [7 empty] | 403 to 1003 | 403 | 1003
404 to 1004 |  | 2BHK | 582.8814 | 0 | 874.322 | [7 empty] | 404 to 1004 | 404 | 1004
405 to 1005 |  | 2BHK | 582.8814 | 0 | 874.322 | [7 empty] | 405 to 1005 | 405 | 1005
11th Floor
1101 |  | 3BHK | 873.6924 | 0 | 1310.5385 | 11th Floor
1102 |  | 3BHK | 873.5309 | 0 | 1310.2963
1103 |  | 2BHK | 524.2606 | 0 | 786.3909
1104 |  | 2BHK | 582.8814 | 0 | 874.322
E Wing
3rd Floor
301 |  | Double Height |  |  |  | 3rd Floor
302 |  | 1BHK | 390.195 | 0 | 585.2925
303 |  | 1BHK | 390.195 | 0 | 585.2925
304 |  | 1BHK | 390.195 | 0 | 585.2925
305 |  | 1BHK | 390.195 | 0 | 585.2925
4th to 7th, 9th, 10th Floor
401,..,1001 |  | 1BHK | 372.7143 | 0 | 559.0714 | 4th to 7th, 9th, 10th Floor | [6 empty] | 401,..,1001 | 401 | 1001
402,..,1002 |  | 1BHK | 390.195 | 0 | 585.2925 | [7 empty] | 402,..,1002 | 402 | 1002
403,..,1003 |  | 1BHK | 390.195 | 0 | 585.2925 | [7 empty] | 403,..,1003 | 403 | 1003
404,..,1004 |  | 1BHK | 390.195 | 0 | 585.2925 | [7 empty] | 404,..,1004 | 404 | 1004
405,..,1005 |  | 1BHK | 390.195 | 0 | 585.2925 | [7 empty] | 405,..,1005 | 405 | 1005
406,..,1006 |  | 1BHK | 372.7035 | 0 | 559.0552 | [7 empty] | 406,..,1006 | 406 | 1006
407,..,1007 |  | 1BHK | 372.7035 | 0 | 559.0552 | [7 empty] | 407,..,1007 | 407 | 1007
8th Floor
801 |  | 1BHK | 372.7143 | 0 | 559.0714 | 8th Floor
802 |  | 1BHK | 390.195 | 0 | 585.2925
803 |  | 1BHK | 390.195
804 |  | 1BHK | 390.195 | 0 | 585.2925
805 |  | Refuge Area
806 |  | 1BHK | 372.7035 | 0 | 559.0552
807 |  | 1BHK | 372.7035 | 0 | 559.0552
11th Floor
1101 |  | Terrace Floor |  |  |  | 11th Floor
1102 |  | 1BHK | 390.195 | 0 | 585.2925
1103 |  | 1BHK | 390.195 | 0 | 585.2925
1104 |  | Terrace Floor
F Wing
3rd Floor
301 |  | 1BHK | 390.195 | 0 | 585.2925 | 3rd Floor
302 |  | 2BHK | 583.1935 | 0 | 874.7903
303 |  | 2BHK | 594.1728 | 0 | 891.2592
304 |  | 2BHK | 594.1728 | 0 | 891.2592
305 |  | 2BHK | 583.1935 | 0 | 874.7903
4th to 10th Floor
401 to 1001 |  | 1BHK | 390.195 | 0 | 585.2925 | 4th to 10th Floor | [6 empty] | 401 to 1001 | 401 | 1001
402 to 1002 |  | 2BHK | 583.1935 | 0 | 874.7903 | [7 empty] | 402 to 1002 | 402 | 1002
403 to 1003 |  | 2BHK | 594.1728 | 0 | 891.2592 | [7 empty] | 403 to 1003 | 403 | 1003
404 to 1004 |  | 2BHK | 594.1728 | 0 | 891.2592 | [7 empty] | 404 to 1004 | 404 | 1004
405 to 1005 |  | 2BHK | 583.1935 | 0 | 874.7903 | [7 empty] | 405 to 1005 | 405 | 1005
406 to 1006 |  | 1BHK | 372.6174 | 0 | 558.9261 | [7 empty] | 406 to 1006 | 406 | 1006
407 to 1007 |  | 1BHK | 372.7143 | 0 | 559.0714 | [7 empty] | 407 to 1007 | 407 | 1007
408 to 1008 |  | 1BHK | 372.7143 | 0 | 559.0714 | [7 empty] | 408 to 1008 | 408 | 1008
11th Floor
1101 |  | Terrace Floor |  |  |  | 11th Floor
1102 |  | 2BHK | 583.1935 | 0 | 874.7903
1103 |  | 2BHK | 594.1728 | 0 | 891.2592
1104 |  | 2BHK | 594.1728 | 0 | 891.2592
1105 |  | 2BHK | 583.1935 | 0 | 874.7903
Remarks:
1 | Wing A to F = Construction work increased as compared to last visit (Very Slow Speed). Wing B, C, D & E = Construction work is the same as last visit (07/05/2024). | [6 empty] | is the same as last visit (07/05/2024).
2 | We considered Saleable area as per our calculation. | [6 empty] | Wing B, C, D & E = Construction work is the same as last visit (07/05/2024).
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area.
5 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes).
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | On Site, we meet Mr. Akshay - 8329505038.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ravindra vishwakarma |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Planet 6
Google Map :
C Wing
D Wing
E Wing
F Wing
D Wing

## Sheet1
A Wing |  | B Wing |  |  | C Wing |  |  | D Wing |  |  | E Wing |  | F Wing
1 | 390.195 | 1 | 806.2236 | 273.3303 | 1 | 538.1462 | 273.0612 | 1 | 806.2021 | 280.9189 | 1 | Double Height | 1 | 390.195
2 | 583.1935 | 2 | 801.0784 | 163.8604 | 2 | 538.1354 | 280.6498 | 2 | 790.8634 | 524.1853 | 2 | 390.195 | 2 | 583.1935
3 | 594.1728 | 3 | 572.8601 | 57.0492 | 3 | 564.8409 | 278.7123 | 3 | 497.1353 | 106.5636 | 3 | 390.195 | 3 | 594.1728
4 | 594.1728 | 4 | 583.2043 |  | 4 | 538.1354 | 280.6498 | 4 | 582.8814 |  | 4 | 390.195 | 4 | 594.1728
5 | 583.1935 |  |  |  | 5 | 538.1462 | 273.0612 |  |  |  | 5 | 390.195 | 5 | 583.1935
4th to 10th Floor |  | 4th to 10th Floor |  |  | 4th to 7th, 9th, 10th Floor |  |  | 4th to 10th Floor |  |  | 4th to 7th, 9th, 10th Floor |  | 4th to 10th Floor
1 | 390.195 | 1 | 873.7139 |  | 1 | 599.8239 |  | 1 | 873.6924 |  | 1 | 372.7143 | 1 | 390.195
2 | 583.1935 | 2 | 855.9748 |  | 2 | 599.8131 |  | 2 | 873.5309 |  | 2 | 390.195 | 2 | 583.1935
3 | 594.1728 | 3 | 589.9748 |  | 3 | 620.0602 |  | 3 | 524.2606 |  | 3 | 390.195 | 3 | 594.1728
4 | 594.1728 | 4 | 583.2043 |  | 4 | 599.8131 |  | 4 | 582.8814 |  | 4 | 390.195 | 4 | 594.1728
5 | 583.1935 | 5 | 583.2043 |  | 5 | 599.8239 |  | 5 | 582.8814 |  | 5 | 390.195 | 5 | 583.1935
6 | 372.7143 | 6 | 589.9748 |  | 6 | 575.9924 |  |  |  |  | 6 | 372.7035 | 6 | 372.6174
7 | 372.7143 |  |  |  | 7 | 396.169 |  |  |  |  | 7 | 372.7035 | 7 | 372.7143
8 | 372.7143 |  |  |  | 8 | 396.169 | [6 empty] | 8 | 372.7143
[5 empty] | 9 | 575.9924
[5 empty] | 8th Floor | [5 empty] | 8th Floor
[5 empty] | 1 | 599.8239 |  |  |  |  | 1 | 372.7143
[5 empty] | 2 | 599.8131 |  |  |  |  | 2 | 390.195
[5 empty] | 3 | Refuge Area |  |  |  |  | 3 | 390.195
[5 empty] | 4 | 599.8131 |  |  |  |  | 4 | 390.195
[5 empty] | 5 | 599.8239 |  |  |  |  | 5 | Refuge Area
[5 empty] | 6 | 575.9924 |  |  |  |  | 6 | 372.7035
[5 empty] | 7 | 396.169 |  |  |  |  | 7 | 372.7035
[5 empty] | 8 | 396.169
[5 empty] | 9 | 575.9924
11th Floor |  | 11th Floor |  |  | 11th Floor |  |  | 11th Floor |  |  | 11th Floor |  | 11th Floor
2 | 583.1935 | 1 | 873.7139 |  | 1 | 599.8239 |  | 1 | 873.6924 |  |  |  | 2 | 583.1935
3 | 594.1728 | 2 | 855.9748 |  | 2 | 599.8131 |  | 2 | 873.5309 |  |  |  | 3 | 594.1728
4 | 594.1728 | 3 | 589.9748 |  | 3 | Refuge Area |  | 3 | 524.2606 |  | 3 | 390.195 | 4 | 594.1728
5 | 583.1935 | 4 | 583.2043 |  | 4 | 599.8131 |  | 4 | 582.8814 |  | 4 | 390.195 | 5 | 583.1935
[5 empty] | 5 | 599.8239

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted