## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 22/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group As per RERA |  |  |  | Nagesh Buildtech LLP
Name of the builder company As Per Builder |  |  |  | Vishwagreen Plus LLP
Name of the Project |  |  |  | Plan M Business Park
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Sachin Garg 9322668754 |  |  |  |  | Mr. Nayan 8104972376 /
Site Person - Contact Details (Name & Contact No.) |  |  |  | 9821555414 |  |  |  |  | Photos taken from 10th slab(podium top) Visit date 03/05/2024
Name / No of the Building |  |  |  | Wing A, B & C
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P51700023125
Project location details |  | Plan M Business Park, Plot No.9 & 9A, near Destination India Shopping Mall, Thane - Belapur Road, Turbhe, Turbhe, Turbhe, Thane, Thane - 400706.
Plot No |  | 9 & 9A
Locality |  | Turbhe
Road |  | Thane - Belapur Road |  | Locality/Village |  | Turbhe
City |  | Turbhe |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400706
Nearby Landmark |  | Destination India Shopping Mall |  | Distance from city centre: |  | 0.75 KM from Turbhe Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Thane - Belapur Road
North | NA | NA |  |  | Destination India Shopping Mall
South | NA | NA |  |  | Turbhe Chemicals Pvt. Ltd
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.071659,73.019871
Location Link |  | https://goo.gl/maps/ukxhhJQRXvkCLXZT8?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10010
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 3
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 30030
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Industrial Development Corporation (MIDC)
Layout Approval No |  | EE/Dn.II/MHP/SPA/B24865/2023 |  |  | Dated | 2023-05-17
Approved Floor plan No. |  | EE/Dn.II/MHP/SPA/B24865/2023 |  |  | Dated | 2023-05-17
Commencement-CC No Valid Up to: |  | EE/Dn.II/SPA/A52003/2019 |  |  | Dated | 2019-02-07
A Wing = G + 1st to 6th Floor B Wing = G + 1st to 12th Floor C Wing = G + 1st to 12th Floor
Combined Approval Letter Valid Up to: |  | EE/Dn.II/MHP/SPA/B24865/of2023 |  |  | Dated | 2023-05-17
Plot No. 9/9A Total Builtup Area = 25697.24Sq.m Amended to Approved Floor Plans dtd. 17/05/2023
Airports Authority Of India-NOC No Valid Up to: |  | NAVI/WEST/B/081318/326469 |  |  | Dated | 2018-09-11
|  | 88.29M (AMSL) |  |  | Valid Upto Date | 2026-09-10
Part O. Certificate No.: |  | EE/Dn.II/SPA/MHP/IFMS/E38934/ 2022 Approved upto : Wing A = G + 1st Floor |  |  | Dated | 2022-12-30
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 30030
Approved no of units |  |  | Shopping Outlet - 06, Financial Office - 27, IT Office - 330
Approved no of Floors |  |  | A Wing = G + 1st to 6th Floor B Wing = G + P1 to P8(23.35m) + 6th(26.25m) to 18th Floor C Wing = G + P1 to P8(23.35m) + 6th(26.25m) to 18th Floor
Proposed no of Floors |  |  | A Wing = G + 1st to 6th Floor
B Wing = G + 1st to 29th Floor
C Wing = G + 1st to 29th Floor
C Wing (Part II) = G + 1st to 29th Floor
Expected Completion |  |  | As per RERA - 01/11/2025
Projected life of the structure |  |  | 60 Years after completion |  |  |  |  | 58 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Common Conference Room, Water Body, Cafeteria Cafe, Yoga & Meditation Center, Gymnasium, Indoor Mini Golf, Themed Spa & Salon, Indoor Games, Steam Room With Sauna, Swimming Pool With Jacuzzi etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = G + 1st to 6th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 2 Floor Completed | , Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 6 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.5
Excavation |  | 6 | 100% | 91.67% |  | 95% |  | Excavation in process | 3
Plinth |  | 6 | 100% |  |  |  |  | Excavation Completed | 6
RCC (Including podiums) |  | 7 | 100% |  |  |  |  | Footing in Process | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% |  |  |  |  | Footing Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% |  |  |  |  | Basement 1 | 0
Facade & Plumbing | External Plaster & Plumbing | 6 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 33.33% |  |  |  |  | Plinth in process | 4.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 6
Construction details: |  | B Wing = G + 1st to 29th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 23 Slab, Brickwork upto 18 Floor Completed | , RCC upto 23 Slab, Brickwork upto 18 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 29 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 23 Slab, Brickwork upto 18 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 45.32% |  | 71.1% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 23 | 76.67% |  |  |  |  | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 18 | 62.07% |  |  |  |  | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Facade & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 29
Construction details: |  | C Wing = G + 1st to 29th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 20 Slab, Brickwork upto 17 Floor Completed | , RCC upto 20 Slab, Brickwork upto 17 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 29 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 20 Slab, Brickwork upto 17 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 41.06% |  | 67.93% |  | Excavation in process | 14.5
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 20 | 66.67% |  |  |  |  | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 17 | 58.62% |  |  |  |  | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Facade & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 29
Construction details: |  | C Wing (Part II) = G + 1st to 29th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 9 Slab, Brickwork upto 4 Floor Completed | , RCC upto 9 Slab, Brickwork upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 29 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 9 Slab, Brickwork upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.25
Excavation |  | 29 | 100% | 23.03% |  | 54.69% |  | Excavation in process | 14.5 |  | AS PER SITE MEET PERSON HAMZA ON 04/07/2023
Plinth |  | 29 | 100% |  |  |  |  | Excavation Completed | 29
RCC (Including podiums) |  | 9 | 30% |  |  |  |  | Footing in Process | 7.25
Brickwork | Brickwork & Internal Plaster | 4 | 13.79% |  |  |  |  | Footing Completed | 14.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Facade & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 29
Average Construction of Wing C |  | Progress % |  | 32.05% | Disbursement % |  | 61.31%
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Shopping Outlet Per Sq. Ft. |  |  |  |  | 23000
Recommended rate of the Financial Office Per Sq. Ft. (1st to 6th Floor) |  |  |  |  | 12000
Recommended rate of the IT Office Per Sq. Ft. (1st to 10th Floor) |  |  |  |  | 12000
Recommended rate of the IT Office Per Sq. Ft. (11th to 29th Floor) |  |  |  |  | 11500
Floor Rise Rate
Development Charges |  |  |  |  | 300000
Club Charges |  |  |  |  | 200000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 9600
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shopping Outlet | 6 |  | 15691.7662 |  | 25106.826
| Financial Office | 27 |  | 68453.4773 |  | 109525.5637
Wing B | IT Office | 126 |  | 59191.2898 |  | 94706.0637
Wing C | IT Office | 204 |  | 77817.2347 |  | 124507.5755
Total |  | 363 |  | 221153.768 |  | 353846.0289
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Otla area | Saleable area Loading : | Floor
60%
Wing A
Ground Floor For Commercial
1 |  | Shopping Outlet | 2637.7588 | 0 | 4220.4141 | Ground Floor For Commercial |  | 245.7796 | 245.0538
2 |  | Shopping Outlet | 2608.1131 | 0 | 4172.981 |  |  | 227.6732
3 |  | Shopping Outlet | 2608.1131 | 0 | 4172.981
4 |  | Shopping Outlet | 2608.1131 | 0 | 4172.981
5 |  | Shopping Outlet | 2606.327 | 0 | 4170.1232 |  |  | 460.131
6 |  | Shopping Outlet | 2623.3411 | 0 | 4197.3457 |  |  | 460.131
1st Floor For Commercial | [7 empty] | 10.764
1 |  | Financial Office | 4622.0415 | 0 | 7395.2664 | 1st Floor For Commercial
2 |  | Financial Office | 4586.5849 | 0 | 7338.5358
3 |  | Financial Office | 4599.5365 | 0 | 7359.2583
2nd to 4th Floor For Commercial
1 |  | Financial Office | 2276.8881 | 0 | 3643.021 | 2nd to 4th Floor For Commercial
2 |  | Financial Office | 2276.8881 | 0 | 3643.021
3 |  | Financial Office | 2276.8881 | 0 | 3643.021
4 |  | Financial Office | 2276.8881 | 0 | 3643.021
5 |  | Financial Office | 2276.8881 | 0 | 3643.021
6 |  | Financial Office | 2276.8881 | 0 | 3643.021
5th Floor For Commercial (Refuge Balcony Provided)
1 |  | Financial Office | 2276.8881 | 0 | 3643.021 | 5th Floor For Commercial (Refuge Balcony Provided)
2 |  | Financial Office | 2276.8881 | 0 | 3643.021
3 |  | Financial Office | 2276.8881 | 0 | 3643.021
4 |  | Financial Office | 2276.8881 | 0 | 3643.021
5 |  | Financial Office | 2276.8881 | 0 | 3643.021
6 |  | Financial Office | 2276.8881 | 0 | 3643.021
6th Floor For Lawn & Gazebo
Wing B
Ground Floor For Parking
1st Podium Floor For Electric Room & Parking
2nd to 8th Podium Floor (P1 to P8) For Parking
6th Floor For Food Court & Café Area (Part Terrace Area)
7th Floor For Gym
8th, 10th, 11th, 12th, 14th, 15th, 16th & 18th Floor For Commercial
1 |  | IT Office | 527.7589 | 0 | 844.4143 | 8th, 10th, 11th, 12th, 14th, 15th, 16th & 18th Floor For Commercial |  | 28.5166 |  | 1050 | 1.9895
2 |  | IT Office | 527.7589 | 0 | 844.4143
3 |  | IT Office | 527.7589 | 0 | 844.4143
4 |  | IT Office | 527.7589 | 0 | 844.4143
5 |  | IT Office | 527.7589 | 0 | 844.4143
6 |  | IT Office | 527.7589 | 0 | 844.4143
7 |  | IT Office | 527.7589 | 0 | 844.4143
8 |  | IT Office | 527.7589 | 0 | 844.4143
9 |  | IT Office | 331.8541 | 0 | 530.9666
10 |  | IT Office | 339.1198 | 0 | 542.5917 |  |  |  |  | 1.5
11 |  | IT Office | 339.1198 | 0 | 542.5917
12 |  | IT Office | 331.8541 | 0 | 530.9666
9th, 13th & 17th Floor (Part Refuge Area)
1 |  | IT Office | 527.7589 | 0 | 844.4143 | 9th, 13th & 17th Floor (Part Refuge Area) |  | 28.5166
2 |  | IT Office | 527.7589 | 0 | 844.4143
3 |  | IT Office | 527.7589 | 0 | 844.4143
4 |  | IT Office | 527.7589 | 0 | 844.4143
5 |  | IT Office | 527.7589 | 0 | 844.4143
6 |  | IT Office | 527.7589 | 0 | 844.4143
7 |  | IT Office | 527.7589 | 0 | 844.4143
8 |  | IT Office | 527.7589 | 0 | 844.4143
9 |  | IT Office | 331.8541 | 0 | 530.9666
10 |  | IT Office | 339.1198 | 0 | 542.5917 |  |  |  |  | 1.5
11 |  | Refuge Area
12
Wing C
Ground Floor For Meter Room & Parking
1st to 8th Podium Floor (P1 to P8) For Parking
6th Floor For Cofee Shop, Restaurant & Loung Bar (Part Terrace Area)
7th Floor For Commercial
1 |  | IT Office | 371.4118 | 0 | 594.2589 | 7th Floor For Commercial |  | 28.5166
2 |  | IT Office | 371.4118 | 0 | 594.2589
3 |  | IT Office | 371.4118 | 0 | 594.2589
4 |  | IT Office | 371.4118 | 0 | 594.2589
5 |  | IT Office | 371.4118 | 0 | 594.2589
6 |  | IT Office | 371.4118 | 0 | 594.2589
7 |  | IT Office | 371.4118 | 0 | 594.2589
8 |  | IT Office | 371.4118 | 0 | 594.2589
9 |  | IT Office | 519.955 | 0 | 831.928
10 |  | IT Office | 371.4118 | 0 | 594.2589 |  |  |  |  | 1.5
11 |  | IT Office | 371.4118 | 0 | 594.2589
12 |  | IT Office | 371.4118 | 0 | 594.2589
13 |  | IT Office | 371.4118 | 0 | 594.2589
14 |  | IT Office | 371.4118 | 0 | 594.2589
15 |  | IT Office | 371.4118 | 0 | 594.2589
16 |  | IT Office | 371.4118 | 0 | 594.2589
17 |  | IT Office | 371.4118 | 0 | 594.2589
8th, 10th, 11th, 12th, 14th to 16th & 18th Floor
1 |  | IT Office | 372.8381 | 0 | 596.5409 | 8th, 10th, 11th, 12th, 14th to 16th & 18th Floor |  | 28.5166
2 |  | IT Office | 372.8381 | 0 | 596.5409
3 |  | IT Office | 372.8381 | 0 | 596.5409
4 |  | IT Office | 372.8381 | 0 | 596.5409
5 |  | IT Office | 372.8381 | 0 | 596.5409
6 |  | IT Office | 372.8381 | 0 | 596.5409
7 |  | IT Office | 372.8381 | 0 | 596.5409
8 |  | IT Office | 372.8381 | 0 | 596.5409
9 |  | IT Office | 521.3813 | 0 | 834.21
10 |  | IT Office | 372.8381 | 0 | 596.5409 |  |  |  |  | 1.5
11 |  | IT Office | 372.8381 | 0 | 596.5409
12 |  | IT Office | 372.8381 | 0 | 596.5409
13 |  | IT Office | 372.8381 | 0 | 596.5409
14 |  | IT Office | 372.8381 | 0 | 596.5409
15 |  | IT Office | 372.8381 | 0 | 596.5409
16 |  | IT Office | 372.8381 | 0 | 596.5409
17 |  | IT Office | 372.8381 | 0 | 596.5409
9th, 13th & 17th Floor (Balcony Refuge Area)
1 |  | IT Office | 372.8381 | 0 | 596.5409 | 9th, 13th & 17th Floor (Balcony Refuge Area) |  | 28.5166
2 |  | IT Office | 372.8381 | 0 | 596.5409
3 |  | IT Office | 372.8381 | 0 | 596.5409
4 |  | IT Office | 372.8381 | 0 | 596.5409
5 |  | IT Office | 372.8381 | 0 | 596.5409
6 |  | IT Office | 372.8381 | 0 | 596.5409
7 |  | IT Office | 372.8381 | 0 | 596.5409
8 |  | IT Office | 372.8381 | 0 | 596.5409
9 |  | IT Office | 521.3813 | 0 | 834.21
10 |  | IT Office | 372.8381 | 0 | 596.5409 |  |  |  |  | 1.5
11 |  | IT Office | 372.8381 | 0 | 596.5409
12 |  | IT Office | 372.8381 | 0 | 596.5409
13 |  | IT Office | 372.8381 | 0 | 596.5409
14 |  | IT Office | 372.8381 | 0 | 596.5409
15 |  | IT Office | 372.8381 | 0 | 596.5409
16 |  | IT Office | 372.8381 | 0 | 596.5409
17 |  | IT Office | 372.8381 | 0 | 596.5409
Remarks:
* | Wing A, B & C = Construction work is in process at the time of Visit. Internal Visit was not allowed. (Very Very Slow Speed)
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Open balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As Wing B is mentioned twice in the approved layout and floor plan, we have considered Wing Bifercation as per the sale plan.
* | We have updated approved floor plan of Wing A, B & C (on 03/07/2023).
* | A Builder Name Clarification Letter is attached below.
* | Please provide revised approved plans & CC, As the construction work goes beyond the CC permission, Combined Approval letter and approved plans (Wing B & C = G + 1st to 18th Floor)
* | We have updated Combined Approval Letter on 14/11/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Anish Vishwakarma |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Plan M Business Park
Layout :
Builder Name Clarification Letter :
Google Map :
A Wing
B Wing
C Wing
A
B
C
A
B

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted