## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-11
Name of the builder group |  |  |  |  | M/s.Suraj Estate Developers Pvt Ltd
Name of the builder company |  |  |  |  | M/s.Suraj Estate Developers Pvt Ltd
Name of the Project |  |  |  |  | Ocean Star I
Contect Details ( Name & Contect No.) |  |  |  |  | 2224460707
Name / No of the Building |  |  |  |  | Building No. 1 ( Sale Building)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC, Cost Sheet.
RERA No. |  |  |  |  | P51900007257
Project location details |  | Ocean Star I, F.P. Nos.1198 & 1199, T.P.S IV, Mahim, Kashinath Dhuru Marg, Mahim, Dadar, Mumbai.
F.P. Nos |  | 1198 & 1199, T.P.S IV |  |  | Locality |  | Mahim
Road |  | Kashinath Dhuru Marg |  |  | District |  | Mumbai
City |  | Dadar |  |  | Pin Code |  | 400028
Near by Landmark |  | Rameshwaram Apartment |  |  | Distance from city centre: |  | 1.9Km from Dadar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Road |  | Building |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.0198012,72.829678
Location Link |  | https://goo.gl/maps/sgF5YiM17ESyzjSN6
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 1497.83
Permissible FSI |  |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 3
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 4493.49
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | CHE/CTY/1445/G/N/337(NEW) |  |  |  | Dated | 2024-01-23
Approved Floor plan No. |  | CHE/CTY/1445/G/N/337(NEW) |  |  |  | Dated | 2024-01-23
Commencement Certificate No. Valid Up to: |  | CHE/CTY/1445/G/N/337(NEW)/ FCC/3/Amend |  |  |  | Dated | 2024-02-20
|  | This C.C. is Further. granted upto 40 floor top as per Last Amended Approval dt. 23.01.2024. |  |  |  | Valid upto date: | 2025-08-31 |  |  | 35.9
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2021-07-06 |  | Expected Completion |  | 2026-06-30
Building wise Construction details
Approved area of the building in Sq.Mt |  | 8590.96 |  |  | Approved no of units |  | Sale Flats = 51 Rehab Flats = 9
Approved no of Floors |  | Bldg No.1 (Sale) = B + Gr. + P1 to P7 + 8th Service + 9th to 42nd Floor
Proposed no of Floors |  | Bldg No.1 (Sale) = B + Gr. + P1 to P7 + 8th Service + 9th to 42nd Floor
Material laying at Site: : |  | Bricks, Cement & Steel etc.
Construction details: |  | Bldg No.1 (Sale) = B + Gr. + P1 to P7 + 8th Service + 9th to 42nd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 38 Floor, Internal Plaster upto 32 Floor, External Plaster upto 30 Floor, Flooring upto 9 Floor Completed
Basement | 1 | Ground | 1 | Podium |  | 0 | Floors | 42
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 41 Slab, Brickwork upto 38 Floor, Internal Plaster upto 32 Floor, External Plaster upto 30 Floor, Flooring upto 9 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 10.5
Excavation |  | 42 | 100% |  | 69.93% |  | 86.58% |  | Excavation in process | 21
Plinth |  | 42 | 100% | [5 empty] | Excavation Completed | 42
RCC (Including podiums) |  | 41 | 95.35% | [5 empty] | Footing in Process | 10.5
Brickwork | Brickwork & Internal Plaster | 38 | 90.48% | [5 empty] | Footing Completed | 21 | 39
Internal Plaster | Brickwork & Internal Plaster | 32 | 76.19% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 30 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 21.43% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 31.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 42
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 53000 |  |  |  | 41250
Recommended rate of Parking | [5 empty] | 1600000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 42400
Residential Area Details : Building No. 1 Sale
Building & Wing |  | No. of Flats |  | Total Carpet Area |  |  | Total Saleable Area
Sale |  | 51 |  | 68457.9636 |  |  | 102769.4515
Rehab |  | 9 |  | 6316.3152 |  |  | 9540.4023
Total |  | 60 |  | 74774.2788 |  |  | 112309.8538
Building details Floor Wise | [9 empty] | 36
Details of Flats in Building
Flat No. | Mhada/ Rehab/ Sale | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | Floor
Building No.1 (Sale)
Basement Floor For Parking
Ground Floor For Parking & Entrance Lobby
1st to 6th Podium Floor For Parking
4th & 5th Podium Floor For Parking
6th Podium Floor For Parking
7th Podium Floor For Amenties
Girder Bottom Floor between 7th & 8th Floor
8th Floor used as Service Floor
9th Floor (Part Refuge Area) | [11 empty] | 10.764
1 | Rehab | 1BHK | 487.8245 |  | 0 | 731.7367 | 9th Floor (Part Refuge Area)
2 | - | Refuge Area
3 | Rehab | 1BHK | 487.6092 |  | 0 | 731.4138
10th Floor
1 | Rehab | 1BHK | 531.5263 |  | 0 | 797.2895 | 10th Floor
2 | Rehab | 1BHK | 532.818 |  | 0 | 799.227
3 | Rehab | 1BHK | 490.1926 |  | 0 | 735.2888
11th Floor
1 | Rehab | 2BHK | 771.9941 |  | 0 | 1157.9911 | 11th Floor
2 | Sale | 1BHK | 576.0893 |  | 0 | 864.1339
3 | Sale | 1.5BHK | 427.4384 |  | 0 | 641.1577
12th Floor
1 | Rehab | 2BHK | 843.8976 |  | 131.859 | 1331.7759 | 12th Floor
2 | Rehab | 2.5BHK | 919.2456 |  | 0 | 1378.8684
13th Floor
1 | Sale | 2.5BHK | 1009.2326 |  | 0 | 1513.849 | 13th Floor
2 | Sale | 3BHK | 1088.9939 |  | 0 | 1633.4908
14th & 15th Floor
1 | Sale | 3BHK | 1086.9487 |  | 0 | 1630.4231 | 14th & 15th Floor |  |  | 41706.966
2 | Sale | 3BHK | 1086.9487 |  | 0 | 1630.4231
16th Floor (Part Refuge Area)
1 | Sale | 4BHK | 1628.8085 |  | 0 | 2443.2127 | 16th Floor (Part Refuge Area)
2 | - | Refuge Area
17th Floor
1 | Sale | 3BHK | 1089.3168 |  | 41.253 | 1675.2282 | 17th Floor
2 | Sale | 3BHK | 1089.3168 |  | 41.253 | 1675.2282
18th Floor
1 | Sale | 3BHK | 1090.1779 |  | 0 | 1635.2669 | 18th Floor |  |  | 35162.4562
2 | Sale | 3BHK | 1091.6849 |  | 0 | 1637.5273
19th & 20th Floor
1 | Sale | 3BHK | 1086.3029 |  | 0 | 1629.4543 | 19th & 20th Floor
2 | Sale | 3BHK | 1086.3029 |  | 0 | 1629.4543
21st Floor
1 | Sale | 3BHK | 1251.2074 |  | 0 | 1876.811 | 21st Floor |  |  | 34100.3962
2 | Rehab | 3BHK | 1251.2074 |  | 0 | 1876.811
24th, 25th, 29th, 31st to 36th & 38th to 40th Floor
1 | Sale | 3BHK | 1251.2074 |  | 0 | 1876.811 | 24th, 25th, 29th, 31st to 36th & 38th to 40th Floor |  |  | 34100.3962
2 | Sale | 3BHK | 1251.2074 |  | 0 | 1876.811
22nd Floor
1 | Sale | 3BHK | 1257.0199 |  | 0 | 1885.5299 | 22nd Floor |  |  | 33942.7132
2 | Sale | 1BHK | 1242.3809 |  | 0 | 1863.5713
23rd Floor (Part Refuge Area)
1 | Sale | 3BHK | 1856.0365 |  | 0 | 2784.0548 | 23rd Floor (Part Refuge Area)
2 | - | Refuge Area
26th Floor
1 | Sale | 3BHK | 1250.8844 |  | 0 | 1876.3267 | 26th Floor
2 | Sale | 3BHK | 1250.8844 |  | 0 | 1876.3267
27th(Lower) + 28th Floor (Upper) Duplex Flat
1 | Sale | 4BHK | 4408.0733 |  | 0 | 6612.1099 | 27th(Lower) + 28th Floor (Upper) Duplex Flat
30th Floor (Part Refuge Area)
1 | Sale | 4BHK | 1853.7761 |  | 0 | 2780.6641 | 30th Floor (Part Refuge Area)
2 | - | Refuge Area
37th Floor (Part Refuge Area)
1 | Sale | 4BHK | 1866.5852 |  | 0 | 2799.8779 | 37th Floor (Part Refuge Area)
2 | - | Refuge Area
41st(Lower) + 42nd Floor (Upper) Duplex Flat
1 | Sale | 4BHK | 4408.0733 |  | 0 | 6612.1099 | 41st(Lower) + 42nd Floor (Upper) Duplex Flat
Remarks:
1. Construction work is in process at the time of visit.(Internal Visit Was Not Allowed.) 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Car parking is subjected to authentic documentation. 6. We have updated revised approved floor plan (on 16/02/2024). 7. We have considered construction percent as per proposed no of floor 8. We have updated revised approved CC from MCGM site. (on 07/05/2024). 9. The validity of CC is expired on 31/08/2024. Please provide revised, approved CC. 9. On site, we meet Mr.Vaibhav(Sales person) - 9819739261 7. On site, we meet Mr. Yash(Site Person) - 9130000938 & Mr.Vaibhav(Sales person) - 9819739261
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Karan Misal |  |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Ocean Star I
Google Map :
Formulas:
Mahim = [Mahim, row above]

## Sheet1
1 | 2201,….,2601 | 2201,….,2601
2 | 2202,….,2602 | 2202,….,2602
3 | 2203,….,2603 | 2203,….,2603

## C%
Particulars | totaL floor | 29
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 30 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 30 | 9 | 27.5862 | Progress |  |  | 10 | 12 | 4.1379 | 1.3793 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 13.7931 | Recommended |  |  | 30 | 9 | 4.1379 | 1.3793 | 0 | 0 | 0
| 29 | 8 | 0
plaster | Total Floor | completed Floor | 0
| 29 | 4 | 0
Flooring | Total Floor | completed Floor
| 29 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 29 | 0 |  | RCC | 12 | 9
Finishing | Total Floor | completed Floor |  | Bricks | 4.1379 | 4.1379
| 29 | 0 |  | Plaster | 1.3793 | 1.3793
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 27.5172 | 44.5172

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Ocean Star I | 3BHK | 0 | 1743 | 39013.1956 | 68000000
99 Acres | Ocean Star I | 3BHK | 0 | 1747 | 32913.5661 | 57500000 | 33000
99 Acres | Ocean Star I | 3BHK | 1221 | 1953.6 | 32760.0328 | 64000000
99 Acres | Ocean Star I | 4BHK | 1221 | 1953.6 | 37110.9746 | 72500000
Average |  |  |  |  | 35449.4423
Valuation Adopted |  |  |  |  | 35500

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0