## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-14
Name of the builder |  |  |  |  | M/s.Puranik Builders Private Limited
Name of the builder company |  |  |  |  | M/s.Puranik Builders Private Limited
Name of the Project |  |  |  |  | Puranik City - Sector 3 | [5 empty] | Puranik City - Sector 3
Contact Details ( Name & contact No.) |  |  |  |  | 2225988888
Site Person Details ( Name & contact No.) |  |  |  |  | Mr.Sameer Jamghere - 9284439176
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC.
RERA Number : |  |  |  |  | P52000017953
Project location details |  | Puranik City, SubPlot no. 18 - Sector 3, S.No. 58, 60/78, 64/7, 134/1,2,3,4,5, Neral-Gdhawan Road, Village - Pimploli, Neral, Post- Sugawe, Taluka- Karjat, Raigad.
Plot No | 18 | S No /G. No | S.No. 58, 60/78, 64/7, 134/1,2,3,4,5 |  |  |  | Locality | Pimploli
Road | Neral-Gdhawan Road |  |  |  | District | Karjat
City | Neral |  |  |  | Pin Code | 410201
RERA Number : |  | SubPlot no. 18 - Sector 3 : P52000017953
No of the Buildings |  | SubPlot no. 18 - Sector 3 (08 Buildings) = |  |  | Building Type GBC (G + 7 Floors) Building Type HB1 (G + 7 Floors) Building Type JAC (G + 4 Floors) Building Type JB (G + 7 Floors) Building Type LB1 (G + 7 Floors) Building Type LB2 (G + 7 Floors) Building Type LB3 (G + 7 Floors) Building Type PB (G + 7 Floors)
Near by Landmark |  | Puranik Future City |  |  | Distance from city centre: |  | About 4.8 KM from Neral Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 5 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot |  | Road |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.029459,73.349686
Location Link |  | https://goo.gl/maps/351hZrBRdkxxXrBi9
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 33953.56
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 0.2
Total FSI availaible for the project |  |  |  |  | 1.3
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 428667.86
Total number of Buildings |  |  |  |  | 08 Buildings
Approval Detail : Plan approval
Layout Approval No |  | MSHA/L.N.A.1(B)/P.NO.95/2016. |  |  |  | Dated | 12/02/2018.
Building plan approval No |  | MSHA/L.N.A.1(B)/P.NO.95/2016. |  |  |  | Dated | 12/02/2018.
NA Order Cum Commencement Certificate |  | MSHA/L.N.A.1(B)/P.NO.95/2016. Valid Upto : All buildings = G + 7th Floors Building JAC = G + 4 Floors |  |  |  | Dated | 12/02/2018. | Expiry date: One year from date of issue
O. Certificate No.: |  | NA |  |  |  | Dated | NA
Commencement date of construction |  |  | 12/02/2018. |  | Expected Completion |  | 01/09/2028.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 428667.86 |  | Approved no of units |  | Shops = 23 & Flats = 451
Approved no of Floors |  | All buildings = G + 1st to 7th Floor Building JAC = G + 1st to 4 Floor
Quality of construction: Good |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Brick, cement, sand etc
Construction details: |  | Bldg Type JAC = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 10% |  | 45% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Bldg Type JB = G + 1st to 7th Floor Bldg Type LB1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work is process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work is process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 7.5% |  | 38.75% |  | Excavation in process | 3.5
Plinth |  | 5.25 | 75% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Bldg Type GBC = G + 1st to 7th Floor Bldg Type HB1 = G + 1st to 7th Floor Bldg Type LB3 = G + 1st to 7th Floor Bldg Type PB = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Bldg Type HB1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Bldg Type LB1 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work is process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work is process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 7.5% |  | 38.75% |  | Excavation in process | 3.5
Plinth |  | 5.25 | 75% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Bldg Type LB2 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Footing work Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Footing work Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 5% |  | 32.5% |  | Excavation in process | 3.5
Plinth |  | 3.5 | 50% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Bldg Type LB3 = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Bldg Type PB = G + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 0 | 0% | [5 empty] | Footing in Process | 1.75
Brickwork |  | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Under construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4300
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Maintenence charges for 12 months | [5 empty] | 18,000/-
Society formation charges | [5 empty] | NA
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3440
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Sub Plot no.18 - Sector 3
Building Type GBC (G + 7 Floors)
Ground Floor
1 |  | Shop | 120.5568 |  | 0 | 180.8352 | N | Ground
2 |  | Shop | 213.5578 |  | 0 | 320.3366 | N | Ground
3 |  | Shop | 206.4535 |  | 0 | 309.6803 | N | Ground
4 |  | Shop | 304.7288 |  | 0 | 457.0933 | N | Ground
5 |  | Shop | 323.8888 |  | 0 | 485.8331 | N | Ground
6 |  | Shop | 323.8888 |  | 0 | 485.8331 | N | Ground
7 |  | Shop | 304.7288 |  | 0 | 457.0933 | N | Ground
8 |  | Shop | 206.4535 |  | 0 | 309.6803 | N | Ground
9 |  | Shop | 213.5578 |  | 0 | 320.3366 | N | Ground
10 |  | Shop | 120.5568 |  | 0 | 180.8352 | N | Ground
1 |  | Entrance Lobby & Society Office | [5 empty] | Ground
2 |  | 2 BHK | 437.35 |  | 0 | 634.1575 | N | Ground
7 |  | 2 BHK | 437.35 |  | 0 | 634.1575 | N | Ground
8 |  | 2 BHK | 491.54 |  | 0 | 712.733 | N | Ground
1st to 7th Floors
1 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
2 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
3 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
4 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
5 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
6 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
7 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
8 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
Building Type HB1 (G + 7 Floors)
Ground Floor For Residential
1 |  | 2 BHK | 491.54 |  | 0 | 712.733 | N | Ground
2 |  | 2 BHK | 491.17 |  | 0 | 712.1965 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 2 BHK | 436.99 |  | 0 | 633.6355 | N | Ground
5 |  | 2 BHK | 437.35 |  | 0 | 634.1575 | N | Ground
6 |  | 2 BHK | 491.17 |  | 0 | 712.1965 | N | Ground
1st to 7th Floors
1 |  | 2 BHK | 515.65 |  | 0 | 747.6925 | N | 1st to 7th
2 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
3 |  | 2 BHK | 514.8 |  | 0 | 746.46 | N | 1st to 7th
4 |  | 2 BHK | 464.2 |  | 0 | 673.09 | N | 1st to 7th
5 |  | 2 BHK | 465.61 |  | 0 | 675.1345 | N | 1st to 7th
6 |  | 2 BHK | 515.52 |  | 0 | 747.504 | N | 1st to 7th
Building Type JAC (G + 4 Floors)
Ground Floor
1 |  | Shop | 90.2023 |  | 0 | 135.3035 | N | Ground
2 |  | Shop | 187.8318 |  | 0 | 281.7477 | N | Ground
3 |  | Shop | 176.099 |  | 0 | 264.1486 | N | Ground
4 |  | Shop | 185.679 |  | 0 | 278.5185 | N | Ground
5 |  | Shop | 128.3607 |  | 0 | 192.5411 | N | Ground
6 |  | Shop | 113.8831 |  | 0 | 170.8247 | N | Ground
7 |  | Shop | 124.0013 |  | 0 | 186.0019 | N | Ground
8 |  | Shop | 120.1801 |  | 0 | 180.2701 | N | Ground
9 |  | Shop | 128.393 |  | 0 | 192.5895 | N | Ground
10 |  | Shop | 185.679 |  | 0 | 278.5185 | N | Ground
11 |  | Shop | 176.099 |  | 0 | 264.1486 | N | Ground
12 |  | Shop | 187.8318 |  | 0 | 281.7477 | N | Ground
13 |  | Shop | 90.2023 |  | 0 | 135.3035 | N | Ground
1 |  | 1 BHK | 368.43 |  | 0 | 534.2235 | N | Ground
2 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
7 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
1st to 4th Floors
1 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 4th
2 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 4th
3 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 4th
4 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 4th
5 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 4th
6 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 4th
7 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 4th
8 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 4th
Building Type JB (G + 7 Floors)
Ground Floor
1 |  | 1 BHK | 368.43 |  | 0 | 534.2235 | N | Ground
2 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
3 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
4 |  | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
5 |  | 1 BHK | 367.55 |  | 0 | 532.9475 | N | Ground
6 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
7 |  | 1 BHK | 426.79 |  | 0 | 618.8455 | N | Ground
8 |  | Entrance Lobby & Society Office | [5 empty] | Ground
1st to 7th Floors
1 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
2 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
3 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
4 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
5 |  | 1 BHK | 397.39 |  | 0 | 576.2155 | N | 1st to 7th
6 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
7 |  | 1 BHK | 455.25 |  | 0 | 660.1125 | N | 1st to 7th
8 |  | 1 BHK | 398.27 |  | 0 | 577.4915 | N | 1st to 7th
Building Type LB1 (G + 7 Floors)
Ground Floor
1 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
2 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | Ground
5 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
6 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | Ground
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 352.16 |  | 0 | 510.632 | N | 1st to 7th
2 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
3 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | 1st to 7th
5 |  | 1 BHK | 352.05 |  | 0 | 510.4725 | N | 1st to 7th
6 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | 1st to 7th
Building Type LB2 (G + 7 Floors)
Ground Floor
1 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
2 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | Ground
5 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
6 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | Ground
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 352.16 |  | 0 | 510.632 | N | 1st to 7th
2 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
3 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | 1st to 7th
5 |  | 1 BHK | 352.05 |  | 0 | 510.4725 | N | 1st to 7th
6 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | 1st to 7th
Building Type LB3 (G + 7 Floors)
Ground Floor
1 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
2 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
3 |  | Entrance Lobby & Society Office | [5 empty] | Ground
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | Ground
5 |  | 1 BHK | 323.68 |  | 0 | 469.336 | N | Ground
6 |  | 1 BHK | 323.44 |  | 0 | 468.988 | N | Ground
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | Ground
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 352.16 |  | 0 | 510.632 | N | 1st to 7th
2 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
3 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
4 |  | 1 RK | 213.91 |  | 0 | 310.1695 | N | 1st to 7th
5 |  | 1 BHK | 352.05 |  | 0 | 510.4725 | N | 1st to 7th
6 |  | 1 BHK | 351.91 |  | 0 | 510.2695 | N | 1st to 7th
7 |  | 1 RK | 213.97 |  | 0 | 310.2565 | N | 1st to 7th
8 |  | 1 RK | 213.48 |  | 0 | 309.546 | N | 1st to 7th
Building Type PB (G + 7 Floors)
Ground Floor
1 |  | Entrance Lobby & Society Office | [5 empty] | Ground
2 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
3 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
4 |  | 1 BHK | 329.49 |  | 0 | 477.7605 | N | Ground
5 |  | 1 BHK | 329.49 |  | 0 | 477.7605 | N | Ground
6 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
7 |  | 1 BHK | 368.48 |  | 0 | 534.296 | N | Ground
8 |  | 1 BHK | 329.59 |  | 0 | 477.9055 | N | Ground
1st to 7th Floors
1 |  | 1 BHK | 357.96 |  | 0 | 519.042 | N | 1st to 7th
2 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
3 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
4 |  | 1 BHK | 357.85 |  | 0 | 518.8825 | N | 1st to 7th
5 |  | 1 BHK | 357.85 |  | 0 | 518.8825 | N | 1st to 7th
6 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
7 |  | 1 BHK | 398.32 |  | 0 | 577.564 | N | 1st to 7th
8 |  | 1 BHK | 357.96 |  | 0 | 519.042 | N | 1st to 7th
Remarks: 1. Type JAC, LB3 = Construction work is stopped. Work was same as last visit (12/04/2023). Type GBC, PB, JB, LB2 = Construction work was same as last visit (21/09/2022). Type LB1 & HB1 = Construction work was same as last visit (20/03/2021). (Construction work has stopped for a long time, so we are unable to take photos.) 2. Saleable Area is as per our calculation. 3. We considered carpet area as per approved plan. 4. Shop rate is given as per our valuation. 5. We considered Flat rate as per Market inquiry. 6. At some places leveling work is started (Cutting & Filling). 7. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 8. General Chargers as in cost sheet are not same for all flats so it is not mentioned in report. 9. We are not considering ground floor of HB1 because Entance Lobby in Approved plan is placed on place of Flat no.3 & in sale Plan it is placed on place of Flat no.6. 10. In Sector 3, HB2 and MA are proposed & Sale Plan of it are not provided to us so area details are not mentioned in report. 11. The project has received Complete CC on 12/02/2018, But Construction work is still incomplete. 11.On site, we meet Mr. Pankaj Chavan - 8976378372.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The Saleable Area is as per our calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY OF CUSTOMER: |  |  |  |  | Puranik City - Sector 3
Google Map :

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
magicbricks | Puranik City | 1BHK | 0 | 322 | 5776.3975 | 1860000
magicbricks | Puranik City | 2BHK | 0 | 427 | 5620.6089 | 2400000
magicbricks | Puranik City | 1BHK | 0 | 378 | 6058.2011 | 2290000
magicbricks | Puranik City | 2BHK | 0 | 750 | 4666.6667 | 3500000
housing | Puranik City | 1BHK | 367 | 532.15 | 4697.9235 | 2500000
housing | Puranik City | 1BHK | 368 | 533.6 | 4696.4018 | 2506000
housing | Puranik City | 5BHK | 427 | 619.15 | 4603.0849 | 2850000
housing | Puranik City | 5BHK | 437 | 633.65 | 4603.4877 | 2917000
Average |  |  | 0 | 0 | 5090.3465
Valuation Adopted |  |  |  |  | 5000

## NOTE
03/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.

## Construction % (2) (hidden)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress | 10 | 40 | 15 | 10 | 1.4286 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 30 | 15 | 10 | 0.71429 | 0 | 0
| 7 | 7 | 100
plaster | Total Floor | completed Floor
| 7 | 7 | 100
Flooring | Total Floor | completed Floor
| 7 | 1 | 14.2857 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 7 | 0 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  |  | Bricks | 15 | 15
| 7 | 0 | 0 |  | Plaster | 10 | 10
[5 empty] | Flooring | 1.4286 | 0.71429
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 76.4286 | 85.7143

## Construction % (3) (hidden)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 0 | 20
| 4 | 0 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 0 | 20