## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | M/s.Rajesh D Yadav
Name of the builder company |  |  |  | M/s.Shree Balaji Devlopers
Name of the Project |  |  |  | Prish Apartment
Contact Details ( Name & Contact No.) |  |  |  | 8412913250
Name / No of the Building |  |  |  | Type A8 - E Wing
Docouments Provided |  |  |  | Approved Plans, CC, Builder area sheet, cost sheet
RERA No. |  |  |  | P99000028590
Project location details |  | Prish Apartment, Gut No.144, near Abhi Paradise, Internal Road, Zanzroli, Kelve Road, Palghar, Palghar - 401401.
Gut No |  | 144
Road |  | Internal Road |  | Village |  | Zanzroli
City |  | Kelve Road |  | District |  | Palghar
Taluka |  | Palghar |  | Pin Code |  | 401401
Nearby Landmark |  | Abhi Paradise |  | Distance from city centre: |  | 1.5Km from Kelve Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | U/C Building
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | U/C Building
South | NA | NA |  |  | U/C Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.622756,72.7957918
Location Link |  | https://goo.gl/maps/7ECM33tP9XXPMZkN7?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 10167.73
Permissible FSI |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  | 0.18
Total FSI availaible for the project |  |  |  | 1.08
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10981.15
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | MHASUL/KS.1/T.1/VSP/SR/C.R-241/17 |  |  | Dated | 16/02/2018.
Approved Floor plan No. |  | MHASUL/KS.1/T.1/VSP/SR/C.R-241/17 |  |  | Dated | 16/02/2018.
Commencement Certificate No. |  | MHASUL/KS.1/T.1/ANAP/SR-241/2017 |  |  | Dated | 16/02/2018.
Valid Up to: Type A8 = Gr + 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10981.15
Approved no of units |  |  | Flats - 27
Approved no of Floors |  |  | Type A8 = Gr + 1st to 4th Floor
Proposed no of Floors |  |  | Type A8 = Gr + 1st to 5th Floor
Expected Completion |  |  | As per RERA - 30/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | Type A8 = Gr + 1st to 5th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 2 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 69% |  | 87% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 40% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 5
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 3300 |  |  | 3500 to 3300 | Sachin | 2023-08-21 | market inquiry
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 100000/-
Distressed valuation of the Property |  |  |  |  | 2640
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flat |  | 27 |  | 8565.3454 |  | 15020
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Type A8 - E Wing
Ground Floor for Residential & Parking
1 |  | 1BHK | 319.2602 | 0 | 560 | Ground Floor for Residential & Parking |  | 1.7541
2 |  | 1BHK | 312.6942 | 0 | 550 | Ground Floor for Residential & Parking
3 |  | 1BHK | 313.7706 | 0 | 550 | Ground Floor for Residential & Parking
4 |  |  |  |  | #REF! | Ground Floor for Residential & Parking
5 |  |  |  |  | #REF! | Ground Floor for Residential & Parking
6 |  |  |  |  | #REF! | Ground Floor for Residential & Parking
7 |  |  |  |  | #REF! | Ground Floor for Residential & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
1st to 4th Floor | [11 empty] | to |  | 1st | 4
101 to 401 |  | 1BHK | 322.92 | 0 | 565 | 1st to 4th Floor | [5 empty] | 101 to 401 | 1 | 101 | 401
102 to 402 |  | 1BHK | 322.92 | 0 | 565 | 1st to 4th Floor | [5 empty] | 102 to 402 | 2 | 102 | 402
103 to 403 |  | 1BHK | 319.2602 | 0 | 560 | 1st to 4th Floor | [5 empty] | 103 to 403 | 3 | 103 | 403
104 to 404 |  | 1BHK | 312.6942 | 0 | 550 | 1st to 4th Floor |  | 2636.3636 |  |  |  | 104 to 404 | 4 | 104 | 404
105 to 405 |  | 1BHK | 313.5553 | 0 | 550 | 1st to 4th Floor | [5 empty] | 105 to 405 | 5 | 105 | 405
106 to 406 |  | 1BHK | 313.5553 | 0 | 550 | 1st to 4th Floor | [5 empty] | 106 to 406 | 6 | 106 | 406
Remarks:
1. Construction work is same as last visit (dtd. 07/02/2025) in process at the time of visit.( Very Slow Speed) 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 7. Car parking is subjected to authentic documentation. 8. We have considered proposed No. of Floor for Stage Calculation. 9. Construction work goes beyond approved no. of floor. Please provide Approved plans & CC. 10. Since the project has received first CC on 16/02/2018., But construction work of Prish Apartment is under construction. 7. On Site, we meet Mr. Pritish Patil - 8793631192
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnesh Patil |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Prish Apartment
Google Map :

## C%
Construction details: Building No. = | [6 empty] | Plinth work completed
Ground | 1 |  | Podium | 3 | Floors | 42 | All work Completed. Wait For OC.
Stage of construction: | Plinth work completed | [5 empty] | All work Completed. Provide OC.
Type of Work | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth | 10 | 100% | 10% |  | 30%
RCC Slab | 0 | 0% |  |  |  |  | Excavation in process | 1% | 2%
Brick | 0 | 0% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster | 0 | 0% |  |  |  |  | Footing in Process | 4% | 8%
Flooring | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
|  |  | 10% |  | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.5 | 2.9 | 13.05 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 1.88 | 2.13 | 4.0044 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.9 | 1.07 | 2.033 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 205.4568 | 19.0874 |  |  | 0 | 0 |  | 0 | 0
|  |  | 205.4568 | 19.0874

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Prish Apartment | 1BHK | 312 | 452.4 | 3205.1282 | 1450000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted