## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-13
Name of the builder group |  |  |  |  | M/s.Radha Krishna Realty
Name of the builder company |  |  |  |  | M/s.Radha Krishna Realty
Name of the Project |  |  |  |  | Radha Krishna Residency
Contact Details ( Name & Contact No.) |  |  |  |  | 9867339630
Name / No of the Building |  |  |  |  | Building No.1(A & B Wing) Building No.3(A & B Wing)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA Name & No. |  |  |  |  | P99000020418
Project location details |  | Radha Krishna Residency, Survey No.99/1/B, .Adarsh Nagar, Internal Road, Tembhode, Palghar, Palghar, Palghar.
Survey No |  | 99/1/B |  |  |  |  | Adarsh Nagar
Road |  | Internal Road |  |  | Village |  | Tembhode
City |  | Palghar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401404
Near by Landmark |  | Garden Court Apartment |  |  | Distance from city centre: |  | About 2.6Km from Palghar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Building |  | Open Plot |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.692750,72.755703
Latitude & Longitude |  | https://goo.gl/maps/rqSRaw4rQeTLJ2if6
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 5022
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5022
Total number of Buildings |  |  |  |  | 04 Wings
Approval Detail : Plan approval
Layout Approval No |  | CBPPE/RB/2022/APL/00015 |  |  |  | Dated | 2022-05-20
Approved Floor plan No. |  | CBPPE/RB/2022/APL/00015 |  |  |  | Dated | 2022-05-20
Commencement Certificate No. |  | CBPPE/RB/2022/APL/00015 |  |  |  | Dated | 2022-05-20 | Valid upto date: One year from date of issue
Valid Up to: Building No.1(A Wing) - Gr. + 1st to 5th Floor Building No.1(B Wing) - Gr. + 1st to 5th + 6th (Pt)Floor Building No.3(A Wing) - Gr. + 1st to 5th Floor Building No.3(B Wing) - Gr. + 1st to 5th + 6th (Pt)Floor
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 2019-02-05 |  | Expected Completion |  | 2026-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 5580 |  | Approved no of units |  | Flats = 126
Approved no of Floors |  | Building No.1(A Wing) - Gr. + 1st to 5th Floor Building No.1(B Wing) - Gr. + 1st to 5th + 6th (Pt) Floor Building No.3(A Wing) - Gr. + 1st to 5th Floor Building No.3(B Wing) - Gr. + 1st to 5th + 6th (Pt) Floor
Proposed no of Floors |  | Building No.1(A Wing) - Gr. + 1st to 6th Floor Building No.1(B Wing) - Gr. + 1st to 5th + 6th (Pt) Floor Building No.3(A Wing) - Gr. + 1st to 5th Floor Building No.3(B Wing) - Gr. + 1st to 5th + 6th (Pt) Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Building No.1(A Wing) - Gr. + 5th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 4 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 84% |  | 93% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 80% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 80% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 60% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3.75
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.1(B Wing) - Gr. + 6th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 6
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.5
Excavation |  | 6 | 100% |  | 50.54% |  | 74.88% |  | Excavation in process | 3
Plinth |  | 6 | 100% | [5 empty] | Excavation Completed | 6
RCC |  | 6 | 85.71% | [5 empty] | Footing in Process | 1.5
Brickwork | Brickwork & Internal Plaster | 5 | 83.33% | [5 empty] | Footing Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 4.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 6
Construction details: |  | Building No.3(A Wing) - Gr. + 1st to 5th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 5
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% |  | 100% |  | 100% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% | [5 empty] | Excavation Completed | 5
RCC |  | 6 | 100% | [5 empty] | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 5 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 100% | [5 empty] | Plinth in process | 3.75
Possession |  | 5 | 100% | [5 empty] | Plinth completed | 5
Construction details: |  | Building No.3(B Wing) - Gr. + 1st to 5th + 6th (Pt) Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 6
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.5
Excavation |  | 6 | 100% |  | 100% |  | 100% |  | Excavation in process | 3
Plinth |  | 6 | 100% | [5 empty] | Excavation Completed | 6
RCC |  | 7 | 100% | [5 empty] | Footing in Process | 1.5
Brickwork | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Footing Completed | 3
Internal Plaster | Brickwork & Internal Plaster | 6 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 6 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 100% | [5 empty] | Plinth in process | 4.5
Possession |  | 6 | 100% | [5 empty] | Plinth completed | 6
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [9 empty] | 3500 to 4200 | rushikesh | 2023-04-29 | cost sheet
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4200
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society Formation charges | [5 empty] | 100000 |  |  |  | 450000
Society & Other charges | [5 empty] | 90000 |  |  |  | 450000
Development charges | [5 empty] | 150000 |  |  |  | 450000
Recommended rate of Parking | [5 empty] | 100000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3360
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No.1 (A Wing) |  | 20 | 6444.6759 |  |  | 9344.7801
Building No.1 (B Wing) |  | 34 | 12061.6271 |  |  | 17489.3593
Building No.3 (A Wing) |  | 24 | 8477.9417 |  |  | 12293.0154
Building No.3 (B Wing) |  | 48 | 16903.5703 |  |  | 24510.177
Total |  | 126 | 43887.815 |  |  | 63637.3318
Building details Floor Wise
Details of Flats in Building
Flat No. (As per Sale Plan) | Flat No. (As per Approved Plan) | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building No.1
A Wing
Ground Floor for Parking
1st to 5th Floor for Residential
1 |  | 1BHK | 335.9175 |  | 0 | 487.0804 | N | 1st to 5th Floor for Residential
2 |  | 1BHK | 327.6831 |  | 0 | 475.1405 | N
3 |  | 1BHK | 312.6673 |  | 0 | 453.3676 | N |  |  | 2150000 | 46.9579 | 1813470.282
4 |  | 1BHK | 312.6673 |  | 0 | 453.3676 | N |  |  | 250000
Building No.1 | [9 empty] | 1900000 | 336529.718
B Wing | [9 empty] | 4190.86
Ground Floor for Parking
1st to 5th Floor for Residential
1 |  | 1BHK | 312.6673 |  | 0 | 453.3676 | N | 1st to 5th Floor for Residential
2 |  | 1BHK | 312.6673 |  | 0 | 453.3676 | N
3 |  | 1BHK | 335.5408 |  | 0 | 486.5341 | N
4 |  | 2BHK | 508.7874 |  | 0 | 737.7417 | N
5 |  | 1BHK | 339.2813 |  | 0 | 491.9579 | N
6 |  | 1BHK | 313.7975 |  | 0 | 455.0064 | N
6th Floor (Part Terrace Area)
1 |  | 1BHK | 312.6673 |  | 0 | 453.3676 | N | 6th Floor (Part Terrace Area)
2 |  | 1BHK | 312.6673 |  | 0 | 453.3676 | N
3 |  | 2BHK | 508.7874 |  | 0 | 737.7417 | N
4 |  | 1BHK | 313.7975 |  | 0 | 455.0064 | N
Building No.3
A Wing
Ground Floor for Residential
1 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N | Ground Floor for Residential
2 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
3 |  | 1BHK | 335.2717 |  | 0 | 486.144 | N
4 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N
1st To 4th Floor
1 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N | 1st To 4th Floor
2 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
3 |  | 1BHK | 335.2717 |  | 0 | 486.144 | N
4 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N
5th Floor
1 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N | 5th Floor
2 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
3 |  | 1BHK | 335.2717 |  | 0 | 486.144 | N
4 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N
B Wing
Ground Floor for Residential, Amenties & Parking
1 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N | Ground Floor for Residential, Amenties & Parking
2 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
3 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
4 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
1st To 4th Floor
1 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N | 1st To 4th Floor
2 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N
3 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
4 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
5 |  | 1BHK | 335.191 |  | 0 | 486.0269 | N
6 |  | 1BHK | 335.191 |  | 0 | 486.0269 | N
7 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
8 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
5th Floor
1 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N | 5th Floor
2 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N
3 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
4 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
5 |  | 1BHK | 335.191 |  | 0 | 486.0269 | N
6 |  | 1BHK | 335.191 |  | 0 | 486.0269 | N
7 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
8 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
6th Floor (Part Terrace Area)
1 |  | 2BHK | 458.6809 |  | 0 | 665.0874 | N | 6th Floor (Part Terrace Area)
2 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
3 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
4 |  | 1BHK | 309.5188 |  | 0 | 448.8023 | N
Remarks:
1. Building No.1 (Wing A & B ) = Construction work is in process at the time of Visit. Building No.3 (A & B Wing) = All work Completed. Please provide OC. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We have considered construction percent as per proposed no of floor 9. We have updated revised plans & CC (on 25/04/2023). 10. We met on site Mr. Vikas Yadav 8356003435 . | [8 empty] | Construction Building No.1 (Wing B) = Construction work is in process at the time of Visit.work is Same as last visit (dtd. 08/02/2025) but work is in process at the time of Visit. (Slow Speed).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Radha Krishna Residency
Google Map :
Formulas:
Tembhode = [Tembhode, row above]
Building No.3
Building No.1(A Wing)
Building No.1(B Wing)
Building No.3
Bldg No. 1B
Bldg No. 1A
Bldg No. 1A
Bldg No. 1B

## B1
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 2
Particulars | total floor | 2
plinth | 10 | 0 | 0%
slab | 3 | 0 | 0% |  | Parking |  | Rate
Bricks | 2 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 2 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 2 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 2 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 2 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 0 | 20 |  | Progress |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 0% | 20% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B3-A% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 1 | 25% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 2.5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 2.5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 2.5 | 2.5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 67.5% | 77.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B3-B% (3)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 1 | 25% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 2.5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 2.5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 2.5 | 2.5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 67.5% | 77.5% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B1-A% (3)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 10% | 30% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## B1-B% (4)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 7 | 70%
slab | 5 | 0 | 0% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 7 | 27 |  | Progress |  | 7 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 27 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 7% | 27% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
Date | Checked By | Description
23/07/2020. |  | 1. On Site, we meet Mr. Vikas Yadav(Supervisor) - 8356003435. As per his information rate of flat is 3500/-sqft.
22/03/2021 | Pratiksha

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 4.3 | 2.75 | 11.825 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.45 | 2.15 | 5.2675 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.75 | 7.5625 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.05 | 2.75 | 8.3875 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 2.15 | 2.58 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 2.15 | 2.58 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.9 | 2.45 | 2.205 |  |  |  | 0 |  |  | 0
| passage2 | 0.9 | 2.2 | 1.98 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 456.259 | 42.3875 |  |  | 0 | 0 |  | 0 | 0
|  |  | 456.259 | 42.3875